## Slide 1: Project Consistency workshop
Session 1: Supplementary Background Information

## Slide 2: Meet the Instructors
      John Doe
      TXDOT
      Tel. (512) XXX-XXXX
      John.doe@txdot.gov
      Jane Doe
      TXDOT
      Tel. (512) XXX-XXXX
      Jane.doe@txdot.gov

## Slide 3: Target Audience and Workshop Goal
New and experienced staff at TxDOT Districts, Divisions, and MPOs.
Goal of the Workshop:
  To help TxDOT staff set up communication process to minimize unintended delays due to inconsistencies during the project development process.
  To address project inconsistency by establishing and implementing a set of recommended procedures.

## Slide 4: Project Inconsistency Solution
Key Elements to Maintain Consistency:
  Communication is the key
  Understand how the overall project development process works
  Know your tools and resources
  Know your role and responsibility in the overall project development process
  Establish and document procedures to maintain project consistency
Notes: Note to Speaker: emphasize that this workshop provides a set of solutions for maintaining project consistency. These solutions consists of a set of procedures that the participants need to establish as part of their routine tasks and responsibilities. These procedures are simple elements that complement their routine tasks.

## Slide 5: Session 1 Objectives
Help TxDOT staff to gain a broader perspective regarding their place and role in the project development process.
Provide an overview of subjects supporting the project consistency management:
  Transportation Planning and Programming.
  Project Development Process.
  Environmental Review Process.
  Transportation Conformity.
Notes: There are two goals for the workshop.
First, to provide TxDOT project delivery team and their MPO counterparts with the information they need to develop a project consistency maintenance plan in order to minimize the risk of project inconsistency; and second, to offer a set of best practices and tools to detect and correct an inconsistency before it causes an extensive delay to the project.

## Slide 6: Section 1: Overview For more information refer to Chapter 1 of Supplementary Information Document

## Slide 7: Why Care about Project Consistency?
Streamlined project delivery important goal of TxDOT leadership.
Required by federal and state statutory and regulatory laws.
Inconsistencies can caused delayed federal funding.
Critical for projects in nonattainment and maintenance areas.
For more information on project consistency refer to Part A: Project Consistency Management Guidebook.
Notes: Federal and state transportation planning and regulatory laws require transportation projects to be consistent with transportation plans and programs before the Federal Highway Administration (FHWA) or the Federal Transit Authority (FTA) can approve and sign off on a project.
Any unnecessary delay in the project delivery process may exacerbate the cost of the project. Federal and state transportation planning statutory and regulatory laws require transportation projects to be consistent with transportation plans (MTP/RTP) and programs (TIP and STIP) before the Federal Highway Administration (FHWA) or the Federal Transit Authority (FTA) can approve and sign off on a project.
Significant delays in project delivery can potentially occur as the federal funding would be withheld for such projects and FHWA/FTA would not authorize their construction until the inconsistencies are fully addressed.
Critical for projects in nonattainment and maintenance areas. This is because an individual project’s conformity is directly linked to the consistency of the projects with appropriate transportation plans (MTP/RTP) and improvement programs (TIP and STIP). A non-conforming project might trigger a conformity failure for the entire TIP.

## Slide 8: Regulations for Project Consistency
Federal: 23 CFR 450
Texas: 43 TAC 16
Conformity Regulation:
  40 CFR 93, subchapter A
Notes: Below are the regulations that define and establish requirement for project consistency:
-Federal: 23 CFR 450
-Texas: 43 TAC 16
-Conformity Regulation: 40 CFR 93, subchapter A

## Slide 9: Elements of Project Consistency
  Project Limits.
  Location.
  Type of Facility.
  Scheduled Let Date.
  Number of Lanes.
  Length.
  Signalization.
  Other Specific Information.
  Project cost must NOT exceed what is contained in the MTP/RTP by more than 50%.
Design Scope
Cost
Design Concept
Notes: This figure shows the elements that must be consistent in all planning documents, i.e., MTP/RTP, TIP, STIP, and UTP.
The cost requirement regarding the 50 percent increase is only applicable to the federal portion.

## Slide 10: Section 2: Transportation Planning and Project Development Process For more information refer to Chapter 2 of Supplementary Information Document

## Slide 11: Overview of Transportation Planning
Process of developing an integrated strategy for transportation investments to advance the area’s long-term goals.
Used to decide which transportation project to fund.
Involves transportation and non-transportation goals.
Involves developing a series of plans and programs.
Notes: Transportation planning is the process use to decide which transportation projects to build/fund.
Primary transportation planning functions of the state DOT:
Prepare and Maintain a Long-Range Statewide Transportation Plan: Develop and update a long-range transportation plan for the state. Plans vary from state to state and may be broad and policy-oriented, or may contain a specific list of projects.
Develop a Statewide Transportation Improvement Program (STIP): Develop a program of transportation projects based on the state’s long-range transportation plan and designed to serve the state’s goals, using spending, regulating, operating, management, and financial tools. For metropolitan areas, the STIP incorporates the TIP that the MPO developed.
Involve the public: Involve the general public and all of the other affected constituencies in the essential functions listed above.

## Slide 12: Transportation Planning Process
Monitor
Existing Conditions
Estimate
The Impact on Environment
Develop
A Financial
Plan
Forecast
Population, Employment, and Travel Demand
Identify
Transportation Problems and Needs
Develop
Long-Range Plans and Short-Range Programs
Feedback
Public Participation
Notes: The Transportation Planning Process starts with a look at existing conditions on the transportation system. Planners then analyze current and forecasted demographic, economic, and land use data to identify existing and future problems and needs. With input from stakeholders and the public, TxDOT and the MPOs develop long-range plans that define goals and strategies to address the problems and needs, and short-range, fiscally-constrained programs that contain projects that build and preserve infrastructure or provide services to achieve planning goals.
The Planning Process includes:
Monitoring existing conditions;
Forecasting future population and employment growth, including assessing projected land uses in the region and identifying major growth corridors;
Identifying current and projected future transportation problems and needs and analyzing, through detailed planning studies, various transportation improvement strategies to address those needs;
Developing long-range plans and short-range programs of alternative capital improvement and operational strategies for moving people and goods;
Estimating the impact of recommended future improvements to the transportation system on environmental features, including air quality; and
Developing a financial plan for securing sufficient revenues to cover the costs of implementing strategies.
Feedback and public participation are on-going activities throughout the planning process.

## Slide 13: Effective Transportation Planning
Continuing
  Planning must be maintained as an ongoing activity and should address both short-term needs and the long-term vision for the region.
Cooperative
Comprehensive
  The process must involve a wide variety of interested parties through a public participation process.
  The process must cover all transportation modes and be consistent with regional and local land-use and economic-development plans.
Notes: Transportation planning plays a fundamental role in the state, region, or community’s vision for its future. It includes a comprehensive consideration of possible strategies; an evaluation process that encompasses diverse viewpoints, the collaborative participation of relevant transportation-related agencies and organizations, and open, timely, and meaningful public involvement.
Transportation planners undertake a comprehensive analysis and evaluation of the potential impact of transportation plans and programs while addressing the aspirations and concerns of the society served by these plans and programs.
Main Functions for MPOs:
Establish a setting for regional decision making.
Identify and evaluate transportation improvement alternatives.
Develop and maintain a Metropolitan Transportation Plan (MTP).
Develop a Transportation Improvement Program (TIP).
MPOs coordinate with TxDOT during the planning process.

## Slide 14
  MTP/RTP
  Metropolitan or Regional Transportation Plan
  Long-Term, Major Investments
  UTP
  Unified Transportation Program
  Medium-Term, linking MTP/RTP and TIP
  TIP
  Transportation Improvement Program
  Short-Term, Projects with Funding Identified
  STIP
  Statewide Transportation Improvement Program
  Short-Term, Collection of TIPs
Funding Contract Awarded
Long-Range Planning – System Planning
Develop
Construct
MTP/RTP/LRTP
TIP/STIP
UTP
Project Initiation
Plan
Programming – Project Planning
Letting
Schedule
Transportation Planning Products (1)
Notes: Long-Range Plans
Long-range transportation plans such as TxDOT’s statewide LRTP and the MPO MTP/RTPs contain goals and strategies to address transportation needs in the rural and metropolitan areas of the state.
The Transportation Planning and Programming (TPP) Division develops TxDOT’s statewide LRTP, which guides collaborative planning efforts with TxDOT’s stakeholders to reach consensus on the projects and services needed to address system deficiencies, and to accomplish the goals in TxDOT’s Strategic Plan. The statewide LRTP is multimodal and includes passenger and freight components. It is consistent with the Texas Freight Mobility Plan (TFMP) and other statewide mode-specific, passenger and freight (e.g., rail, airport, water port) plans and includes MPO MTPs and RTPs by reference.
The statewide LRTP identifies statewide corridors—and projects within those corridors—that address mobility and connectivity between metropolitan areas. The projects included are long-range improvements being considered for development.
MPOs develop MTP/RTPs in cooperation with TxDOT and publicly-owned transit services. MTP/RTPs identify needed transportation improvements within the metropolitan area boundaries based on a comprehensive analysis of an area's current and projected demographic (i.e., population, household size, employment, household income and land use), economic, and land use data and the existing transportation system conditions. but MPOs should update MTP/RTPs every five years (four years for nonattainment and maintenance areas). The MTP/RTP must include sufficient financial information suggesting that all projects in the MTP/RTP can be implemented under available revenue sources (4).
Projects are strategically arranged within the statewide LRTP or an MTP/RTP based upon several key factors:
A project's complexity related to its development timeline;
A project's projected cost and its ability to fit within the plan's overall funding constraints as well as the annual forecasts of allocated revenues; and
A project's priority based upon a statewide, regional, or local need.
The planning process may result in more than one solution to address a problem or need, and there is no guarantee that any particular project will be implemented. A project may be delayed for financial or environmental reasons or canceled if no longer needed.
Unified Transportation Program (UTP)
TxDOT’s UTP is developed by TPP in cooperation with the MPOs and TxDOT Districts and Divisions. It includes transportation projects and services identified in the first 10 years of the statewide LRTP and MTP/RTPs, for which TxDOT can reasonably anticipate funding. Projects in the UTP have Commission authorization for preliminary engineering work, environmental analysis, right-of-way acquisition, final geometric design, and construction. Projects that are beyond the first 10 years of a long-range plan are generally not authorized for preliminary engineering work other than environmental studies. UTP is financially constrained and it becomes the basis for the District to prepare its financially constrained TIP (4).
TxDOT’s Cash Forecast, a component of the UTP, is developed by the Finance (FIN) Division and is comprised of revenues, expenditures, and fund balances. This forecast is essential to project selection and the timing of project development and implementation. The forecast is based on an analysis that considers historical trends, the Comptroller's Biennial Revenue Estimate (BRE), current law, current events, and other appropriate sources.
Expenditures are carefully balanced with incoming revenues to ensure that sufficient funds will be available beyond the biennium to make project payouts over several years. Additionally, FIN projects future expenditure totals based on budgets established under the General Appropriations Act, planned contract-letting amounts in the UTP, remaining obligations on previously let projects, and other relevant data.
Finally, the Cash Forecast enables TxDOT to establish its annual “letting” budget. Letting is the process of providing notice, issuing proposals, receiving bids, and awarding vendor contracts for transportation improvements.
Transportation Improvements Program (TIP) and Statewide Transportation Improvement Program (STIP)
As projects move closer to construction or implementation, they will advance from the UTP into either a rural TIP developed by a TxDOT District or an MPO TIP. A TIP is a four-year program that contains a fiscally constrained list of multimodal (e.g., highway, transit, bicycle, etc.) transportation projects in a specific rural or metropolitan area that accomplish the planning goals set out in a long-range plan (statewide LRTP or MTP/RTP).
The STIP is the four-year program of the transportation projects to be constructed or implemented statewide. It is developed by TPP in cooperation with TxDOT Districts and MPOs, and includes all of the rural and MPO TIPs, as well as statewide federal programs. It includes highway and transit projects funded under Title 23 United States Code (USC) and Title 49 USC, Chapter 53, and any modal projects with phases or components funded under those titles. Regionally significant projects that will be implemented with state or local funds are included for planning, coordination, and public disclosure purposes. In an air-quality nonattainment area, only those projects determined to conform to the requirements of the CAA and the SIP may be included in the STIP.
Projects that are not considered by TxDOT and the MPOs to be of appropriate scale for individual identification in a given program year (e.g., minor rehabilitation, preventive maintenance, non-urbanized transit projects) may be grouped by function, geographic area, or work type. In nonattainment and maintenance areas, classification must be consistent with the exempt project classifications contained in the Environmental Protection Agency (EPA) conformity regulations.
A TIP and the STIP are similar in that they are fiscally constrained, four-year programs that are consistent with applicable long-range plans, but there are also important differences between the two documents. A TIP is a stand-alone document, approved at the local level that includes projects within a rural area or MPO boundary. TIPs do not require federal approval. The STIP is subject to a statewide public involvement process that culminates in a single public hearing in Austin, Texas, before its adoption by the Commission.
Once adopted, the STIP is then approved by both the FHWA and FTA. Federal dollars cannot be expended on a project in a TIP unless that project is listed, individually or by reference, in the STIP. With few exceptions, projects must generally be included in a TIP and the STIP in order to advance to construction or implementation.
Letting Schedule
The letting schedule lists projects that will be let within the next two years. At this point, the final contract documents (i.e., the Plans, Specifications, and Estimates [PS&E] that provide a detailed description of the project, how it will be constructed, and the estimated cost) have been or are nearing completion.
A list of the transportation plans and programs is provided on page 4 of the supplementary information document.

## Slide 15: Transportation Planning Products (2)
Planning Product | Who Develops? | Who Approves? | Time Period | Content | Update Cycle | Project Fiscal Constraints Funding Requirements |  | 
 |  |  |  |  |  | Year 1 – Year 2 | Year 3 – Year 4 | Year 5 – Year 20+
Metropolitan Transportation Plan (MTP) | MPO | MPO | 20 + years | Future goals, strategies, and projects | Every 5 years (4 years) | Committed Funds | Reasonably Available | Reasonably Available
Unified Transportation Program (UTP) | TxDOT | Texas Transportation Commission | 10 years | Projects to be funded/built in a 10-year period | Annual |  |  | 
Transportation Improvement Programs (TIPs) | MPO - TxDOT Districts | Governors/ MPOs | 4 years | Transportation investments (projects) | Every 2 years |  |  | 
Statewide Transportation Improvement Program (STIP) | TxDOT | USDOT | 4 years | Transportation investments | Every 2 years |  |  | 
Federal Requirement–MTP, TIP, and STIP must be fiscally constrained, i.e., sufficient funds by source must be demonstrated
* More detailed information can be found in Part B: Supplementary Information Document
Notes: The following definitions will apply for fiscal constraint funding terms:
Committed Funds–These are funds for projects that are approved to be let. The letting schedule is prepared for a 24-month timeframe.
Reasonably Available Funds–Projected funding beyond the current year in approved cash flow forecast.
The MTP must include sufficient financial information suggesting that all projects in the MTP can be implemented under available revenue sources.
UTP: District funding is normally handled through the UTP, which is annually prepared by the Programming and Scheduling Section of TPP. UTP is financially constrained and it becomes the basis for the District to prepare its financially constrained TIP.
More detailed is provided in the guidebook supplementary, page numbers 3-9.

## Slide 16: Transportation Funding Sources
Federal:
  Highway Trust Fund.
  Other funding mechanisms.
State:
  Motor Fuel Tax.
  Vehicle Sales Tax.
  Vehicle Registration Fees.
Local:
  Local Contribution.
  Private Funding (Public-Private Partnership).
Notes: Transportation funds come from a range of sources, including the federal government, state governments, public or private tolls, local assessment Districts, local government general fund contributions (such as local property and sales taxes), and impact fees.
Federal funding is made available to state DOTs through the Federal Highway Trust Fund, which is the primary funding source for major transportation plans and programs. State DOTs administer federal program funds and are responsible for distributing those funds to metropolitan areas through the UTP. The state DOT has authority to allocate the money to urban and rural areas based on state and local transportation needs; however, some federal programs are allocated to areas based on population size, are competitive, or are under specific criteria such as the Congestion Mitigation and Air Quality Improvement (CMAQ) program.
The federal funding process for transportation projects is not a cash-up-front system; rather, eligible expenditures are reimbursed. The process follows:
States are notified that they have federal funds available for their use. Projects are approved and work is started. The federal government then reimburses the states, MPOs, and transit operators for costs as they are incurred, reimbursing up to the limit of the federal share
Funding recipients are liable for complying with all applicable federal laws. When local governments directly oversee a federally funded project, the state DOT monitors local government compliance with state and federal laws.
Fiscal constraint is a “demonstration of sufficient funds from federal, state, local, or private sources to implement proposed transportation system improvements, as well as to operate and maintain the entire system, through the comparison of revenues and costs.” The MTP/RTP, TIP, and STIP must be fiscally constrained in order to meet federal requirements.
Guidebook reference, page numbers 9-10.

## Slide 17: Section 3: Project Development and Environmental Review For more information refer to Chapter 3 of Supplementary Information Document

## Slide 18: TxDOT Project Development Process
Notes: TxDOT identifies four general stages in the project life cycle: project initiation, planning, development, and construction. TxDOT Districts, in conjunction with MPOs, manage the project through these four stages.
The figure shows a simplified overview of the TxDOT PD process and where key TxDOT Divisions are involved.
This diagram was developed based on TxDOT’s Project Development Process Manual, 2012.
Note: Appendix A in the Guidebook Supplementary Document references the phases and actions of the project development process.

## Slide 19: TxDOT’s Environmental Review Process
Interagency Coordination
Final Environmental Document
Environmental Clearance
Planning/
Preliminary Survey
Draft Environmental Document
Public Involvement
Natural/Cultural Resource Impacts
Socio-economic Impacts
Noise Impacts
Hazardous Materials Evaluation
Air Quality Analysis
Environmental
Re-evaluation
Environmental Commitments
Permitting
PROJECT INITIATION
PLAN
Authority Required
DEVELOP
Authority Required
CONSTRUCT
Authority Required
ENVIRONMENTAL
Notes: The figure illustrates where the Environmental Process falls within TxDOT’s Project Development Process and the typical activities that comprise the Environmental Process. These activities are:
Preliminary survey/planning.
Interagency coordination.
Environmental documentation.
Public involvement.
Permitting.
Commitments.
Obtaining the environmental clearance is a critical requirement to proceed with the design phase.
Transportation and NEPA:
TxDOT ENV is responsible for preparing the environmental documents that include: natural/cultural resource impact, socioeconomic impact, noise impact, hazardous materials evaluation, and air quality analysis.

## Slide 20: Environmental Documentation
Categorical exclusion (CE).*
  Project with no significant environmental impact.
Environmental assessment (EA).
  Unclear whether the impacts are significant.
Environmental Impact Statement (EIS).
  Clear significant environmental impacts.
  *Delegated to TxDOT Districts
Notes: A CE applies to projects that, based on previous experience, do not have significant environmental impacts.
An EA applies to projects for which the significance of the environmental impacts is unclear. The outcome of the EA is either a Finding of No Significant Impact (FONSI) or the need to prepare an Environmental Impact Statement. Expected to be delegated to TxDOT—expected fall 2014.
An EIS applies to projects that are believed will have significant social, economic, and/or environmental impacts.

## Slide 21: Section 4: Transportation Conformity For more information refer to Chapter 4 of Supplementary Information Document

## Slide 22: Air Quality
The Clean Air Act (CAA) sets the framework and goals for improving air quality to protect public health.
National Ambient Air Quality Standards (NAAQS) for criteria pollutants.
When an area violates a NAAQS, it is designated as a Nonattainment (NA) area.
When a NA area achieves attainment of the NAAQS, it will be redesignated as an Attainment Maintenance Area for 20 years.
Notes: The CAA provisions ensure that the SIP achieves its goals to protect human health, coordinates transportation and air quality planning processes, and improves data and planning assumptions.
An area is in violation of a standard if it exceeds the concentration level for the specified form of the standard and evaluation timeframe.
A nonattainment area may request redesignation as a maintenance area if the area has three consecutive years of “clean data” (three consecutive years of no violations detected at air quality monitoring stations).
The National Ambient Air Quality Standards (NAAQS) are promulgated and may be found at 40 CFR 50.

## Slide 23: Criteria Pollutants
NAAQS exist for the following pollutants.
Ozone (O3)
Precursors:
Oxides of Nitrogen (NOx)
Volatile Organic Compounds (VOCs)
Particulate Matter
(PM10 and PM2.5)
Carbon Monoxide (CO)
Nitrogen Dioxide (NO2)
Sulfur Dioxide (SO2)
Lead (Pb)
Notes: EPA calls these the six common pollutants. See: http://epa.gov/pm/actions.html.
Texas MPO areas are in nonattainment or attainment maintenance designation for Ozone, CO, NOx, and PM10.

## Slide 24: Air Quality Planning
The principal framework for efforts to protect air quality from man-made pollution sources.
Texas Commission on Environmental Quality (TCEQ).
State Implementation Plan (SIP) is the air quality plan for the state that the TCEQ had developed. The Plan:
  Shows how all areas of the state will meet the NAAQS.
  Establishes an emissions “budget” for on-road sources for each pollutant in NA area.
Notes: For a good overview of SIPs and much specific information is contained in the Transportation Conformity Reference Guide at: www.fhwa.dot.gov/environment/air_quality/conformity/reference/reference_guide/sectionb.cfm
Responsibility for the development of SIPs rests with the State. The Governor designates the lead agency.
The SIP allocates emissions reductions among all categories of emissions including on-road, non-road, stationary, and areas’ sources. The SIP then establishes an “emissions budget” for on-road sources. Conformity must show that the motor vehicle emissions budget (“emissions budget”) is not exceeded for specified analysis years.
Some areas are not required to have budgets because of their classification and/or because they qualify for EPA’s limited maintenance plan or insignificance policies. See 40 CFR 93.109(j) and (k) for specific criteria for these policies.

## Slide 25: Transportation Conformity
Transportation Conformity
  What is Conformity?
  Who is Responsible?
  What is Subject to Transportation Conformity?
Transportation Conformity
Air Quality Planning
State Implementation Plan (SIP)
Transportation Planning
MTP/RTP and TIP
Notes: Transportation conformity is a process that ensures transportation projects are supporting air quality goals. Transportation conformity is the process that links transportation planning and air quality planning.
The MPO is responsible for ensuring conformity of their planning documents( MTP/RTP and TIP) are conforming to air quality goals which are documented in the SIP.
However, MPOs need input/support from TxDOT and other agencies. The process is dependent on federal, state, and local transportation agencies working together to meet the conformity requirements.
Note: Appendix C in the Guidebook Supplementary Document references the federal laws and regulations on transportation conformity.
There are two levels of conformity:
Regional: This refers to all plans and programs in nonattainment or maintenance areas.
Project-level: Each project should come from a conforming MTP/RTP and TIP
Hot-spot analysis is for specific pollutants (PM10 and CO) and some projects are found to significant air quality impact might be subject to additional steps to evaluate their local impact.
MTP/RTP and TIP are subject to transportation conformity.
A transportation projects is subject to project-level transportation conformity if it:
Is located within a nonattainment or maintenance area for ozone, carbon monoxide, nitrogen dioxides, or particulate matter.
Is not exempt from transportation conformity per 40 CFR 93.126.
Has FHWA/FTA funding, needs an FHWA/FTA decision, or is regionally significant (regardless of federal involvement).
Transportation Planning and NEPA
Transportation plans and programs are not subject to the environmental review process under NEPA, but federal planning rules provide guidance that has allowed TxDOT to better incorporate information, analysis, and products from its planning process into project-level NEPA documents by engaging in the following activities during plan and program development:
Consultations with resource agencies, such as those responsible for land use management, natural resources, environmental protection, conservation, and historic preservation, which involve, as appropriate, comparisons of resource maps and inventories.
Discussion of potential environmental mitigation activities.
Development and documentation of a consultative process for stakeholder participation that is separate and discreet from the public involvement process.
Inclusion of visualization techniques to describe plans, programs, and projects.
Increased accessibility to published plans, programs, and public involvement proceedings using multiple electronic formats.

## Slide 26: Transportation Conformity Process
FHWA/FTA signs a decision for the environmental document.
FHWA/FTA approves the federal funding for the project.
Project Approval
TCEQ sets emissions budgets for the region.
SIP Emissions Budget
MPO performs regional air quality analysis of MTP/RTP and TIP.
Total emissions from the regional transportation activities after implementation of MTP/RTP and TIP should not exceed SIP emissions budget.
MTP/RTP and TIP are fiscally constrained.
Plan and Program Conformity Determination
FHWA/FTA determines that MTP/RTP and TIP are conforming to SIP.
MTP and TIP Approval
Project must come from a conforming MTP/RTP and TIP.
Project must be consistent with MTP/RTP and TIP.
Hot spot analysis is maybe needed for PM and CO.
Determined based on information on the environmental document.
Project–Level Conformity Determination
Notes: What Is Conformity and Who Is Responsible?
Air quality planning is the principal framework for national, state, and local efforts to protect air quality from certain man-made pollution sources. In Texas, air quality planning is administered by the Texas Commission on Environmental Quality (TCEQ) through development of the SIP.
The goal of conformity is to ensure that FHWA and FTA funding and approvals are given to transportation projects that will not cause or contribute to any new violations of the NAAQS, increase the frequency or severity of NAAQS violations, or delay timely attainment of the NAAQS or any required interim milestone.
Nonattainment or maintenance areas are those that fail or failed in the past to meet NAAQS for the criteria pollutants defined in the CAA.
The transportation conformity process is carried out by a consultative group of reviewing agencies representing EPA, FHWA, FTA, TCEQ, TxDOT, and MPOs located in nonattainment and maintenance areas.
In addition to general transportation conformity, some projects are also required to conform to project-level conformity requirements. A transportation project is subject to transportation conformity if it:
Is located within a nonattainment or maintenance area for ozone, carbon monoxide (CO), nitrogen dioxides, or particulate matter (PM).
Is not exempt from transportation conformity per 40 CFR 93.126.
Has FHWA/FTA funding, needs an FHWA/FTA decision, or is regionally significant (regardless of federal involvement).

## Slide 27: Texas Transportation Conformity Process and Timeline
Notes: The figure provides an overview of the expected time required for major steps of the conformity re-evaluation process. For example, if a project inconsistency trips regional conformity, it may cause more than a year of delay for that project.

## Slide 28: Failure of Conformity
Failure to Meet Regional Conformity Requirements
Conformity Lapse
1-Year Grace Period
During the Conformity Lapse, Only the Following Projects Can Proceed
Exempt Projects
TCMs in
Approved SIP
Approved by FHWA/FTA
(with a signed FPAA*)
before failure)
*FPAA: Federal Project Authorization Agreement
Notes: If a regional conformity determination is not made on the MTP/RTP or TIP during the required schedule, the area has a one-year grace period to make the determination before there is a conformity lapse. During a conformity lapse, only certain types of projects can proceed.
As previously stated, a project must meet the following to demonstrate project-level conformity:
Come from the currently conforming MTP/RTP and TIP.
Have a design concept and scope that must not have changed significantly from that in the MTP/RTP and TIP.
In PM nonattainment and maintenance areas, projects coming from currently conforming MTP/RTPs and TIPs must demonstrate compliance with any control measures in the SIP.
In carbon monoxide and PM nonattainment and maintenance areas, additional analysis may be necessary to determine if a project has localized air quality impacts. This localized air analysis is referred to as a hot-spot analysis.

## Slide 29: Federal Actions
Approval of the STIP.
Conformity determinations.
Approval of an EA, CE or EIS.
Approval of a Federal Project Authorization Agreement (FPAA).
  Required for the reimbursement of project costs with federal funds.
Notes: A project funded with federal dollars that is, by definition, required to be listed in a fiscally constrained and conforming MTP/RTP and TIP, must be consistently described in those documents in order to receive federal action. Though there is not a federal requirement stipulating consistency of plans and programs with the UTP, projects listed in an MTP/RTP and TIP must be consistent with the UTP because TxDOT demonstrates the fiscal constraint of the STIP, and all included TIPs, via the UTP. This presentation focuses specifically on project consistency to facilitate the following federal actions:
Approval of the STIP.
Conformity determinations (approval of modeled network consistent with a fiscally-constrained MTP/RTP and TIP in a nonattainment or maintenance area).
Approval of an EA, CE, or EIS.
Approval of an FPAA (required for the reimbursement of project costs with federal funds).