## Slide 1: Project Consistency Workshop
Session 2: Maintaining Project Consistency

## Slide 2: Section 1: Overview For more information refer to Chapter 1 of Project Consistency Guidebook

## Slide 3: Workshop Goals and Objectives
To help TxDOT staff to minimize unintended delays due to inconsistencies during the project development process:
This session provides an overview of the following subjects:
  Definition of project consistency and causes of inconsistencies.
  Information for external entities and TxDOT offices and districts.
  Critical junctures for checking project consistency.
  Tools and best practices.
  Project consistency checklist.

## Slide 4: Section 2: Project Consistency For more information refer to Chapter 2 of Project Consistency Guidebook

## Slide 5: What Is Project Consistency?
A federal and state requirement.
    Transportation projects must be described consistently in all applicable documents (transportation plans and programs) with regard to the following descriptive elements:
      Design Concept: project limits, location, facility type.
      Design Scope: project configuration (e.g., number of lanes, length, signalization).
      Project Cost.
Notes: Project consistency refers to the federal and state requirements that a project be consistent with the applicable MTP/RTP and TIP, and/or STIP. A project must be consistent with these planning documents with regard to three major elements:
Design concept, including project limits, location, type of facility, and scheduled letting date.
Design scope, including specific information such as number of lanes, length, signalization, etc.
Project cost.

## Slide 6: Regulations for Project Consistency
Federal: 23 CFR 450
Texas: 43 TAC 16
Conformity Regulation:
  40 CFR 93, subchapter A
Notes: Below are the regulations that define and establish requirement for project consistency:
-Federal: 23 CFR 450
-Texas: 43 TAC 16
-Conformity Regulation: 40 CFR 93, subchapter A
Federal and state transportation planning statutory and regulatory laws require transportation projects to be consistent with transportation plans and programs in order for the FHWA under NEPA regulations to sign a Record of Decision (ROD), Finding of No Significant Impact (FONSI), or approve a Categorical Exclusion (CE) for a project.

## Slide 7: Project Consistency Requirements
  Projects described in ROD, FONSI, or CE shall be consistent with the MTP/RTP, TIP, STIP, and AQ conformity documentation (if applicable).
All project phases planned within the life of the transportation plan have to be included in the fiscally constrained MTP/RTP for FHWA approval.
MTP/RTP
  Must be fiscally constrained and must include a financial summary that is fiscally constrained to funding forecasts by TxDOT’s Finance Division.
  Inclusion of projects only if consistent with state and local long-range plans.
  The timing of subsequent phases should be consistent with the MTP/RTP and the environmental document.
TIP & STIP
Notes: For the purposes of this project, maintaining project consistency will be in the context of the MTP/RTP, TIP, and STIP, and will not include the Statewide LRTP, based on the current practices of TxDOT and MPOs, which assume that a project must be consistent with the Statewide LRTP before it is adopted in the STIP.
This figure shows the requirements of federal regulations regarding the plans and programs that are subject to maintaining project consistency. Each project or project phase included in the TIP, in metropolitan planning areas, must be consistent with an approved MPO transportation plan. Note that some types of projects may be excluded from an MPO TIP and the STIP by agreement between TxDOT and the MPO in accordance with requirements established in Title 43, Texas Administrative Code (TAC) 16.101(d), the next slide covers these project types.

## Slide 8: Projects That Are Subject to Project Consistency
Non-exempt transportation projects listed individually in a TIP and STIP.
Excluded projects:
  Safety projects funded under 23 USC 402.
  Most planning and research activities.
  Projects under 23 USC 104(b)(1), (b)(4), and 144, which will not alter the functional traffic capacity or capability of the facility.
Notes: All non-exempt transportation projects listed individually in a TIP and STIP must be consistent with an MTP/RTP (where applicable), and the UTP for the purposes of fiscal constraint.
Note that some types of projects may be excluded from an MPO TIP and the STIP by agreement between TxDOT and the MPO in accordance with requirements established in Title 43, Texas Administrative Code (TAC) 16.101(d). Those projects include:
  Safety projects funded under 23 USC 402 (highway safety programs and emergency relief projects, except those involving substantial functional, location, and capacity changes);
  Planning and research activities, except those activities funded with National Highway System or Surface Transportation Program funds other than those used for major investment studies; and
  Projects under 23 USC 104(b)(1), (b)(4), and 144 that are for resurfacing, restoration, rehabilitation, reconstruction, or highway safety improvement, and which will not alter the functional traffic capacity or capability of the facility being improved.
The types of projects listed above are less likely to encounter delays due to project inconsistency because they are less likely to be included in an MTP/RTP, UTP, TIP, or the STIP. However, there are notable exceptions as follows:
An MPO may opt to include individual projects that would be “exempt” by federal definition under the agreement. If a project is listed individually, for whatever reason, it will be treated as a non-exempt project during federal review.
Projects that are considered of Regional Significance must be listed individually. This includes those that could be exempted by definition.
Project and project phases that will have an impact on air quality in nonattainment areas.

## Slide 9: Consistency and Federal Action
This training focuses specifically on project consistency to facilitate the following federal actions:
Approval of the STIP.
Conformity determinations (MTP/RTP and TIP).
Approval of an EA, CE*, or EIS*.
Approval of an FPAA–required for the reimbursement of project costs with federal funds.
*Delegated or expected to be delegated to TxDOT
Notes: A project funded with federal dollars that is, by definition, required to be listed in a fiscally constrained and conforming MTP/RTP and TIP, must be consistently described in those documents in order to receive federal action. Though there is no federal requirement stipulating consistency of plans and programs with the UTP, projects listed in an MTP/RTP and TIP must be consistent with the UTP because TxDOT demonstrates the fiscal constraint of the STIP, and all included TIPs, via the UTP.
Approval of the STIP;
Conformity determinations (approval of modeled network consistent with a fiscally constrained MTP/RTP and TIP in a nonattainment or maintenance area);
Approval of an EA, CE, or EIS; and
Approval of an FPAA (required for the reimbursement of project costs with federal funds).

## Slide 10: Project Consistency and Transportation Conformity
Project Consistency is:
  One of the key criteria for project-level conformity determination.
  An important factor for the regional transportation conformity for MTP/RTP and TIP.
Federal project-level conformity requirements state that:
  Projects need to be from and consistent with a currently conforming MTP/RTP and TIP.
A failure of project conformity as a result of project inconsistency:
  Can potentially result in a failure of regional transportation conformity and a need for a conformity redetermination.
Notes: Federal project-level conformity requirements state that projects need to be from and consistent with a currently conforming MTP/RTP and TIP. A failure of project conformity as a result of project inconsistency can potentially result in failure of regional transportation conformity and a need for a conformity redetermination.

## Slide 11: Consequences of Project Inconsistency
Unnecessary Delays to the Project
Consequences of Project Inconsistency
Failure of Project-Level Conformity
Withholding of Federal Funding
Potential Failure of MTP/RTP and/or TIP Conformity
Potential Need for MTP/RTP and/or TIP Conformity Re-evaluation
Nonattainment & Maintenance
All Areas
Notes: In general, if a project does not meet the federal project consistency requirements, FHWA/FTA will not take an action on it. When federal action cannot be taken due to project inconsistency, delays occur, and those delays put TxDOT at financial risk. More importantly, without these federal actions, TxDOT cannot be reimbursed with federal funds for eligible project costs. This slide summarizes the potential consequences of a project inconsistency.
According to the federal project-level conformity requirements, a project is no longer in conformity if its design concept and scope:
Has changed from what was originally included in the regional emissions analysis; or
Was not adequate to determine the contribution of a project to regional emissions in the MTP/RTP and TIP.
In addition to unnecessary delays for the project and withholding of federal funding, a failure of project conformity can potentially result in failure of regional air quality conformity and a need for a conformity re-evaluation. A regional conformity re-evaluation can cause an excessive delay for the project. In some cases, FHWA/FTA can authorize only limited types of projects until the conformity redetermination for MTP/RTP and/or TIP is complete.
This issue is especially critical for projects in nonattainment and attainment maintenance areas since an inconsistency-induced failure of project-level conformity can affect the region’s transportation conformity determination.

## Slide 12: Section 3: Origins of Project Consistency For more information refer to Chapter 3 of Project Consistency Guidebook

## Slide 13: Causes That Lead to Inconsistency
Projects Evolve
Inconsistency in Regulatory Processes
Communication
Complexity of Funding Scenarios
Notes: The causes of project inconsistency can be numerous, but the following summarizes the most common causes:
Projects evolve. The long periods of time that elapse between stages in the planning, project development, and environmental processes increase the chances that a project’s design, scope, estimated cost, or estimated letting date will change. When changes are not communicated, it is difficult to maintain project consistency in every document in which the project has been listed—from project initiation to construction.
Inconsistency in regulatory processes. A project of significant scope may be subject to changes in established regulations and administrative rules over time without the benefit of being grandfathered.
Communication. More to the point, there can be a lack of communication between the numerous local, state, and federal entities responsible for the completion of the plans, programs, and processes to advance a project from inception to construction. For example, if the project description is changed during the preliminary design phase, TxDOT would need to notify the MPO to update the project description in the MTP/RTP before that project is carried into the TIP with an inconsistent—or rather, incorrect—project description.
Complexity of Funding Scenarios. Programming transportation projects is a dynamic process. Changes in funding levels, fund sources, agency operations, economic conditions, current law, timing of project schedules, and other factors such as changes in the estimated cost of a project over the time it takes to develop a project, will result in changes to one or more aspects of a project’s scope, design, or description that would have to be revised in the appropriate planning and environmental documents.
Note: In the Project Consistency Guidebook, Chapter 3 covers the causes that lead to inconsistency, page 7.

## Slide 14: Examples of Possible Inconsistencies (1)
Project design concept and scope not consistent with MTP/RTP, TIP, UTP and/or STIP.
Not fiscally constrained because:
  Not included in the fiscally constrained portion of the MTP/RTP.
  Project funding type not consistent with MTP/RTP, TIP, and/or STIP.
  Total federal funding exceeds what is documented in the MTP/RTP, UTP, TIP, and/or STIP by more than 50 percent.

## Slide 15: Examples of Possible Inconsistencies (2)
Project is not included in the TIP or STIP, but is found earlier in the planning documents such as the MTP/RTP or UTP.
In the nonattainment and maintenance areas, the project completion year is not consistent with the MTP/RTP and/or TIP regional emissions analysis years for conformity determination.
Notes: In the nonattainment and maintenance areas, the expected year of completion MUST fall between the following years:
The 1st year in which the project is included in the MTP/RTP emissions analysis; and
The Last Year in which the project is NOT included in the MTP/RTP emissions analysis.

## Slide 16: Consistency and Federal Actions in the Project Development
Notes: For some projects, inconsistency is unavoidable, given the complexity of the various processes to which projects are subject. The successful delivery of projects requires time and effort on the part of many professionals at local, state, and federal transportation planning and regulatory agencies. While no one can control the outcomes of all the various phases and steps in the planning, project development, and environmental processes, one can only attempt to better understand the relationships between the various processes.
Projects are generally designed to conform to federal planning and environmental regulations under the assumption that federal funding may be required to complete some or all of the project development activities or actual construction. The planning, environmental, and project development processes are interdependent and somewhat sequential in nature. Some processes have phases or steps that are under way concurrently at any given time when federal action may be requested (see above Figure).

## Slide 17: Section 4: Maintaining Project Consistency For more information refer to Chapter 4 of Project Consistency Guidebook
Notes: The elements of project consistency management include:
Staff roles and responsibilities;
Maintaining project consistency;
Project consistency prevention,
Project inconsistency detection and
Tools, resources, and recommendation to maintain project consistency.

## Slide 18: Project Consistency Responsibility
Primary.
  TxDOT Districts:
    Director of Transportation Planning and Development (TP&D).
    Project Managers.
    Environmental Coordinator.
  MPOs.
  Project Sponsor.
Secondary.
  TxDOT Divisions:
    Transportation Planning and Programming (TPP).
    Finance (FIN).
    Environmental Affairs (ENV).
Notes: It is highly important for Districts and MPOs to identify the staff responsible for key consistency-related steps/activities during the project development process, both inside their own agency and their partner agency.
Responsibilities should be clearly explained and assigned to staff, and an effort should be made to ensure that they know the responsible party for the other activities.
MPOs must update MTP/RTP and TIP of any necessary revisions or changes.

## Slide 19: TxDOT Consistency-Related Activities
  Internal Communication and Coordination.
    Tracking and internal coordination of changes made to projects.
    As project moves through the PD process, checks environmental documents for any inconsistencies.
  External Communication and Coordination.
    Communicates changes to/from MPOs and headquarter staff.
    Ultimately responsible for maintaining project consistency and coordinating with the MPO and TxDOT Divisions.
District Project Managers
District TP&D Director
Notes: TxDOT Districts:
The TP&D director communicates these issues to outside stakeholders including the MPO at the Technical Advisory Meetings. The District Environmental Coordinator coordinates the District’s activities regarding the preparation of environmental documents for projects.
TxDOT project managers are usually the individuals overseeing project development and are in a position to coordinate and track all changes to a project during this process. In some Districts, a separate project manager (i.e., environmental project manager) oversees the environmental process activities for a project. Project managers report to the TP&D director on any issues or challenges regarding project development at internal meetings. The TP&D director communicates these issues to outside stakeholders including the MPO at the Technical Advisory Meetings. The District Environmental Coordinator coordinates the District’s activities regarding the preparation of environmental documents for projects.
TxDOT District project managers, the director of Transportation Planning and Development (TP&D), and/or District environmental coordinator play a central role in maintaining project consistency.
Because TxDOT project managers are the closest person to projects and changes made to them, they are the responsible party to maintain consistency by ensuring that all changes are coordinated and communicated internally in an effective and timely manner.
The District TP&D director is responsible for ensuring that all the changes are communicated effectively and quickly with external partners, specifically MPO staff.

## Slide 20: TxDOT Consistency-Related Activities
    Review of Submitted Environmental Documents and Project Scope.
ENV Project Delivery Manager
  Oversee and Coordinate Environmental Process.
    Compiles environmental documents for projects, and checks for any inconsistencies with the planning documents (MTP/RTP, TIP, STIP, UTP).
District Environmental Coordinator
Notes: The District Environmental Coordinator coordinates the District’s activities regarding the preparation of environmental documents for projects and will check for any inconsistencies with the planning documents.

## Slide 21: MPO Consistency-Related Activities
External Communication and Coordination
Communicating changes to/from TxDOT District staff
Updating MTP/RTP, TIP, and/or Conformity Analysis
Notes: It is critical that the MPO is involved in communicating changes to planning documents because they will need to update the MTP/RTP, TIP, and review the conformity analysis.
The MPO and District need to be in constant communication to ensure consistency.

## Slide 22: Maintaining Project Consistency
Consistency: Design Concept and Scope and Cost.
Maintaining project consistency is an ongoing process and covers all phases of a project:
  Critical during the last 4 years before letting.
  Critical for Nonattainment, Near Nonattainment, and Maintenance areas.
  Starts with scoping.
  Early coordination is the key.
Consistency is required for federal actions (as noted in previous slides).
Notes: Maintaining project consistency, or Project Consistency Management (PCM), is an ongoing process and covers all phases of project development. It becomes critical during the last 4 years of the project development process (i.e., when projects are listed in the TIP and STIP).
The scoping document is a collection of the first set of information on a project. It is often used as the foundation for setting up the project in different documents and database systems within and outside TxDOT. A robust scoping effort coupled with early coordination ensures that the project is set up by various stakeholders in a consistent and timely manner. This early consistency has been indicated to greatly help the stakeholders to maintain the consistency of information in the later stages of project development.
The project should be consistent with all applicable planning documents throughout the project development process and into the preparation of the environmental review document. The main mechanism through which ENV and FHWA/FTA check for project consistency is the environmental review document and applicable planning documents (i.e., MTP/RTP, UTP, TIP, and STIP). If the project design concept or scope changes significantly after the project is environmentally cleared, a re-evaluation will be required and planning documents will likely need to be updated.

## Slide 23: Minimum Level of Communication for PCM
District PM
District TP&D Director
District Env. Coordinator
MPO Staff
District TP&D Director
District Env. Coordinator
District TP&D Director
District Env. Coordinator
TPP/MPO Field Coordinator
MPO Staff
District TP&D Director
TPP – UTP & STIP Staff
Finance Division
TPP – UTP Staff
TPP – STIP Staff
TPP/MPO Field Coordinator
District TP&D Director
District Env. Coordinator
Finance Division
District TP&D Director
District Env. Coordinator
Report changes to design concept and scope
Report changes to design concept, scope, funding
Report changes to project cost and/or funding
Report changes to design concept, scope, funding
Report changes to TIP and/or MTP/RTP
Report changes to project funding and/or cost
Notes: This is an example of communication flows between district, MPO and division staff to maintain project consistency.

## Slide 24: Project Consistency Management (PCM)
  Goal: to minimize the risk of inconsistency.
  Prevention of project inconsistencies through best practices and improvements to the routine operation of TxDOT District and partners.
Goal: to minimize the damage of an inconsistency, i.e., to detect and address inconsistencies before they cause major delays as a result of a need for project and/or plan changes.
Early detection of unexpected inconsistencies minimizing unforeseen delays.
Serves as the second line of defense.
Prevention
Detection
Components of PCM
Project inconsistencies are strongly associated with a breakdown of communication and poor coordination.
Notes: The basic principle of project consistency management (PCM) is a seemingly simple task that becomes a challenge in practice because at any given time, there are multiple teams working on different aspects of a project and each uses different tools and data resources. That is why project inconsistencies are strongly associated with a breakdown of communication and poor coordination. Establishing a systematic process for this task can greatly help Districts to simplify the coordination of efforts between different parties and achieve the goal of PCM.
The PCM consists of a two-step process: prevention and detection. Both of the steps are important to ensure project consistency.

## Slide 25: Prevent Project Inconsistencies
Establish project inconsistency prevention as a routine part of project development process at the District level.
Proposed steps:
  Step 1: Training.
  Step 2: Assign Responsibility.
  Step 3: Authority and Tools.
  Step 4: Establish a PCM Work Flow.
  Step 5: Systematic Coordination and Communication.
Notes: The following proposed steps can help in establishing such a process. The goal of these steps is to establish project inconsistency prevention as a routine part of the PD process at the District level.

## Slide 26: Step 1 - Training
Ensure project managers and key staff have a general understanding of:
  Project delivery process.
  Planning and programming documents.
  Environmental process.
  Transportation conformity.
  Importance of maintaining project consistency.
Notes: Step 1: Training – Make sure that project managers and identified key staff have a general understanding of the project delivery process, planning and programming documents, the environmental process, transportation conformity, and the importance of maintaining project consistency.
Identify key staff in charge of different aspects of developing projects; e.g., environmental coordinators, designers and planners.

## Slide 27: Step 2 – Assign Responsibility
Clearly assigned roles for staff.
All staff and parties involved in the project inconsistency prevention have a clear understanding of their responsibility in the process.
Notes: Step 2: Assign Responsibility – Clear role assignment is an important factor in establishing an effective PCM process. Ensure that all staff and parties involved in the project inconsistency prevention, specifically project managers, have a clear understanding of their responsibility in the process. Their role needs to be explicitly articulated and communicated.

## Slide 28: Step 3 – Authority and Tools
Project managers and identified key staff should be assigned the authority to meet their responsibilities and be equipped with the right tools to accomplish them.
Notes: Step 3: Authority and Tools – To establish an effective PCM process, project managers and identified key staff should be assigned the authority to meet their responsibilities and be equipped with the right tools to accomplish them. The next section provides an overview of the tools and data sources that TxDOT District staff can use to maintain project consistency. The consistency checklist can be used as a guide to keep track of the changes to a project.
Proper training is needed prior to establishing authority specifically to modifying information on TxDOT databases such as ECOS and DCIS. Furthermore, they need to understand the system when inputting data and understand how the inputted data can impact the entire system.

## Slide 29: Tools and Resources
DCIS
To check scope, limits, time period, project status.
ECOS
To check the consistency of environmental documents with planning documents.
E-STIP
Use to check the consistency with STIP.
P6
Check project schedules with letting schedule and environmental clearance dates.
Notes: Design & Construction Information System (DCIS) – is a statewide computer network that allows all TxDOT Districts and TxDOT Divisions to maintain project data in a common format. The information is used to prepare the MTP/RTP, STIP, UTP, and the letting schedule. DCIS is often the primary tool to check for the updated information on individual projects and therefore a key tool for project consistency checking.
Environmental Compliance Oversight System (ECOS) – is a statewide computer application for stakeholders involved in the environmental process to provide enhanced tracking, reporting, and metrics for environmental issues. It provides an automated initial scoping form that generates recommended tasks to be performed based on the information that the user had entered.
E- STIP – is TxDOT’s electronic statewide transportation improvement program database that collects and stores project information for all highway, transit, non-motorized, and statewide planning projects to be constructed/implemented within the four-year STIP horizon. A similar format is development for the UTP.
Primavera Version 6 (P6) – is the new project management tracking program that allows users to access information on transportation projects in one database in real time. It creates project schedules for project development work beginning with preliminary tasks such as surveying, environmental clearance, right-of-way acquisition and utility coordination, through schematic and final planning, and contract letting.
Note: more details on tools and resource can be found in the Project Consistency Guidebook, page 15.

## Slide 30: Step 4 –Establish a PCM Work Flow
A basic workflow communicates and identifies the following three major points and establishes effective interactions between them:
  How should the project changes be identified and communicated through the different PD process stages?
  Who is held accountable for each step?
  Where are the supporting tools and resources located?
Notes: Step 4: Establish a PCM Work Flow – Establishing a workflow helps to clarify the steps necessary for maintaining project consistency. A workflow is a depiction of a sequence of operations and connected steps, which demonstrate the elements and flow of work in a simple form. A basic workflow communicates and identifies the following three major points and establishes simple and effective interactions between them.
How should the project changes be identified and communicated through the different PD process stages (action steps and time)?
Who is held accountable for each step?
Where are the supporting tools and resources located?

## Slide 31: Example Workflow for Preventing Project Inconsistencies
Detect and Document Changes in Project Design Scope, Limits, and Cost
Immediately Notify TP&D Director and Environmental Coordinator and Update DCIS, ECOS, and P6
Coordinate and communicate the changes with MPO staff
Communicate the changes to planning documents to District project managers and environmental coordinator and TPP
Who?
District Project Manager
How?
Project consistency checklist
Tools/Resources
DCIS, E-STIP, MTP/RTP, E-UTP*
Who? District Project Manager
How? Attach consistency check list
Who? District TP&D Director
TPP for UTP updates
Who? District TP&D Director
How? Attach the consistency checklist and details of the needed revisions to TIP and MTP/RTP
Notes: This is a simple example of a workflow for preventing project inconsistencies. This can be used as a starting pointing for Districts to develop their own workflow based on their specific practices.

## Slide 32: Step 5 – Systematic Communication
Effective communication and coordination procedures.
Personal-level communication necessary but not sufficient:
  Discontinuity: Staff turnover.
  No guarantee of a minimum level of communication.
Notes: Step 5: Systematic Coordination and Communication – Having a set of effective communication and coordination procedures, specifically with MPO staffers, is fundamental to achieve a successful project consistency management process. At many TxDOT Districts, communication and coordination occur on a personal level. While personal level communication and coordination is necessary and works in many instances, it has a few major flaws that can cause a breakdown of communication:
  Risk of discontinuity: Staff turnovers can cause a major breakdown of communication until the new person establishes the working/personal relationship.
  No guarantee of a minimum level of communication: It requires a strong personal-level relationship of the staff and can become unreliable if a strong working/personal relationship does not exist between the parties.

## Slide 33: Communication Best Practices
Regular Meetings with MPO – Keep MPOs aware of any changes to projects as well as amendments or updates needed in the planning documents.
Regular Internal Project Meetings – Help maintain communication as a project is developed at the District level.
Notes: Regular Meetings with MPO – The TP&D director and/or environmental coordinators in some Districts have monthly or quarterly meetings with MPO staffers. The main purpose of these meetings is to keep MPOs aware of any changes to projects as well as amendments or updates needed in the planning documents. Items such as project scope, costs, and limits are discussed in the meetings. A popular and effective practice is to prepare a list of projects to be discussed and send it to all participants in advance.
Regular Internal Project Meetings – Some Districts have regular internal meetings between the various District departments working on projects, including design, environmental, and planning. These internal meetings help maintain communication as a project is developed at the District level. The involved parties are usually the District planners, environmental coordinators, and design engineers. These meetings are held on a regular basis or at critical junctures such as 30 percent, 60 percent, and 90 percent design or environmental analysis completed.
The Districts that hold these meeting as part of their business routine have noted that:
The meetings have helped them ensure that the environmental coordinators and project managers are communicating on the environmental documents; and
The limits, scope, and project descriptions are kept consistent in all necessary documents.

## Slide 34: Project Inconsistency Detection
Project inconsistencies can occur despite all the precautions taken to prevent them.
Early detection and timely response.
Detect and address at critical junctures.
Recommended list of critical junctures:
  Design concept conference.
  30 percent and 90 percent PS&E development.
  Environmental scoping.
  Annual scheduled checking for all projects listed on TIP, STIP, UTP, and SPA list with an expected letting data within the next four years.
Notes: Project inconsistencies can occur despite all the precautions taken to prevent them. Early detection of these inconsistencies will help in minimizing unforeseen delays to the project. A project inconsistency detection process serves as a second line of defense in these situations. The goal is to detect and address the inconsistencies before they cause major delays as a result of a need for project and/or plan changes.
The focus of the PCM is to detect and address the inconsistencies at critical junctures along the PD process. Critical junctures are points during the PD process at which a project inconsistency can be detected and addressed. It is recommended that the Districts select at least three critical junctures for the purpose of project inconsistency detection; each covering a different stage of the project development. Districts can also establish schedule-based critical junctures (i.e., semi-annual or annual). The following is a recommended list of critical junctures for this purpose:
  Design concept conference.
  30 percent and 90 percent PS&E development.
  Environmental Scoping.
  Annual scheduled checking for all projects listed on TIP, STIP, UTP, and SPA list with an expected letting data within the next four years.

## Slide 35: Critical Junctures for Checking Project Consistency
Notes: The figure shows a simplified overview of the TxDOT PD process and where key TxDOT Divisions are involved along with a sample of critical junctures for checking project consistency.

## Slide 36: Project Consistency Checklist
Checklist is a tool for practitioners to reference during the development of a project to check for consistency.
Checklist highlights areas where inconsistency can become a problem.
Includes checking design cost, scope, and conformity information.
Notes: This screen shot shows the project consistency checklist that staff can use to check for consistency of the project’s design scope and cost throughout all the planning documents.
Please refer to Appendix A on page 19 in the Project Consistency Guidebook.

## Slide 37: Project Consistency Checklist – Project Overview
Notes: This screen shot shows the information in DCIS that needs to be consistent in all planning documents. It includes a section whereby if the project is in a nonattainment or maintenance area, the reader can check if the analysis years are correct in the MTP/RTP.

## Slide 38: Project Consistency Checklist – Design Concept
Notes: This section of the checklist helps ensuring that elements of the design concept are consistent in the environmental documents, DCIS, MTP/RTP, TIP/STIP and the UTP. Elements of the design concept include expected let date, expected year of completion, type of facility, limits, and roadway.

## Slide 39: Project Consistency Checklist – Design Scope and Cost
Notes: This section of the checklist includes more elements of the design scope (number of lanes, length, access control and number and location of interchanges) as well as project cost. Total federal funding in DCIS, TIP/STIP, and UTP/SPA must not exceed what is contained in the MTP/RTP by more than 50%.
A project with an estimated cost over $1.5 million in MTP/RTP, TIP, and STIP, the total federal funding cannot exceed by more than 50% over what is stated in the MTP/RTP, TIP, and STIP.

## Slide 40: Role of Finance Division
Updates letting schedule monthly based on letting list from Districts.
Prepares and submits Federal Project Agreement Authorization.
FIN Communication Role:
  Districts usually report funding changes to FIN and TPP.
  FIN communicates funding changes/decisions made by the TxDOT administration.
Notes: The main focus of this document is to outline the responsibilities and best practices at the District level where the majority of changes to a project occur. However, there are changes that are initiated at the Divisions, most notably the Finance Division (FIN).
Finance is involved at the very end of the project development process when the project is ready to let, but before the FHWA allocates the funding.
Every month, FIN receives a letting list from the Districts enumerating the projects that are environmentally cleared. Shortly before the letting date of a project, FIN prepares a Federal Project Agreement Authorization (FPAA) and sends the package to FHWA/FTA for their authorization to proceed.
The FPAA package includes project location information, description of work, ENV clearance, STIP approval, the amount of federal funds and the specific federal program that FIN estimated the project will need as well as any non-federal fund sources. After FHWA/FTA signs the FPAA, TxDOT can begin to incur costs for federal reimbursement.
FIN is involved in communication with the Districts in two ways:
FIN updates the funding changes that will impact the FPAA package sent to FHWA for authorization. In the majority of cases, the Districts know about the funding changes before FIN and TPP; therefore, the District staff needs to communicate the changes to FIN and TPP.
In some cases, changes can be made to funding of projects by TxDOT administration. Examples of such cases are budget cuts and the American Recovery and Reinvestment Act of 2009. In these cases, it is the responsibility of FIN to communicate the changes to the Districts and TPP in a timely manner.

## Slide 41: Project Consistency Guidebook
Notes: This document was developed for transportation professionals responsible for project development and has three basic goals:
Define project consistency and identify the causes of project inconsistencies and the critical junctures in the project development process where project consistency should be reviewed.
Identify resources and best practices that minimize project delays and financial risk, including the Project Consistency Checklist.
Provide contact information for external entities and TxDOT offices of primary responsibility (OPRs) as well as communication guidelines for resolving project inconsistencies.

## Slide 42: Project Consistency Guidebook
Notes: The Supplementary Information Document covers the environmental process, project development process, transportation planning and conformity.

## Slide 43: Additional Resources
The Transportation Planning Process: Key Issues. A Briefing Book for Transportation Decision makers, Officials, and Staff. U.S. Department of Transportation, 2007, http://www.planning.dot.gov/documents/briefingbook/bbook.htm.
Texas Department of Transportation. (2001). Transportation Planning Process Manual. Retrieved from http://onlinemanuals.txdot.gov/txdotmanuals/prc/transportation_planning_and_programming_process.htm.
Federal Highway Administration, 2010. Transportation Conformity: A Basic Guide for State and Local Officials, http://www.fhwa.dot.gov/environment/air_quality/conformity/guide/guide09.cfm.
Federal Highway Administration, Transportation Conformity, Linking Transportation and Air Quality. http://www.fhwa.dot.gov/environment/air_quality/conformity/con_broc.cfm.