## Sheet1
8:51
Date: 6/5/2024 |  | Notes: References to R and L are with respect to facing north.
Bridge Number: 101-0134 (NB I-39 over Kishuakee)
Inspectors: Mathew Ingram, Denilson Saavedra
Weather: 67 degrees, cloudy
Photo No. | Photo name or description | Looking
1 | Tendon 7L with end cap removed at pier 2 | N
2 | Tendon 7L with sample removed at pier 2 | N
3 | Tendon 8R at pier 2 with end cap removed | N
4 | Tendon 8R at pier 2 after sample taken | NE
5 | Tendon 8L at pier 2 with end cap removed, missing sealing gasket | N
6 | Tendon 8L at pier 2 with sample removed | N
7 | Tendon 6R at pier 4 with end cap removed | S
8 | Tendon 5L at pier 4 with end cap removed | S
9 | Tendon 6R at pier 4 with sample taken | S
10 | Tendon 5L at pier 4 corrosion at wedge block | S
11 | Tendon 5L at pier 4 after sample taken | S
12 | Tendon 5R at pier 4 - excessive caulk misaligned bolts at end cap - did not remove because of this | S
13 | Tendon 6L at pier 4 - end cap removed | S
14 | Tendon 6L at pier 4 after sample | S
15 | Tendon 12R at pier 4 end cap removed | N
16 | Tendon 12R at pier 4 after sample taken | N
17 | Tendon 12L at pier 4 end cap removed | N
18 | Tendon 11L at pier 4 end cap removed | N
19 | Tendon 11R at pier 4 end cap removed | N
20 | Tendon 11R at pier 4 after sample taken | N
21 | Tendon 11L at pier 4 after sample taken | N
22 | Tendon 12L at pier 4 after sample taken | N
23 | Tendon 9R at N abut after end cap removel | S
24 | Tendon 9R at N abut after sample taken | S
25 | Tendon 9L at N abut after end cap removal | S
26 | Tendon 9L at N abut after sample taken | S
27 | Tendon 10R at N abut with end cap removed | S
28 | Tendon 10R at N abut after sample taken | S
29 | Tendon 10L at N abut with end cap removed | S
30 | Tendon 10L at N abut after sample taken | S
31 | Tendon 5R at pier 1, excessive sealant at end cap (was this retensioned?), pier 4 similar | N
32 | Tendon 5R trumpet base plate with torched base and missing bolts | N
33 | Tendon 5R trumpet base plate with torched base and missing bolts | N
34 | Tendon 5R trumpet base plate with torched base and missing bolts | N
35 | Tendon 5R at pier 1 end cap removed | N
36 | Tendon 5R at pier 1 after sample removed | N
37 | Tendon 1R near south abut, sheathing removed and top grout removed, corrosion found about 1 ft from end | S
38 | Tendon 1R near south abut, sheathing removed and top grout removed, corrosion found about 1 ft from end | S
39 | Tendon 1R near S abut, sheathing removed and top grout removed about 4 ft from end | S
40 | Tendon 1R near S abut, sheathing removed and top grout removed about 4 ft from end | N
41 | Tendon 2R approx 8 ft delam near deviator 2 | N
42 | Visible water leakage between precast box segments NBI-S5 and NBI-S3 | N
43 | Tendon 2R, 2 ft delam at deviator 3 | S
44 | Tendon 6L, 2 ft delam at pier 3 | NW