## Summary
Test Results Summary
Test | Total Tests | Pass | Fail | Needs Investigation | Reviewed Pass | Defer | Retest 1 Pass | Retest 1 Fail | Retest 2 Pass | Retest 2 Fail | Remaining | Success Rate (of tests executed) | Test Description
Self Nav | 12 | 9 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 100% | Tests the ability of the vehicle to run a route without sensor input, aside from GPS and inertial components.
Mode Transitions | 24 | 21 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 100% | Tests the ability of the vehicle to transition in and out of auto and manual mode under different conditions.
Path Following | 21 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | n/a | Tests the ability of the vehicle to run a route with all sensors active and under nominal conditions.
Object Detection and Avoidance | 90 | 81 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 100% | Test the ability of the vehicle to detect and avoid a variety of obstacles.
Following, Pacing, Stopping | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | n/a | Test the ability of the vehicle to detect object speed and pace behind at an appropriate distance.
Intersections | 42 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | n/a | Tests the ability of the vehicle to navigate intersections, with and without other vehicles.
Use Case- Remote Start | 21 | 6 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 100% | Tests the ability of the vehicle to turn on and off remotely.
Use Case- Bus Wash | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | n/a | Tests the ability of the vehicle to navigate lanelines and the bus wash without GPS.
Use Case- Charging | 6 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 100% | Tests the ability of the vehicle to navigate under the pantograph charger and charge the vehicle.
Use Case- Precision Parking | 15 | 3 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 100% | Tests the ability of the vehicle to park precisely (=/<12") in same location over multiple repititions.
Robustness Testing | 16 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | n/a | Test the ability of the vehicle to drive in automated mode for 30 minutes without human intervention.
Grand Total | 274 | 125 | 0 | 0 | 0 | 148 | 1 | 0 | 0 | 0 | 0 | 100%
Test Results | Description
Pass | The test passed. The expected results were met.
Fail | The test failed. The expected results were not met.
Needs Investigation | Inconclusive. There may have been an action that warrants a log review.
Reviewed Pass | Pass resulting from an log investigation. Check the comments for more details.
Defer | The test will not be be executed during the testing phase.
Not Executed | The test has not been executed yet.

## Test Cases
Category | Test # | Test Description | Expected Results | Test Comments | Test Result | Date | Test Log Link | Test Eng(s) | Retest 1 Comments | Retest 1 Result | Retest 1 Log Link | Retest 2 Comments | Retest 2 Result | Retest 2 Log Link | Speed | Weather Conditions
Self Nav | 1 | Run the AV on a self-nav mission straight ahead with the sensors switched off. | The bus should be able to path follow based upon GPS alone. | n/a | Pass | 2025-06-09 | 06-09-2025_17-52-13_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Self Nav | 2 | Run the AV on a self-nav mission straight ahead with the sensors switched off. | The bus should be able to path follow based upon GPS alone. | n/a | Pass | 2025-06-09 | 06-09-2025_17-57-10_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Self Nav | 3 | Run the AV on a self-nav mission straight ahead with the sensors switched off. | The bus should be able to path follow based upon GPS alone. | n/a | Pass | 2025-06-09 | 06-09-2025_18-01-29_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Self Nav | 4 | Run the AV on a self-nav mission with a left turn ahead with the sensors switched off. | The bus should be able to path follow based upon GPS alone. | n/a | Pass | 2025-06-09 | 06-09-2025_17-52-13_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Self Nav | 5 | Run the AV on a self-nav mission with a left turn ahead with the sensors switched off. | The bus should be able to path follow based upon GPS alone. | n/a | Pass | 2025-06-09 | 06-09-2025_17-57-10_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Self Nav | 6 | Run the AV on a self-nav mission with a left turn ahead with the sensors switched off. | The bus should be able to path follow based upon GPS alone. | n/a | Pass | 2025-06-09 | 06-09-2025_18-01-29_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Self Nav | 7 | Run the AV on a mission with a right turn ahead with the sensors switched off. | The bus should be able to path follow based upon GPS alone. |  | Defer
Self Nav | 8 | Run the AV on a mission with a right turn ahead with the sensors switched off. | The bus should be able to path follow based upon GPS alone. |  | Defer
Self Nav | 9 | Run the AV on a mission with a right turn ahead with the sensors switched off. | The bus should be able to path follow based upon GPS alone. |  | Defer
Self Nav | 10 | Run the AV on a mission straight through a stop sign controlled instersection ahead with the sensors switched off. | The bus should be able to path follow based upon GPS alone. | n/a | Pass | 2025-06-09 | 06-09-2025_18-14-22_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Self Nav | 11 | Run the AV on a mission straight through a stop sign controlled instersection ahead with the sensors switched off. | The bus should be able to path follow based upon GPS alone. | n/a | Pass | 2025-06-09 | 06-09-2025_18-20-04_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Self Nav | 12 | Run the AV on a mission straight through a stop sign controlled instersection ahead with the sensors switched off. | The bus should be able to path follow based upon GPS alone. | n/a | Pass | 2025-06-09 | 06-09-2025_18-24-43_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Mode Transitions | 1 | With the AV on, run a mission aligned with the route, switch from manual mode and transition into auto mode. | The bus should begin running the mission autonimously. | n/a | Pass | 2025-06-09 | 06-09-2025_18-43-36_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Mode Transitions | 2 | With the AV on, run a mission aligned with the route, switch from manual mode and transition into auto mode. | The bus should begin running the mission autonimously. | n/a | Pass | 2025-06-09 | 06-09-2025_18-52-15_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Mode Transitions | 3 | With the AV on, run a mission aligned with the route, switch from manual mode and transition into auto mode. | The bus should begin running the mission autonimously. | n/a | Pass | 2025-06-09 | 06-09-2025_18-53-18_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Mode Transitions | 4 | With the AV on, running a mission in auto mode, transition into manual mode. | The bus should transition to operator control. | n/a | Pass | 2025-06-09 | 06-09-2025_18-31-49_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Mode Transitions | 5 | With the AV on, running a mission in auto mode, transition into manual mode. | The bus should transition to operator control. | n/a | Pass | 2025-06-09 | 06-09-2025_18-32-37_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Mode Transitions | 6 | With the AV on, running a mission in auto mode, transition into manual mode. | The bus should transition to operator control. | n/a | Pass | 2025-06-09 | 06-09-2025_18-35-01_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Mode Transitions | 7 | With the AV on and in manual mode, attempt to transition into auto mode when not aligned with route, offset left by half bus width. | Bus corrects to path and proceeds | n/a | Pass | 2025-06-09 | 06-09-2025_19-04-40_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Mode Transitions | 8 | With the AV on and in manual mode, attempt to transition into auto mode when not aligned with route, offset left by half bus width. | Bus corrects to path and proceeds | n/a | Pass | 2025-06-09 | 06-09-2025_19-06-08_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Mode Transitions | 9 | With the AV on and in manual mode, attempt to transition into auto mode when not aligned with route, offset left by half bus width. | Bus corrects to path and proceeds | n/a | Pass | 2025-06-09 | 06-09-2025_19-06-53_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Mode Transitions | 10 | With the AV on and in manual mode, attempt to transition into auto mode when not aligned with route, offset right by half bus width. | Bus corrects to path and proceeds | n/a | Pass | 2025-06-09 | 06-09-2025_19-10-49_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Mode Transitions | 11 | With the AV on and in manual mode, attempt to transition into auto mode when not aligned with route, offset right by half bus width. | Bus corrects to path and proceeds | n/a | Pass | 2025-06-09 | 06-09-2025_19-11-36_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Mode Transitions | 12 | With the AV on and in manual mode, attempt to transition into auto mode when not aligned with route, offset right by half bus width. | Bus corrects to path and proceeds | n/a | Pass | 2025-06-09 | 06-09-2025_19-12-13_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Mode Transitions | 13 | With the AV on and in manual mode, attempt to transition into auto mode when not aligned with route, offset left by a full bus width. | Mission will not start due to off track distance - 4M tolerance | n/a | Pass | 2025-06-09 | 06-09-2025_19-18-11_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Mode Transitions | 14 | With the AV on and in manual mode, attempt to transition into auto mode when not aligned with route, offset left by a full bus width. | Mission will not start due to off track distance - 4M tolerance | n/a | Pass | 2025-06-09 | 06-09-2025_19-18-17_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Mode Transitions | 15 | With the AV on and in manual mode, attempt to transition into auto mode when not aligned with route, offset left by a full bus width. | Mission will not start due to off track distance - 4M tolerance | n/a | Pass | 2025-06-09 | 06-09-2025_19-18-44_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Mode Transitions | 16 | With the AV on and in manual mode, attempt to transition into auto mode when not aligned with route, offset right by a full bus width. | Mission will not start due to off track distance - 4M tolerance | n/a | Pass | 2025-06-09 | 06-09-2025_20-09-02_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Mode Transitions | 17 | With the AV on and in manual mode, attempt to transition into auto mode when not aligned with route, offset right by a full bus width. | Mission will not start due to off track distance - 4M tolerance | n/a | Pass | 2025-06-09 | 06-09-2025_20-11-21_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Mode Transitions | 18 | With the AV on and in manual mode, attempt to transition into auto mode when not aligned with route, offset right by a full bus width. | Mission will not start due to off track distance - 4M tolerance | n/a | Pass | 2025-06-09 | 06-09-2025_20-12-17_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Mode Transitions | 19 | With the AV on and in manual mode, attempt to transition into auto mode when aligned with the route on a curve portion of the route. | As long as it is still close to the path, the vehicle will resume auto mode | n/a | Pass | 2025-06-09 | 06-09-2025_20-18-09_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Mode Transitions | 20 | With the AV on and in manual mode, attempt to transition into auto mode when aligned with the route on a curve portion of the route. | As long as it is still close to the path, the vehicle will resume auto mode | n/a | Pass | 2025-06-09 | 06-09-2025_20-20-31_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Mode Transitions | 21 | With the AV on and in manual mode, attempt to transition into auto mode when aligned with the route on a curve portion of the route. | As long as it is still close to the path, the vehicle will resume auto mode | n/a | Pass | 2025-06-09 | 06-09-2025_20-21-58_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
Mode Transitions | 22 | With the vehicle on and in auto mode, press the e-stop | Brakes apply quickly, parking brake is set. Mission can not resume until e-stop button is reset and parking brake is manually released. TONY is not stopped. Also locks out PB until e-stop is reset |  | Defer
Mode Transitions | 23 | With the vehicle on and in auto mode, press the e-stop | Brakes apply quickly, parking brake is set. Mission can not resume until e-stop button is reset and parking brake is manually released. TONY is not stopped. Also locks out PB until e-stop is reset |  | Defer
Mode Transitions | 24 | With the vehicle on and in auto mode, press the e-stop | Brakes apply quickly, parking brake is set. Mission can not resume until e-stop button is reset and parking brake is manually released. TONY is not stopped. Also locks out PB until e-stop is reset |  | Defer
Path Following | 1 | BEB runs full route with all sensors on & GPS nav functionality active with no obstacles present along the route. | The AV should run the mission, start to finish, with no false detections. |  | Defer
Path Following | 2 | BEB runs full route with all sensors on & GPS nav functionality active with no obstacles present along the route. | The AV should run the mission, start to finish, with no false detections. |  | Defer
Path Following | 3 | BEB runs full route with all sensors on & GPS nav functionality active with no obstacles present along the route. | The AV should run the mission, start to finish, with no false detections. |  | Defer
Path Following | 4 | BEB following planned route with a parked vehicle overlapping travel lane on BEB Passenger side by half a bus width | The AV should stop for the parked vehicle, and possibly bump around the parked vehicle, depending on the route lane width. |  | Defer
Path Following | 5 | BEB following planned route with a parked vehicle overlapping travel lane on BEB Passenger side by half a bus width | The AV should stop for the parked vehicle, and possibly bump around the parked vehicle, depending on the route lane width. |  | Defer
Path Following | 6 | BEB following planned route with a parked vehicle overlapping travel lane on BEB Passenger side by half a bus width | The AV should stop for the parked vehicle, and possibly bump around the parked vehicle, depending on the route lane width. |  | Defer
Path Following | 7 | BEB following planned route with a parked vehicle overlapping travel lane on BEB Driver side by half a bus width | The AV should stop for the parked vehicle. Manual takeover will be required to pass around the parked vehicle overlapping into the driver's lane. |  | Defer
Path Following | 8 | BEB following planned route with a parked vehicle overlapping travel lane on BEB Driver side by half a bus width | The AV should stop for the parked vehicle. Manual takeover will be required to pass around the parked vehicle overlapping into the driver's lane. |  | Defer
Path Following | 9 | BEB following planned route with a parked vehicle overlapping travel lane on BEB Driver side by half a bus width | The AV should stop for the parked vehicle. Manual takeover will be required to pass around the parked vehicle overlapping into the driver's lane. |  | Defer
Path Following | 10 | BEB following planned route through a left turn with a stopped vehicle slightly overlapping travel lane on BEB Driver side | The AV should stop for the parked vehicle. Manual takeover will be required to pass around the parked vehicle overlapping into the driver's lane. |  | Defer
Path Following | 11 | BEB following planned route through a left turn with a stopped vehicle slightly overlapping travel lane on BEB Driver side | The AV should stop for the parked vehicle. Manual takeover will be required to pass around the parked vehicle overlapping into the driver's lane. |  | Defer
Path Following | 12 | BEB following planned route through a left turn with a stopped vehicle slightly overlapping travel lane on BEB Driver side | The AV should stop for the parked vehicle. Manual takeover will be required to pass around the parked vehicle overlapping into the driver's lane. |  | Defer
Path Following | 13 | BEB following planned route through a right turn with a stopped vehicle slightly overlapping travel lane on BEB Driver side | The AV should stop for the parked vehicle. Manual takeover will be required to pass around the parked vehicle overlapping into the driver's lane. |  | Defer
Path Following | 14 | BEB following planned route through a right turn with a stopped vehicle slightly overlapping travel lane on BEB Driver side | The AV should stop for the parked vehicle. Manual takeover will be required to pass around the parked vehicle overlapping into the driver's lane. |  | Defer
Path Following | 15 | BEB following planned route through a right turn with a stopped vehicle slightly overlapping travel lane on BEB Driver side | The AV should stop for the parked vehicle. Manual takeover will be required to pass around the parked vehicle overlapping into the driver's lane. |  | Defer
Path Following | 16 | BEB following planned route through a left turn with a stopped vehicle slightly overlapping travel lane on BEB Passenger side | The AV should stop for the parked vehicle, and possibly bump around the parked vehicle, depending on the route lane width. |  | Defer
Path Following | 17 | BEB following planned route through a left turn with a stopped vehicle slightly overlapping travel lane on BEB Passenger side | The AV should stop for the parked vehicle, and possibly bump around the parked vehicle, depending on the route lane width. |  | Defer
Path Following | 18 | BEB following planned route through a left turn with a stopped vehicle slightly overlapping travel lane on BEB Passenger side | The AV should stop for the parked vehicle, and possibly bump around the parked vehicle, depending on the route lane width. |  | Defer
Path Following | 19 | BEB following planned route through a right turn with a stopped vehicle slightly overlapping travel lane on BEB Passenger side | The AV should stop for the parked vehicle, and possibly bump around the parked vehicle, depending on the route lane width. |  | Defer
Path Following | 20 | BEB following planned route through a right turn with a stopped vehicle slightly overlapping travel lane on BEB Passenger side | The AV should stop for the parked vehicle, and possibly bump around the parked vehicle, depending on the route lane width. |  | Defer
Path Following | 21 | BEB following planned route through a right turn with a stopped vehicle slightly overlapping travel lane on BEB Passenger side | The AV should stop for the parked vehicle, and possibly bump around the parked vehicle, depending on the route lane width. |  | Defer
ODOA | 1 | orange construction barrel in lane of travel | AV should stop for the obstacle and resume it's mission once the obstacle is cleared from the lane. | yellow barrel used. only driver intervention was releasing interlock since no assistant to move barrel and door had to be opened | Pass | 2025-06-08 | 12-30-19 | DP | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 2 | orange construction barrel in lane of travel | AV should stop for the obstacle and resume it's mission once the obstacle is cleared from the lane. | n/a | Pass | 2025-06-08 | 12-33-28 | DP | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 3 | orange construction barrel in lane of travel | AV should stop for the obstacle and resume it's mission once the obstacle is cleared from the lane. | n/a | Pass | 2025-06-08 | 12-36-24 | DP | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 4 | pedestrian standing in the lane of travel | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-08 | 12-38-25 | DP | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 5 | pedestrian standing in the lane of travel | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-08 | 12-40-06 | DP | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 6 | pedestrian standing in the lane of travel | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-08 | 12-40-44 | DP | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 7 | stopped vehicle in the lane of travel | AV should stop for the vehicle and resume it's mission once the vehicle is cleared from the lane. | completed all three in a single long run | Pass | 2025-06-08 | 12-53-42 | DP | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 8 | stopped vehicle in the lane of travel | AV should stop for the vehicle and resume it's mission once the vehicle is cleared from the lane. | completed all three in a single long run | Pass | 2025-06-08 | 12-53-42 | DP | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 9 | stopped vehicle in the lane of travel | AV should stop for the vehicle and resume it's mission once the vehicle is cleared from the lane. | completed all three in a single long run | Pass | 2025-06-08 | 12-53-42 | DP | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 10 | vehicle reversing into the lane of travel from the left | AV should stop for the vehicle and resume it's mission once the vehicle is cleared from the lane. | n/a | Pass | 2025-06-08 | 12-57-56 | DP | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 11 | vehicle reversing into the lane of travel from the left | AV should stop for the vehicle and resume it's mission once the vehicle is cleared from the lane. | n/a | Pass | 2025-06-08 | 12-55-59 | DP | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 12 | vehicle reversing into the lane of travel from the left | AV should stop for the vehicle and resume it's mission once the vehicle is cleared from the lane. | n/a | Pass | 2025-06-08 | 13-01-52 | DP | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 13 | vehicle reversing into the lane of travel from the right | AV should stop for the vehicle and resume it's mission once the vehicle is cleared from the lane. | n/a | Pass | 2025-06-10 | 06-10-2025_17-38-27_RC | MG | [6 empty] | 5 MPH | partly cloudy 90+ degrees
ODOA | 14 | vehicle reversing into the lane of travel from the right | AV should stop for the vehicle and resume it's mission once the vehicle is cleared from the lane. | n/a | Pass | 2025-06-10 | 06-10-2025_17-39-27_RC | MG | [6 empty] | 5 MPH | partly cloudy 90+ degrees
ODOA | 15 | vehicle reversing into the lane of travel from the right | AV should stop for the vehicle and resume it's mission once the vehicle is cleared from the lane. | n/a | Pass | 2025-06-10 | 06-10-2025_17-40-32_RC | MG | [6 empty] | 5 MPH | partly cloudy 90+ degrees
ODOA | 16 | crossing pedestrian- close straight left to right | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | 10m away | Pass | 2025-06-11 | 06-11-2025_16-28-35_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 17 | crossing pedestrian- close straight left to right | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | 10m away | Pass | 2025-06-11 | 06-11-2025_16-30-08_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 18 | crossing pedestrian- close straight left to right | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | 10m away | Pass | 2025-06-11 | 06-11-2025_16-32-25_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 19 | crossing pedestrian- close straight right to left | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | 10m away | Pass | 2025-06-11 | 06-11-2025_16-34-48_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 20 | crossing pedestrian- close straight right to left | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | 10m away | Pass | 2025-06-11 | 06-11-2025_16-35-43_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 21 | crossing pedestrian- close straight right to left | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | 10m away | Pass | 2025-06-11 | 06-11-2025_16-36-25_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 22 | crossing pedestrian- medium straight left to right | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | 25m away | Pass | 2025-06-11 | 06-11-2025_16-44-57_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 23 | crossing pedestrian- medium straight left to right | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | 25m away | Pass | 2025-06-11 | 06-11-2025_16-45-56_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 24 | crossing pedestrian- medium straight left to right | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | 25m away | Pass | 2025-06-11 | 06-11-2025_16-46-53_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 25 | crossing pedestrian- medium straight right to left | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | 25m away | Pass | 2025-06-11 | 06-11-2025_16-41-41_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 26 | crossing pedestrian- medium straight right to left | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | 25m away | Pass | 2025-06-11 | 06-11-2025_16-42-39_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 27 | crossing pedestrian- medium straight right to left | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | 25m away | Pass | 2025-06-11 | 06-11-2025_16-43-36_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 28 | AV stops for crossing pedestrian- close during left turn inside to outside | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-11 | 06-11-2025_17-21-03_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 29 | AV stops for crossing pedestrian- close during left turn inside to outside | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-11 | 06-11-2025_17-21-55_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 30 | AV stops for crossing pedestrian- close during left turn inside to outside | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-11 | 06-11-2025_17-22-55_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 31 | AV stops for crossing pedestrian- close during left turn outside to inside | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-11 | 06-11-2025_17-24-20_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 32 | AV stops for crossing pedestrian- close during left turn outside to inside | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-11 | 06-11-2025_17-25-27_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 33 | AV stops for crossing pedestrian- close during left turn outside to inside | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-11 | 06-11-2025_17-26-32_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 34 | AV stops for crossing pedestrian- close during right turn inside to outside | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-11 | 06-11-2025_17-07-50_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 35 | AV stops for crossing pedestrian- close during right turn inside to outside | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-11 | 06-11-2025_17-10-00_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 36 | AV stops for crossing pedestrian- close during right turn inside to outside | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-11 | 06-11-2025_17-11-07_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 37 | AV stops for crossing pedestrian- close during right turn outside to inside | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-11 | 06-11-2025_17-12-50_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 38 | AV stops for crossing pedestrian- close during right turn outside to inside | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-11 | 06-11-2025_17-15-49_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 39 | AV stops for crossing pedestrian- close during right turn outside to inside | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-11 | 06-11-2025_17-16-47_RC | MG | [6 empty] | 5 MPH | clear, sunny, 90+ degrees
ODOA | 40 | AV slows or stops for crossing pedestrian- medium during right turn inside to outside | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-12 | 06-12-2025_18-30-33_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 41 | AV slows or stops for crossing pedestrian- medium during right turn inside to outside | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-12 | 06-12-2025_18-31-45_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 42 | AV slows or stops for crossing pedestrian- medium during right turn inside to outside | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-12 | 06-12-2025_18-32-44_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 43 | AV slows or stops for crossing pedestrian- medium during right turn outside to inside | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-12 | 06-12-2025_18-37-17_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 44 | AV slows or stops for crossing pedestrian- medium during right turn outside to inside | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-12 | 06-12-2025_18-38-23_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 45 | AV slows or stops for crossing pedestrian- medium during right turn outside to inside | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-12 | 06-12-2025_18-39-45_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 46 | AV slows or stops for crossing pedestrian- medium during left turn inside to outside | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-12 | 06-12-2025_18-50-44_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 47 | AV slows or stops for crossing pedestrian- medium during left turn inside to outside | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-12 | 06-12-2025_18-52-21_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 48 | AV slows or stops for crossing pedestrian- medium during left turn inside to outside | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-12 | 06-12-2025_18-53-49_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 49 | AV slows or stops for crossing pedestrian- medium during left turn outside to inside | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-12 | 06-12-2025_19-01-42_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 50 | AV slows or stops for crossing pedestrian- medium during left turn outside to inside | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-12 | 06-12-2025_19-02-27_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 51 | AV slows or stops for crossing pedestrian- medium during left turn outside to inside | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-12 | 06-12-2025_19-03-07_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 52 | AV doesn't stop for crossing pedestrian- far left to right | AV should continue the mission as normal without any hesitation. | 30+ m away | Pass | 2025-06-12 | 06-12-2025_16-03-41_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 53 | AV doesn't stop for crossing pedestrian- far left to right | AV should continue the mission as normal without any hesitation. | 30+ m away | Pass | 2025-06-12 | 06-12-2025_16-05-05_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 54 | AV doesn't stop for crossing pedestrian- far left to right | AV should continue the mission as normal without any hesitation. | 30+ m away | Pass | 2025-06-12 | 06-12-2025_16-06-00_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 55 | AV doesn't stop for crossing pedestrian- far right to left | AV should continue the mission as normal without any hesitation. | 30+ m away | Pass | 2025-06-12 | 06-12-2025_16-08-08_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 56 | AV doesn't stop for crossing pedestrian- far right to left | AV should continue the mission as normal without any hesitation. | 30+ m away | Pass | 2025-06-12 | 06-12-2025_16-09-08_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 57 | AV doesn't stop for crossing pedestrian- far right to left | AV should continue the mission as normal without any hesitation. | 30+ m away | Pass | 2025-06-12 | 06-12-2025_16-10-00_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 58 | AV doesn't stop for approaching pedestrian who stops before entering the lane of travel on the left | AV should continue the mission as normal without any hesitation. | n/a | Pass | 2025-06-12 | 06-12-2025_16-11-39_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 59 | AV doesn't stop for approaching pedestrian who stops before entering the lane of travel on the left | AV should continue the mission as normal without any hesitation. | n/a | Pass | 2025-06-12 | 06-12-2025_16-12-42_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 60 | AV doesn't stop for approaching pedestrian who stops before entering the lane of travel on the left | AV should continue the mission as normal without any hesitation. | n/a | Pass | 2025-06-12 | 06-12-2025_16-13-29_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 61 | AV doesn't stop for approaching pedestrian who stops before entering the lane of travel on the right | AV should continue the mission as normal without any hesitation. | n/a | Pass | 2025-06-12 | 06-12-2025_16-14-31_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 62 | AV doesn't stop for approaching pedestrian who stops before entering the lane of travel on the right | AV should continue the mission as normal without any hesitation. | n/a | Pass | 2025-06-12 | 06-12-2025_16-15-35_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 63 | AV doesn't stop for approaching pedestrian who stops before entering the lane of travel on the right | AV should continue the mission as normal without any hesitation. | n/a | Pass | 2025-06-12 | 06-12-2025_16-16-35_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 64 | AV stops for approaching pedestrian who infringes upon the lane of travel on the left | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-12 | 06-12-2025_12-51-52_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 65 | AV stops for approaching pedestrian who infringes upon the lane of travel on the left | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-12 | 06-12-2025_18-18-51_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 66 | AV stops for approaching pedestrian who infringes upon the lane of travel on the left | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-12 | 06-12-2025_18-19-35_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 67 | AV stops for approaching pedestrian who infringes upon the lane of travel on the right | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-12 | 06-12-2025_18-23-13_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 68 | AV stops for approaching pedestrian who infringes upon the lane of travel on the right | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-12 | 06-12-2025_18-23-58_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 69 | AV stops for approaching pedestrian who infringes upon the lane of travel on the right | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. | n/a | Pass | 2025-06-12 | 06-12-2025_18-24-40_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 70 | AV stops for pedestrian who enters the lane of travel, trips, and lays on the ground | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. |  | Defer
ODOA | 71 | AV stops for pedestrian who enters the lane of travel, trips, and lays on the ground | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. |  | Defer
ODOA | 72 | AV stops for pedestrian who enters the lane of travel, trips, and lays on the ground | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. |  | Defer
ODOA | 73 | AV stops for pedestrian laying on the ground in the lane of travel when the vehicle approaches | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. |  | Defer
ODOA | 74 | AV stops for pedestrian laying on the ground in the lane of travel when the vehicle approaches | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. |  | Defer
ODOA | 75 | AV stops for pedestrian laying on the ground in the lane of travel when the vehicle approaches | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. |  | Defer
ODOA | 76 | AV stops for pedestrian on knees tying shoe in the lane of travel when the vehicle approaches | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. |  | Defer
ODOA | 77 | AV stops for pedestrian on knees tying shoe in the lane of travel when the vehicle approaches | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. |  | Defer
ODOA | 78 | AV stops for pedestrian on knees tying shoe in the lane of travel when the vehicle approaches | AV should stop for the pedestrian and resume it's mission once the pedestrian moves out of the lane. |  | Defer
ODOA | 79 | AV stops for already open vehicle car door on the left | AV should stop for the vehicle with the open car door. The AV may resume it's mission once the car door is closed, depending upon the vehicle's encroachment into the lane. | n/a | Pass | 2025-06-12 | 06-12-2025_12-50-16_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 80 | AV stops for already open vehicle car door on the left | AV should stop for the vehicle with the open car door. The AV may resume it's mission once the car door is closed, depending upon the vehicle's encroachment into the lane. | n/a | Pass | 2025-06-12 | 06-12-2025_12-51-04_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 81 | AV stops for already open vehicle car door on the left | AV should stop for the vehicle with the open car door. The AV may resume it's mission once the car door is closed, depending upon the vehicle's encroachment into the lane. | n/a | Pass | 2025-06-12 | 06-12-2025_12-51-52_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 82 | AV stops for already open vehicle car door on the right | AV should stop for the vehicle with the open car door. The AV may resume it's mission once the car door is closed, by bumping aroung the vehicle. This will depend upon the vehicle's encroachment into the lane and the set lane width. | n/a | Pass | 2025-06-10 | 06-10-2025_17-12-37_RC | MG | [6 empty] | 5 MPH | partly cloudy 90+ degrees
ODOA | 83 | AV stops for already open vehicle car door on the right | AV should stop for the vehicle with the open car door. The AV may resume it's mission once the car door is closed, by bumping aroung the vehicle. This will depend upon the vehicle's encroachment into the lane and the set lane width. | n/a | Pass | 2025-06-10 | 06-10-2025_17-13-28_RC | MG | [6 empty] | 5 MPH | partly cloudy 90+ degrees
ODOA | 84 | AV stops for already open vehicle car door on the right | AV should stop for the vehicle with the open car door. The AV may resume it's mission once the car door is closed, by bumping aroung the vehicle. This will depend upon the vehicle's encroachment into the lane and the set lane width. | n/a | Pass | 2025-06-10 | 06-10-2025_17-15-12_RC | MG | [6 empty] | 5 MPH | partly cloudy 90+ degrees
ODOA | 85 | AV stops for late opened vehicle car door on the left | AV should stop for the vehicle with the open car door. The AV may resume it's mission once the car door is closed, depending upon the vehicle's encroachment into the lane. | n/a | Pass | 2025-06-12 | 06-12-2025_12-50-16_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 86 | AV stops for late opened vehicle car door on the left | AV should stop for the vehicle with the open car door. The AV may resume it's mission once the car door is closed, depending upon the vehicle's encroachment into the lane. | n/a | Pass | 2025-06-12 | 06-12-2025_12-51-04_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 87 | AV stops for late opened vehicle car door on the left | AV should stop for the vehicle with the open car door. The AV may resume it's mission once the car door is closed, depending upon the vehicle's encroachment into the lane. | n/a | Pass | 2025-06-12 | 06-12-2025_12-51-52_RC | MG | [6 empty] | 5 MPH | partly sunny, 90+ degrees
ODOA | 88 | AV stops for late opened vehicle car door on the right | AV should stop for the vehicle with the open car door. The AV may resume it's mission once the car door is closed, by bumping aroung the vehicle. This will depend upon the vehicle's encroachment into the lane and the set lane width. | n/a | Pass | 2025-06-10 | 06-10-2025_17-16-38_RC | MG | [6 empty] | 5 MPH | partly cloudy 90+ degrees
ODOA | 89 | AV stops for late opened vehicle car door on the right | AV should stop for the vehicle with the open car door. The AV may resume it's mission once the car door is closed, by bumping aroung the vehicle. This will depend upon the vehicle's encroachment into the lane and the set lane width. | n/a | Pass | 2025-06-10 | 06-10-2025_17-17-27_RC | MG | [6 empty] | 5 MPH | partly cloudy 90+ degrees
ODOA | 90 | AV stops for late opened vehicle car door on the right | AV should stop for the vehicle with the open car door. The AV may resume it's mission once the car door is closed, by bumping aroung the vehicle. This will depend upon the vehicle's encroachment into the lane and the set lane width. | n/a | Pass | 2025-06-10 | 06-10-2025_17-21-26_RC | MG | [6 empty] | 5 MPH | partly cloudy 90+ degrees
Following, Pacing, Stopping | 1 | AV stops no further than .5 m prior to stop point, nor .5m beyond stop point at 5 mph | AV should stop better than the .5m accuracy |  | Defer
Following, Pacing, Stopping | 2 | AV stops no further than .5 m prior to stop point, nor .5m beyond stop point at 5 mph | AV should stop better than the .5m accuracy |  | Defer
Following, Pacing, Stopping | 3 | AV stops no further than .5 m prior to stop point, nor .5m beyond stop point at 5 mph | AV should stop better than the .5m accuracy |  | Defer
Following, Pacing, Stopping | 4 | Target Vehicle is ahead of AV running at 3 mph in the lane. | AV should slow and pace the TV at 3 mph. |  | Defer
Following, Pacing, Stopping | 5 | Target Vehicle is ahead of AV running at 3 mph in the lane. | AV should slow and pace the TV at 3 mph. |  | Defer
Following, Pacing, Stopping | 6 | Target Vehicle is ahead of AV running at 3 mph in the lane. | AV should slow and pace the TV at 3 mph. |  | Defer
Following, Pacing, Stopping | 7 | AV runs up behind a pedestrian while navigating 5 mph in the lane. | AV should slow and pace the pedestrian |  | Defer
Following, Pacing, Stopping | 8 | AV runs up behind a pedestrian while navigating 5 mph in the lane. | AV should slow and pace the pedestrian |  | Defer
Following, Pacing, Stopping | 9 | AV runs up behind a pedestrian while navigating 5 mph in the lane. | AV should slow and pace the pedestrian |  | Defer
Following, Pacing, Stopping | 10 | AV approaches stopped TV in the lane at 5 mph. | AV should stop, and as TV pulls away, the AV follows. |  | Defer
Following, Pacing, Stopping | 11 | AV approaches stopped TV in the lane at 5 mph. | AV should stop, and as TV pulls away, the AV follows. |  | Defer
Following, Pacing, Stopping | 12 | AV approaches stopped TV in the lane at 5 mph. | AV should stop, and as TV pulls away, the AV follows. |  | Defer
Following, Pacing, Stopping | 13 | AV approaches stopped pedestrian in the lane at 5 mph. | AV should stop, and as pedestrian walks away staying in the lane, the AV follows. |  | Defer
Following, Pacing, Stopping | 14 | AV approaches stopped pedestrian in the lane at 5 mph. | AV should stop, and as pedestrian walks away staying in the lane, the AV follows. |  | Defer
Following, Pacing, Stopping | 15 | AV approaches stopped pedestrian in the lane at 5 mph. | AV should stop, and as pedestrian walks away staying in the lane, the AV follows. |  | Defer
Intersections | 1 | AV slows approach to intersection and stops. AV turns right with clear intersection. | AV, without hesitation, proceeds turning right at the intersection. |  | Defer
Intersections | 2 | AV slows approach to intersection and stops. AV turns right with clear intersection. | AV, without hesitation, proceeds turning right at the intersection. |  | Defer
Intersections | 3 | AV slows approach to intersection and stops. AV turns right with clear intersection. | AV, without hesitation, proceeds turning right at the intersection. |  | Defer
Intersections | 4 | AV slows approach to intersection and stops. AV turns left with clear intersection. | AV, without hesitation, proceeds turning left at the intersection. |  | Defer
Intersections | 5 | AV slows approach to intersection and stops. AV turns left with clear intersection. | AV, without hesitation, proceeds turning left at the intersection. |  | Defer
Intersections | 6 | AV slows approach to intersection and stops. AV turns left with clear intersection. | AV, without hesitation, proceeds turning left at the intersection. |  | Defer
Intersections | 7 | AV slows approach to intersection not stopping (from direction with no stop sign and turning left across oncoming traffic). AV turns left with clear intersection. | AV, without hesitation, proceeds turning left at the intersection. |  | Defer
Intersections | 8 | AV slows approach to intersection not stopping (from direction with no stop sign and turning left across oncoming traffic). AV turns left with clear intersection. | AV, without hesitation, proceeds turning left at the intersection. |  | Defer
Intersections | 9 | AV slows approach to intersection not stopping (from direction with no stop sign and turning left across oncoming traffic). AV turns left with clear intersection. | AV, without hesitation, proceeds turning left at the intersection. |  | Defer
Intersections | 10 | AV slows approach to intersection and stops. AV desires to turn right but intersection is blocked by TV. | AV, without hesitation, proceeds turning right, once the intersection is clear. |  | Defer
Intersections | 11 | AV slows approach to intersection and stops. AV desires to turn right but intersection is blocked by TV. | AV, without hesitation, proceeds turning right, once the intersection is clear. |  | Defer
Intersections | 12 | AV slows approach to intersection and stops. AV desires to turn right but intersection is blocked by TV. | AV, without hesitation, proceeds turning right, once the intersection is clear. |  | Defer
Intersections | 13 | AV slows approach to intersection and stops. AV desires to turn left but intersecton is blocked by TV. AV continues after TV clears the intersection. | AV, without hesitation, proceeds turning left, once the intersection is clear. |  | Defer
Intersections | 14 | AV slows approach to intersection and stops. AV desires to turn left but intersecton is blocked by TV. AV continues after TV clears the intersection. | AV, without hesitation, proceeds turning left, once the intersection is clear. |  | Defer
Intersections | 15 | AV slows approach to intersection and stops. AV desires to turn left but intersecton is blocked by TV. AV continues after TV clears the intersection. | AV, without hesitation, proceeds turning left, once the intersection is clear. |  | Defer
Intersections | 16 | AV slows approach to intersection and stops. AV desires to turn left accross oncoming traffic but intersection is blocked by TV. | AV, without hesitation, proceeds turning left, once the intersection is clear, and no oncoming traffic is approaching. |  | Defer
Intersections | 17 | AV slows approach to intersection and stops. AV desires to turn left accross oncoming traffic but intersection is blocked by TV. | AV, without hesitation, proceeds turning left, once the intersection is clear, and no oncoming traffic is approaching. |  | Defer
Intersections | 18 | AV slows approach to intersection and stops. AV desires to turn left accross oncoming traffic but intersection is blocked by TV. | AV, without hesitation, proceeds turning left, once the intersection is clear, and no oncoming traffic is approaching. |  | Defer
Intersections | 19 | AV slows approach to intersection and stops. AV desires to yield to oncoming traffic and turn left but intersection is blocked by TV. | AV, without hesitation, proceeds turning left, once the intersection is clear, and no oncoming traffic is approaching. |  | Defer
Intersections | 20 | AV slows approach to intersection and stops. AV desires to yield to oncoming traffic and turn left but intersection is blocked by TV. | AV, without hesitation, proceeds turning left, once the intersection is clear, and no oncoming traffic is approaching. |  | Defer
Intersections | 21 | AV slows approach to intersection and stops. AV desires to yield to oncoming traffic and turn left but intersection is blocked by TV. | AV, without hesitation, proceeds turning left, once the intersection is clear, and no oncoming traffic is approaching. |  | Defer
Intersections | 22 | AV slows approach to intersection and stops. AV yields to TV(s) approaching from the left and desires to turn right at the intersection. | AV, without hesitation, proceeds turning right, once safe to do so, after yielding to approaching traffic. |  | Defer
Intersections | 23 | AV slows approach to intersection and stops. AV yields to TV(s) approaching from the left and desires to turn right at the intersection. | AV, without hesitation, proceeds turning right, once safe to do so, after yielding to approaching traffic. |  | Defer
Intersections | 24 | AV slows approach to intersection and stops. AV yields to TV(s) approaching from the left and desires to turn right at the intersection. | AV, without hesitation, proceeds turning right, once safe to do so, after yielding to approaching traffic. |  | Defer
Intersections | 25 | AV slows approach to intersection and stops. AV proceeds to turn right while TV(s) are approaching from the right in the opposite lane. | AV, without hesitation, should turn right even if traffic is approaching from the right in the opposite lane. |  | Defer
Intersections | 26 | AV slows approach to intersection and stops. AV proceeds to turn right while TV(s) are approaching from the right in the opposite lane. | AV, without hesitation, should turn right even if traffic is approaching from the right in the opposite lane. |  | Defer
Intersections | 27 | AV slows approach to intersection and stops. AV proceeds to turn right while TV(s) are approaching from the right in the opposite lane. | AV, without hesitation, should turn right even if traffic is approaching from the right in the opposite lane. |  | Defer
Intersections | 28 | AV slows approach to intersection and stops. AV yields to TV(s) approaching from the left and turns left at the intersection. | AV, without hesitation, proceeds turning left, once safe to do so, after yielding to approaching traffic. |  | Defer
Intersections | 29 | AV slows approach to intersection and stops. AV yields to TV(s) approaching from the left and turns left at the intersection. | AV, without hesitation, proceeds turning left, once safe to do so, after yielding to approaching traffic. |  | Defer
Intersections | 30 | AV slows approach to intersection and stops. AV yields to TV(s) approaching from the left and turns left at the intersection. | AV, without hesitation, proceeds turning left, once safe to do so, after yielding to approaching traffic. |  | Defer
Intersections | 31 | AV slows approach to intersection and stops. AV yields to TV(s) approaching from the right and turns left at the intersection. | AV, without hesitation, proceeds turning left, once safe to do so, after yielding to approaching traffic. |  | Defer
Intersections | 32 | AV slows approach to intersection and stops. AV yields to TV(s) approaching from the right and turns left at the intersection. | AV, without hesitation, proceeds turning left, once safe to do so, after yielding to approaching traffic. |  | Defer
Intersections | 33 | AV slows approach to intersection and stops. AV yields to TV(s) approaching from the right and turns left at the intersection. | AV, without hesitation, proceeds turning left, once safe to do so, after yielding to approaching traffic. |  | Defer
Intersections | 34 | AV slows approach to intersection and stops because of oncoming traffic. AV yields to oncoming TV and turns left across the intersection. | AV, without hesitation, proceeds turning left, once safe to do so, after yielding to approaching traffic. |  | Defer
Intersections | 35 | AV slows approach to intersection and stops because of oncoming traffic. AV yields to oncoming TV and turns left across the intersection. | AV, without hesitation, proceeds turning left, once safe to do so, after yielding to approaching traffic. |  | Defer
Intersections | 36 | AV slows approach to intersection and stops because of oncoming traffic. AV yields to oncoming TV and turns left across the intersection. | AV, without hesitation, proceeds turning left, once safe to do so, after yielding to approaching traffic. |  | Defer
Intersections | 37 | AV slows approach to intersection and stops. AV begins left turn and yields to pedestrian target in the mapped lane | AV, without hesitation, proceeds turning left, once the pedestrian clears the intersection. |  | Defer
Intersections | 38 | AV slows approach to intersection and stops. AV begins left turn and yields to pedestrian target in the mapped lane | AV, without hesitation, proceeds turning left, once the pedestrian clears the intersection. |  | Defer
Intersections | 39 | AV slows approach to intersection and stops. AV begins left turn and yields to pedestrian target in the mapped lane | AV, without hesitation, proceeds turning left, once the pedestrian clears the intersection. |  | Defer
Intersections | 40 | AV slows approach to intersection and stops. AV begins right turn and yields to pedestrian target in the mapped lane | AV, without hesitation, proceeds turning right, once the pedestrian clears the intersection. |  | Defer
Intersections | 41 | AV slows approach to intersection and stops. AV begins right turn and yields to pedestrian target in the mapped lane | AV, without hesitation, proceeds turning right, once the pedestrian clears the intersection. |  | Defer
Intersections | 42 | AV slows approach to intersection and stops. AV begins right turn and yields to pedestrian target in the mapped lane | AV, without hesitation, proceeds turning right, once the pedestrian clears the intersection. |  | Defer
use case-remote start | 1 | With the vehicle off, turn vehicle on using remote start. | vehicle turns on using remote start, with no errors | Remote start successful. Using Toughbook database, I was able to start the bus. Upon startup it takes 60 seconds before the Bus is fully operable and on, after the intial start up process, and wait to start notification on the dash. See video. No log link available for this testing. | Pass | 2025-06-12 |  | MG | [6 empty] | 5 MPH | partly cloudy 90+ degrees
use case-remote start | 2 | With the vehicle off, turn vehicle on using remote start. | vehicle turns on using remote start, with no errors | Remote start successful. Using Toughbook database, I was able to start the bus. Upon startup it takes 60 seconds before the Bus is fully operable and on, after the intial start up process, and wait to start notification on the dash. See video. No log link available for this testing. | Pass | 2025-06-12 |  | MG | [6 empty] | 5 MPH | partly cloudy 90+ degrees
use case-remote start | 3 | With the vehicle off, turn vehicle on using remote start. | vehicle turns on using remote start, with no errors | Remote start successful. Using Toughbook database, I was able to start the bus. Upon startup it takes 60 seconds before the Bus is fully operable and on, after the intial start up process, and wait to start notification on the dash. See video. No log link available for this testing. | Pass | 2025-06-12 |  | MG | [6 empty] | 5 MPH | partly cloudy 90+ degrees
use case-remote start | 4 | With the vehicle off, and aligned with the route turn the vehicle on and transition to auto mode | vehicle turns on using remote start, with no errors |  | Defer
use case-remote start | 5 | With the vehicle off, and aligned with the route turn the vehicle on and transition to auto mode | vehicle turns on using remote start, with no errors |  | Defer
use case-remote start | 6 | With the vehicle off, and aligned with the route turn the vehicle on and transition to auto mode | vehicle turns on using remote start, with no errors |  | Defer
use case-remote start | 7 | With the vehicle off, and not aligned with the route turn the vehicle on and attempt to transition to auto mode | vehicle turns on using remote start, with no errors |  | Defer
use case-remote start | 8 | With the vehicle off, and not aligned with the route turn the vehicle on and attempt to transition to auto mode | vehicle turns on using remote start, but does not engage in auto mode. |  | Defer
use case-remote start | 9 | With the vehicle off, and not aligned with the route turn the vehicle on and attempt to transition to auto mode | vehicle turns on using remote start, but does not engage in auto mode. |  | Defer
use case-remote start | 10 | With the vehicle off, and aligned with the route turn the vehicle on and transition to auto mode. Give a mission for the vehicle to begin driving | vehicle turns on using remote start, but does not engage in auto mode. |  | Defer
use case-remote start | 11 | With the vehicle off, and aligned with the route turn the vehicle on and transition to auto mode. Give a mission for the vehicle to begin driving | vehicle turns on using remote start, with no errors, engages auto mode, and begins driving |  | Defer
use case-remote start | 12 | With the vehicle off, and aligned with the route turn the vehicle on and transition to auto mode. Give a mission for the vehicle to begin driving | vehicle turns on using remote start, with no errors, engages auto mode, and begins driving |  | Defer
use case-remote start | 13 | With the vehicle off, and not aligned with the route turn the vehicle on and attempt to transition to auto mode. if successful, give a mission to begin driving | vehicle turns on using remote start, with no errors, engages auto mode, and begins driving |  | Defer
use case-remote start | 14 | With the vehicle off, and not aligned with the route turn the vehicle on and attempt to transition to auto mode. if successful, give a mission to begin driving | vehicle turns on using remote start, but does not engage in auto mode. |  | Defer
use case-remote start | 15 | With the vehicle off, and not aligned with the route turn the vehicle on and attempt to transition to auto mode. if successful, give a mission to begin driving | vehicle turns on using remote start, but does not engage in auto mode. |  | Defer
use case-remote start | 16 | With the vehicle on, in auto mode, and driving, turn the vehicle off using remote stop | vehicle stops, and turns off using remote stop |  | Defer
use case-remote start | 17 | With the vehicle on, in auto mode, and driving, turn the vehicle off using remote stop | vehicle stops, and turns off using remote stop |  | Defer
use case-remote start | 18 | With the vehicle on, in auto mode, and driving, turn the vehicle off using remote stop | vehicle stops, and turns off using remote stop |  | Defer
use case-remote start | 19 | With the vehicle on, in auto mode, and stopped, turn the vehicle off using remote stop | vehicle turns off using remote stop. | Remote stop successful. Using Toughbook database, I was able to turn off the bus. See video. No log link available for this testing. | Pass | 2025-06-12 |  | MG | [6 empty] | 5 MPH | partly cloudy 90+ degrees
use case-remote start | 20 | With the vehicle on, in auto mode, and stopped, turn the vehicle off using remote stop | vehicle turns off using remote stop. | Remote stop successful. Using Toughbook database, I was able to turn off the bus. See video. No log link available for this testing. | Pass | 2025-06-12 |  | MG | [6 empty] | 5 MPH | partly cloudy 90+ degrees
use case-remote start | 21 | With the vehicle on, in auto mode, and stopped, turn the vehicle off using remote stop | vehicle turns off using remote stop. | Remote stop successful. Using Toughbook database, I was able to turn off the bus. See video. No log link available for this testing. | Pass | 2025-06-12 |  | MG | [6 empty] | 5 MPH | partly cloudy 90+ degrees
use case-bus wash | 1 | AV running at 5 mph yard speed, without GPS the AV can stay centered between dry lane lines relying on the Lidar technology. (outside bus wash) | The bus stays centered between the two lane lines |  | Defer
use case-bus wash | 2 | AV running at 5 mph yard speed, without GPS the AV can stay centered between dry lane lines relying on the Lidar technology. (outside bus wash) | The bus stays centered between the two lane lines |  | Defer
use case-bus wash | 3 | AV running at 5 mph yard speed, without GPS the AV can stay centered between dry lane lines relying on the Lidar technology. (outside bus wash) | The bus stays centered between the two lane lines |  | Defer
use case-bus wash | 4 | AV running at 5 mph yard speed, without GPS the AV can stay centered between wet lane lines relying on the Lidar technology. (outside bus wash) | The bus stays centered between the two lane lines |  | Defer
use case-bus wash | 5 | AV running at 5 mph yard speed, without GPS the AV can stay centered between wet lane lines relying on the Lidar technology. (outside bus wash) | The bus stays centered between the two lane lines |  | Defer
use case-bus wash | 6 | AV running at 5 mph yard speed, without GPS the AV can stay centered between wet lane lines relying on the Lidar technology. (outside bus wash) | The bus stays centered between the two lane lines |  | Defer
use case-bus wash | 7 | AV running at 5 mph yard speed, without GPS the AV can stay centered between dry lane lines relying on the Lidar technology. (inside bus wash) | The bus stays centered between the two lane lines |  | Defer
use case-bus wash | 8 | AV running at 5 mph yard speed, without GPS the AV can stay centered between dry lane lines relying on the Lidar technology. (inside bus wash) | The bus stays centered between the two lane lines |  | Defer
use case-bus wash | 9 | AV running at 5 mph yard speed, without GPS the AV can stay centered between dry lane lines relying on the Lidar technology. (inside bus wash) | The bus stays centered between the two lane lines |  | Defer
use case-bus wash | 10 | AV running at 5 mph yard speed, without GPS the AV can stay centered between wet lane lines relying on the Lidar technology. (inside bus wash) | The bus stays centered between the two lane lines |  | Defer
use case-bus wash | 11 | AV running at 5 mph yard speed, without GPS the AV can stay centered between wet lane lines relying on the Lidar technology. (inside bus wash) | The bus stays centered between the two lane lines |  | Defer
use case-bus wash | 12 | AV running at 5 mph yard speed, without GPS the AV can stay centered between wet lane lines relying on the Lidar technology. (inside bus wash) | The bus stays centered between the two lane lines |  | Defer
use case-precision parking | 1 | AV precisely parks in close proximity of the same spot, simulating parking under the Pantograph charger. | Parking accuracy is plus or minus 12" in the lateral and longitudinal direction. | Within 2" off laterally | Pass | 2025-04-06 | 11-58-09 | NP | [6 empty] | 5 MPH | overcast
use case-precision parking | 2 | AV precisely parks in close proximity of the same spot, simulating parking under the Pantograph charger. | Parking accuracy is plus or minus 12" in the lateral and longitudinal direction. | 4" laterally 10" longitude | Pass | 2025-04-06 | 11-59-45 | NP | [6 empty] | 5 MPH | overcast
use case-precision parking | 3 | AV precisely parks in close proximity of the same spot, simulating parking under the Pantograph charger. | Parking accuracy is plus or minus 12" in the lateral and longitudinal direction. | 4" lateral 2" longitude | Pass | 2025-04-06 | 12-01-28 | NP | [6 empty] | 5 MPH | overcast
use case-precision parking | 4 | AV precisely parks in the same spot, with another bus parked in the left adjacent parking space. | Parking accuracy is plus or minus 12" in the lateral and longitudinal direction. |  | Defer
use case-precision parking | 5 | AV precisely parks in the same spot, with another bus parked in the left adjacent parking space. | Parking accuracy is plus or minus 12" in the lateral and longitudinal direction. |  | Defer
use case-precision parking | 6 | AV precisely parks in the same spot, with another bus parked in the left adjacent parking space. | Parking accuracy is plus or minus 12" in the lateral and longitudinal direction. |  | Defer
use case-precision parking | 7 | AV precisely parks in the same spot, with another bus parked in the right adjacent parking space. | Parking accuracy is plus or minus 12" in the lateral and longitudinal direction. |  | Defer
use case-precision parking | 8 | AV precisely parks in the same spot, with another bus parked in the right adjacent parking space. | Parking accuracy is plus or minus 12" in the lateral and longitudinal direction. |  | Defer
use case-precision parking | 9 | AV precisely parks in the same spot, with another bus parked in the right adjacent parking space. | Parking accuracy is plus or minus 12" in the lateral and longitudinal direction. |  | Defer
use case-precision parking | 10 | AV precisely parks in the same spot, between two other buses, that are parked in the right and left adjacent parking spaces. | Parking accuracy is plus or minus 12" in the lateral and longitudinal direction. |  | Defer
use case-precision parking | 11 | AV precisely parks in the same spot, between two other buses, that are parked in the right and left adjacent parking spaces. | Parking accuracy is plus or minus 12" in the lateral and longitudinal direction. |  | Defer
use case-precision parking | 12 | AV precisely parks in the same spot, between two other buses, that are parked in the right and left adjacent parking spaces. | Parking accuracy is plus or minus 12" in the lateral and longitudinal direction. |  | Defer
use case-precision parking | 13 | AV running at 5 mph yard speed, parks itself centered at the end of the bus lane. | Parking accuracy is plus or minus 12" in the lateral and longitudinal direction. |  | Defer
use case-precision parking | 14 | AV running at 5 mph yard speed, parks itself centered at the end of the bus lane. | Parking accuracy is plus or minus 12" in the lateral and longitudinal direction. |  | Defer
use case-precision parking | 15 | AV running at 5 mph yard speed, parks itself centered at the end of the bus lane. | Parking accuracy is plus or minus 12" in the lateral and longitudinal direction. |  | Defer
use case-charging | 1 | Starting from direct alignment with the charger, the bus precision parks at the charger, and the charger is manually deployed to the bus. | The bus parks under the charger, the charger is manually deployed, aligns properly, and the bus begins charging. | Bus successfully completed mission with target range both latitude and longitude. Within 1"-2". Charger inoperable per Heliox issue | Pass | 2025-04-06 | 12-09-47 | NP | [6 empty] | 5 MPH | overcast
use case-charging | 2 | Starting from direct alignment with the charger, the bus precision parks at the charger, and the charger is manually deployed to the bus. | The bus parks under the charger, the charger is manually deployed, aligns properly, and the bus begins charging. | Bus successfully completed mission with target range both latitude and longitude. Within 1"-2". Charger inoperable per Heliox issue | Pass | 2025-04-06 | 12-12-01 | NP | [6 empty] | 5 MPH | overcast
use case-charging | 3 | Starting from direct alignment with the charger, the bus precision parks at the charger, and the charger is manually deployed to the bus. | The bus parks under the charger, the charger is manually deployed, aligns properly, and the bus begins charging. | Bus successfully completed mission with target range both latitude and longitude. Within 1"-2". Charger inoperable per Heliox issue | Pass | 2025-04-06 | 12-13-03 | NP | [6 empty] | 5 MPH | overcast
use case-charging | 4 | Starting from the lane of travel(offset from the charger), the bus precision parks at the charger, the charger is manually deployed to the bus. | The bus parks under the charger, the charger is manually deployed, aligns properly, and the bus begins charging. | Bus successfully completed mission with target range both latitude and longitude. Within 1"-2". Charger inoperable per Heliox issue | Pass | 2025-04-06 | 12-14-19 | NP | [6 empty] | 5 MPH | overcast
use case-charging | 5 | Starting from the lane of travel(offset from the charger), the bus precision parks at the charger, the charger is manually deployed to the bus. | The bus parks under the charger, the charger is manually deployed, aligns properly, and the bus begins charging. | Bus successfully completed mission with target range both latitude and longitude. Within 1"-2". Charger inoperable per Heliox issue | Pass | 2025-04-06 | 12-15-57 | NP | [6 empty] | 5 MPH | overcast
use case-charging | 6 | Starting from the lane of travel(offset from the charger), the bus precision parks at the charger, the charger is manually deployed to the bus. | The bus parks under the charger, the charger is manually deployed, aligns properly, and the bus begins charging. | 18" off longitude | Fail | 2025-04-06 | 12-17-41 | NP | Bus successfully completed mission with target range both latitude and longitude. Charger not working. Within 1-2" | Pass | 12-19-44 | Bus successfully completed mission with target range both latitude and longitude. Charger not working. Exact marking completed. Retest 3 marked as Not executed for summary table purposes | Not Executed | 1941-12-21 | 5 MPH | overcast
Robustness | 1 | Continuous Nominal Operation in ADS mode without an intervention for at least 30 minutes | The AV should run the mission without driver intervention or being switched from auto to manual. |  | Defer
Robustness | 2 | Continuous Nominal Operation in ADS mode without an intervention for at least 30 minutes | The AV should run the mission without driver intervention or being switched from auto to manual. |  | Defer
Robustness | 3 | Continuous Nominal Operation in ADS mode without an intervention for at least 30 minutes | The AV should run the mission without driver intervention or being switched from auto to manual. |  | Defer
Robustness | 4 | Continuous Nominal Operation in ADS mode without an intervention for at least 30 minutes | The AV should run the mission without driver intervention or being switched from auto to manual. |  | Defer
Robustness | 5 | Continuous Nominal Operation in ADS mode without an intervention for at least 30 minutes | The AV should run the mission without driver intervention or being switched from auto to manual. |  | Defer
Robustness | 6 | Continuous Nominal Operation in ADS mode without an intervention for at least 30 minutes | The AV should run the mission without driver intervention or being switched from auto to manual. |  | Defer
Robustness | 7 | Continuous Nominal Operation in ADS mode without an intervention for at least 30 minutes | The AV should run the mission without driver intervention or being switched from auto to manual. |  | Defer
Robustness | 8 | Continuous Nominal Operation in ADS mode without an intervention for at least 30 minutes | The AV should run the mission without driver intervention or being switched from auto to manual. |  | Defer
Robustness | 9 | Continuous Nominal Operation in ADS mode without an intervention for at least 30 minutes | The AV should run the mission without driver intervention or being switched from auto to manual. |  | Defer
Robustness | 10 | Continuous Nominal Operation in ADS mode without an intervention for at least 30 minutes | The AV should run the mission without driver intervention or being switched from auto to manual. |  | Defer
Robustness | 11 | Continuous Nominal Operation in ADS mode without an intervention for at least 30 minutes | The AV should run the mission without driver intervention or being switched from auto to manual. |  | Defer
Robustness | 12 | Continuous Nominal Operation in ADS mode without an intervention for at least 30 minutes | The AV should run the mission without driver intervention or being switched from auto to manual. |  | Defer
Robustness | 13 | Continuous Nominal Operation in ADS mode without an intervention for at least 30 minutes | The AV should run the mission without driver intervention or being switched from auto to manual. |  | Defer
Robustness | 14 | Continuous Nominal Operation in ADS mode without an intervention for at least 30 minutes | The AV should run the mission without driver intervention or being switched from auto to manual. |  | Defer
Robustness | 15 | Continuous Nominal Operation in ADS mode without an intervention for at least 30 minutes | The AV should run the mission without driver intervention or being switched from auto to manual. |  | Defer
Robustness | 16 | Continuous Nominal Operation in ADS mode without an intervention for at least 30 minutes | The AV should run the mission without driver intervention or being switched from auto to manual. |  | Defer