## Slide 2: MHA BVLOS Hotwash
10/4/2024

## Slide 3: Agenda
Topics Covered in Feedback Planning & Coordination
Flight Operations
Safety & Risk Management
Flight Crew, Radar/Surveillance Observers & Visual Observers
Post-Flight Debriefing/After Operation Observation
Community Engagement & Interaction
Overall Experience & Recommendations
Other
  Logistics/Schedule

## Slide 4: Participant Information

## Slide 5: Participant Information
Other:
  Project Staff
  PI for Grant
  Technical platform integrator

## Slide 6: Planning & Coordination

## Slide 7: Planning & Coordination
Other:
  Project Staff
  PI for Grant
  Technical platform integrator

## Slide 8: Planning & Coordination
Overview of timeline of events, expected show times, and operational duration.
Great weather updates.
Defined roles and responsibilities.
Site survey for placement of the three radars was well thought out and strategically placed. Because of this the radar sites had overlapping coverage, which allowed the entire flight to be monitored without any issues. Furthermore, placement of the radar 10 miles east of Mandaree allowed detection of crewed aircraft that were not a part of the operation. This further promoted the aircrafts safe operation and BVLOS traffic avoidance and adherence to regulations.
A BVLOS waiver was approved by the FAA. A full conops and SRM plan was developed and communicated. Waiver was provided to all operators to review and become familiar with. Pre-operations - operations team was available for questions as well as a central person was available for interaction. First aid and related gear was provided. Regular meetings prior to event to outline responsibilities and expectations for each participant.
Consistency.
Meeting and communicating with TAT GIS Dept, EOC, Police, and then TBC to get Routs approved. UND bringing all their expertise to help with all aspects of preparation from UAV experts to FAA experts, Radar, and more!
Amanda seemed on top of things.
The daily prep call prior to each testing flight

## Slide 9: Planning & Coordination
The high level of engagement by the Tribal Nation
Figuring out where everyone will be placed
There was communication but it wasnt effective to all layers and the amount personnel in the field.
adequate time was allocated to assemble aircraft, batteries, perform training and generally prepare for the upcoming flight operations.
The Flight Demo and Planning seemed to work well, and were well thought out. Contingency planning and safety were practiced well during the demo due to thorough planning an coordination
The planning phase would of been marked very or extremely effective up until the last 10 days when VOs were brought into the equation. Without disputing whether they were needed or not, this piece was added too late into the process and was not integrated smoothly into the flight and there was a lot of unknowns and unanswered questions going into the day of the flight to include, where they were at, how many, who was there, what training were they given and proof of training, radio call discipline and what type of calls should be made, etc.
Valkyrie did a great job putting together the run of show and running daily safety briefings.
There were telcons etc in advance of event... The flight path and overall goals were well communicated prior to the event...
The safety meetings prior to the day starting in outlining what the day is going to look like as well as all of the checks with the VO's down the path of the flight

## Slide 10: Planning & Coordination

## Slide 11: Planning & Coordination

## Slide 12: Flight Operations

## Slide 13: Flight Operations

## Slide 14: Flight Operations

## Slide 15: Flight Operations
Tuesday: Delay due to weather (normalized deviation). UAS landed 100 yards from LZ (abnormal deviation). Return flight route cancelled (abnormal deviation, but safe decision). Wednesday: Delayed start due to lack of mx sign off. Return flight route cancelled due to wind and battery concerns. (abnormal deviation, but safe decision).
Coordination regarding flight over busy highway
First flight from New Town to Twin Buttes, Tuesday September 17th.
LZ changed, VO locations, and delays
We intended to conduct round trip flights but due to equipment and weather, we were only able to conduct 2 oneway flights from New Town to Twin Buttes
The flight crew operated exactly as briefed the day of both fights. The only change was the take-off location that was identified 48 hours prior due to construction that was not completed on the timeline the flight operations team was provided by MHA nation. The VOs positions were changed and provided to the flight crew 12 hours prior to the flight. Everything else was as scripted on the flight. However, due to weather, return flights were not flown.
The aircraft landed 100 yards from the specified LZ and no concrete reason was given why.
Not directly observed however the UA landed 100 meters off target on first attempt. The RPIC and other flight crew did a great job researching and fixing any issues that may have been contributory. 2nd Flight landed on target! Nice Job

## Slide 16: Flight Operations
The demonstration of UA technology capable of long distance/long endurance flight with proper payload capacity. Demonstration of ground based surveillance - not only the technology, but the non-cooperative aircraft observed during the flight (by both the tech and VO) demonstrated the need to ground based surveillance solutions in order to normalize routine BVLOS operations.
Demonstrating to the community the capabilities of long-range UAS that can be integrated within their communities and health systems to move goods between their population hubs.
Successful departure from New Town and landing in Twin Buttes.
Safe flight from point A- point B.
No injuries or accident; flight conducted in less than ideal weather conditions; joint operation conducted with multiple organizations. Possible outreach to the community. Community identified flight demonstration as a positive experience.
The flight course.
Performance of vehicles, abilities of Radar, coverage by multiple media modes......
Completing it. Publicity.
Managed to execute two successful flights between New Town and Twin Buttes. The flight path and the crewed air traffic were available for display in the AirHub Portal application.

## Slide 17: Flight Operations
That we did it!
Landing of the aircraft on target
2 one-way flights were successfully achieved
WE were able to conduct 2 34 mile flights from New Town to Twin Buttes and generate excitement from the MHA Nation.
Met and exceeded the stated goals of the Phase 1 grant.
Proof-of-concept that flying medical supplies from one clinic to the other saved over a 3-hour vehicular round trip to pick-up those medical supplies and return, while also providing a safer delivery method of not requiring a human to be on historically dangerous roads. A person would have taken nearly 4 hours to drive to one clinic, go in and get the medication, and drive back. The delivery of medication by drone, on average, takes approximately 30 minutes.
Successful BVLOS for medical delivery use case.. Successful integration of the aircraft telemetry and mobile radar partner with the chosen technical platform from the Tribe.
Flying 30+ miles BVLOS!
Successful demonstration of flights for MHA
The flight itself. For myself I have not been apart of many BVLOS operations so being apart of the operation in sending an aircraft a great distance and landing on point
Successful delivery from New Town to Twin Buttes

## Slide 18: Flight Operations

## Slide 19: Flight Operations

## Slide 20: Flight Operations

## Slide 21: Flight Operations
Unexpected helicopter transition over the top of the Mandaree radar site at approximately 10 AM Tuesday. The Madaree site was still in thick fog, visibility was less than an 1/8th of a mile, an a helicopter transitioned at low altitude directly over the top of the radar site. Suspected to be a Huey helicopter, most likely originating either from the military base, although we were unable to visual confirm through the fog.
Three instances of Non-cooperative aircraft.
Noncooperative (military) traffic identified by Radar; Unforecasted weather conditions - heavy fog; Aircraft technology failures (landing sensors / batteries)
Heard something about a helicopter.
The battery failure during public day.
2 Helicopters were flying very low and through the flight path, one on each of the days we flew. VOs detected them and was safely avoided.
The bird landed 100m away from the LZ, flight crew didnt bring enough batteries.
The UND radar set was not able to record full data as the storage system was full.

## Slide 22: Flight Operations
Personally, was surprised by the limitations put on the operation by the lack of batteries available, as well as the one spare aircraft immediately being grounded upon arrival. Seems like the maintenance provided in the field was extremely limited and therefore before even flying BVLOS operations we were down to one-way operations with no spares if anything else went wrong.
The LZ deviation I alluded to earlier
Off target landing
Battery issues
Non-participating aircraft observations. Amendment to the "hard-stop" allowed operation to be completed on Tuesday. Aircraft inop equipment and mx. Weather (both good and bad).
Higher winds than expected limited the ability to begin a second flight due to battery constraints

## Slide 23: Safety & Risk Management

## Slide 24: Safety & Risk Management

## Slide 25: Safety & Risk Management

## Slide 26: Safety & Risk Management

## Slide 27: Safety & Risk Management
The over confidence of the RPIC that VOs were not needed... Even after pushing the issue, getting FAA clarification.... all concerns were still discounted and an adversarial environment developed.
I selected no, but to type in here it goes to Yes. My answer is no but wanted to add that there were extra levels of safety that were added into this flight that I believe caused more confusion and didn't actually increase safety but hurt it. An example is when one of the VOs said a helicopter was at 500ft (concerning) and then Erin came on to confirm she saw the targe on the screen and it was reporting 4000 ft. There were two times traffic was reported and the wrong direction of flight for that traffic was given as we could see them on the screen, and they were headed in the opposite direction the VOs reported. When there was uncooperative traffic in the area (believe there was reported 3 different times), the information was unclear and went from "in the flight path" to "not a factor" to "flying from the flight path away from flight path" all in the same 60 seconds by two different VOs. In over 15 years of flying UASs, I have personally never had an incident where the VO provided actual safety awareness that increased safety operation. Usually they have trouble obtaining the aircraft and when they do see traffic, often the information they provide is inaccurate, untimely and/or confusing. I wish the FAA would stop using this as a band aid method for solving see and avoid.

## Slide 28: Safety & Risk Management
Duty day and rest periods - suggest defining those in advance (and other crew member safety protocols as necessary).
Sense of flight was going to happen no matter what.
There wasn't enough active surveillance of the airspace other than ADS-B
The weather was a factor.
Debrief to include what did the waiver have has mitigations? Were those mitigations/controls carried out? Were mitigations/ controls effective? What risks were not identified (i.e. non-cooperatiave traffic?). Where there any unintended consequences of mitigations?
We have successfully used radar as an accepted BVLOS safety case many times in the past. There doesn't seem to be any reason this could not have happened here with a bit more time to plan.

## Slide 29: Flight Crew, Radar/Surveillance Observers, & Visual Observers

## Slide 30: Flight Crew, Radar/Surveillance Observers, & Visual Observers

## Slide 31: Flight Crew, Radar/Surveillance Observers, & Visual Observers

## Slide 32: Flight Crew, Radar/Surveillance Observers, & Visual Observers
Helicopter was observed on Day 2 East of my position
Tuesday, prior to flight around 9:30 AM, Robinson helo reported near LZ, no factor, would have impacted operational area, detected by VO, detected by Detect Radar but could not locate on Airspace Link display. Not detected by Vantis or Simulyze.
Tuesday, prior to flight around 9:55 AM, Huey helo reported near Observer 7 prior to flight operation, no factor, would have impacted operational area, detected by VO, not detected by tech solutions.
Tuesday, prior to flight around 10:50 AM, low altitude aircraft Aviat Husky <800’ AGL, BIS to New Town, would have impacted operational area, detected by VO, detected by all 3 tech solutions, but then was dropped by Airspace Link display. Aircraft did have ADSB out.
Tuesday, prior to flight around 10:55 AM, low altitude aircraft red/white Ag Tractor <300’ AGL, observed near New Town, travelling south east bound, dipped into Valley just south of the takeoff location. Detected by VO, not detected by any tech solution. Aircraft did not have ADSB out.
Wednesday, beginning prior to flight operations then during flight ~9:15-9:45, pipeline patrol aircraft detected running east of New Town, parallel to route of flight, travelling south to north, then exiting area to the east. Aircraft altitude varied from 800’ AGL to 100’ AGL. Not detected by VO, detected by all 3 tech solutions initially, but then was lost by Airspace Link display. Aircraft did have ADSB.
Wednesday, during flight around 9:50 AM, low altitude Huey helo reported near observer 6, 7, 8, no factor once visual was obtained. Aircraft passed directly over observer 6. UAS was south of observer 3 at the time, enroute. Helo was initially detected east of the flight operation area (by Simulyze display) at 4000’ MSL and descending. Aircraft entered flight operation area less than 3000’ MSL still descending, and VO approximated altitude less than 500’ AGL. Detected by VO, not detected by Vantis or AirspaceLink. Detected by Simulyze (VAS feed). Aircraft did not have ADSB.

## Slide 33: Flight Crew, Radar/Surveillance Observers, & Visual Observers
There was a non-participating aircraft without ADS-B that was observed by radar electronically.
Discussed previously: At the Madaree Radar Site we had a Huey helicopter transition directly over the top of the site at low altitude in the fog at approximately 10AM
9/17/24 10:50AM My location: 47.934498°, -102.450114° Ag Tractor: <1000 Feet, Aircraft just slightly west of my location.
Saw unknown objects on radar as drone was near TB around 10?
Yes (VO7). I saw a helicopter on the first day as well as a helicopter on the second flight day. Both were flying low and travelled through the flight path.
a helicoptor was identified in 9/18 near the flight path and was ultimately deemed no threat.
I have a summary file from the 2 DeTect radars I can provide. Still compiling data from all 3.
On the second flight I saw non-participating aircraft over the river, near the bridge. I honestly can't account for exactly when as I was not a VO, but it was soon after take-off on the second day.
Tuesday around 10:50AM an aircraft was seen flying North along the West side of Lake Sakakawea

## Slide 34: Flight Crew, Radar/Surveillance Observers, & Visual Observers
SUMMARY:
Tuesday
  Helicopter (Huey) – no ADSB
  Helicopter (Robinson) – unknown
  Airplane (Husky) – with ADSB
  Airplane (Ag Tractor) – no ADSB
Wednesday
  Helicopter (Huey) – no ADSB
  Airplane (Cessna) – ADSB
  Airplane (over river) – unknown

## Slide 35: Post-Flight Debriefing/After Operation Observation

## Slide 36: Post-Flight Debriefing/After Operation Observation

## Slide 37: Post-Flight Debriefing/After Operation Observation
Daily post-flight briefings did not occur.
Operational post-flight did not include all participants (mainly the flight crew). Therefore key insights and lessons learned felt very incomplete.
Teams need more time on-site prior to operation. both operating team and support team.
Lack of all sites knowing the current location of the aircraft via communication channels. All radar sites did not has constant communication with the flight crew, observers, and New Town/Twin Butte sites.
Need for coordination with Minot AFB; amount of traffic on roads; importance of landing location, importance of radar locations
It was amazing how drones can be used.
need for redundant aircraft, batteries, and radar
Future flights require better prior maintenance

## Slide 38: Post-Flight Debriefing/After Operation Observation
Could use better backup systems
More advanced planning for system integration would have been helpful
There really wasnt a de-brief.
You can never prepare for the unexpected enough. Thinking through all possible scenarios is important to ensure proper tools, resources, etc. are available.
Due to the size of this operation and a lot of different organizations involved, it was obvious there was a lot of hidden agendas throughout this operation, that was again shown in the "hot wash", as the focus shifted quickly from lessons learned to how to go about getting Stage 2 funding. My biggest frustration is too many of the people on this project were concerned with stage 2 possibilities and funding and not the immediate task on hand.
Changes needed to next days operations.
I would have a physical meeting of VOs and RPIC/Flight Crew. The use of standard phraseology would also increase safety

## Slide 39: Post-Flight Debriefing/After Operation Observation
The lack of the flight crew and others present was crucial.
But other items not addressed, duty day/rest period.
You can't have an effective post-flight debrief without the pilot present.
I would have like to known why the LZ deviation occurred

## Slide 40: Community Engagement and Interaction

## Slide 41: Community Engagement and Interaction

## Slide 42: Community Engagement and Interaction

## Slide 43: Community Engagement and Interaction

## Slide 44: Community Engagement and Interaction
Seeing some of the MHA cultural locations
Seeing their genuine interest in how this demonstration could be a sustained capability - community buyin/acceptance.
Informed questions regarding airspace management, asking about maintaining the safety and security of the airspace for all flight operations.
Seeing their interest in how they can utilize UAS in their own day to day work.
Talked with the local rancher who owns a large area of ranch land in the Mandaree area. He expressed great interest in the UAS flight, its purpose, and how it helped the area. I relayed the information to him and he was very pleased to have this testing going on in the area!
Answer questions and seeing community excitement.
When people realized that the drone landed in Twin buttes in under 30 minutes. The crowed cheered.
mutual joy and positive reactions to successful flight
Engaging with the community, seeing their excitement and enthusiasm for the potential UAS flights present for the community

## Slide 45: Community Engagement and Interaction
Their enthusiasm for the process and flights
The culture
Seeing the 2 community members make it out and witness a flight op. They were very excited with where this could go.
The community asked insightful questions and seemed eager to learn how UAS could help their communities.
Having news outlets present to share information so they can spread it to a larger audience.
The in-person meetings with tribal departments.
Discussion and excitement with those who did attend.
I enjoyed having dinner in the lodge with the locals
No interaction or engagement
Conducting the operation

## Slide 46: Community Engagement and Interaction
Prior to flight - a quick :30 pitch on the technology and aircraft, providing overview of the flight operation. (Although community arrived late so would have to repeat that anyways).
A dedicated role of a person at the trailer/display area that is listening in on the crew comm channel, or is able to give status updates during the route of flight. Like how far the UAS is now, has it landed yet, when will it get there, how much battery has it burned, etc.
Provide more information on the upcoming potential rule changes and explain to the community how they can be involved in the rulemaking process.
More community outreach is always beneficial.
More organized briefing, possible talking points for those who interacted with community to help create a uniform response
More flyers and media.
Not much. Had live coverage and multiple media reports after successful flight
More advertising, and more engaging activities for the public.
I wish more people would have attended the dinner on Sept 16 from the Tribal Nation.
I was a VO located 15 miles South of TO LZ.... I had no interaction as there was no one near me....
Make it more known to the community and let it known in the community

## Slide 47: Community Engagement and Interaction
Advertise the event more
Overall, there seemed to be a lack of community that showed up for how much hype there was around this. The schedules should have been checked to verify this was the only event going on that week.
The dinner was not fully attended. I'm not sure what communication or coordination went into that event. There might be an opportunity here.
I believe the sub-contractors did everything in their power to get community engagement interaction. Unfortunately, it is my opinion that the MHA members involved on this project did not make a sufficient effort forwarding that information in the community. They were provided invitations, agendas, flyers, etc. and only 5-6 MHA members showed up to the dinner and I believe at the launch, minus media, there as 3-4 members and landing 2-3 members of the community that were not directly involved with the grant. With the amount of effort that went into planning a community dinner and planning the take-off and landing events, I feel this is not a good turn-out. I do feel like using Facebook to live stream was the most successful avenue of sharing real-time information. Basically, the need for more MHA Champions located on the reservation getting information to schools, community centers, and distributed through radio and other media needs to be greatly improved.
More effort of the part of the tribe to get the word out.
If we plan to use oil field access roads, a notice to them would have avoided them questioning why we were there.

## Slide 48: Overall Experience & Recommendations

## Slide 49: Overall Experience & Recommendations
Successfully flying a UAS from New Town to Twin Buttes twice
Showing the complexity of enabling a UAS operation - but while simultaneously demonstrating that the collective team has the skills to conduct the complex operations.
The success of the flight and the communities engagement with it I believe were the biggest successes.
Building positive relationship with MHA Nation
N/A
Everything was fantastic. Intergovernmental successes and collaborations. Media coverage
The proof of concept flight was successful and was received with a lot of excitement.
That we did it!
Getting successful flights in
The flight was able to land successfully.
in addition to showing the capability of UAS in medical transportation, the integration of DeTect, Airspace Link and Swoop was a nice touch to show and communicate with community members.

## Slide 50: Overall Experience & Recommendations
We were able to integrate the feeds of three radars into a single source of data to push the track data to a customer which had not been previously done. Although the planning time for the demo was not sufficient, and the radar locations were terrible from a planning standpoint, we were able to demonstrate the proof of concept to use radar as a safety measure for a useable corridor with multiple overlapping coverage areas to minimize difficult observational areas such as the cone of silence over a single radar emplacement.
Two completed flights.
Showing the tribe how we can apply our SME to support their interests and that BVLOS is possible. To find a technical solution that will work for the tribe today and grow with them as their needs grow. To find the best transportation-based use cases to support the tribe in phase 2.
a successful 30+ mile UAS flight with positive support form the community
Successful 2nd flight...
The flight operation

## Slide 51: Overall Experience & Recommendations

## Slide 52: Overall Experience & Recommendations
If possible, have more VOs and possibly zig zag them across the lake/rivers to get more coverage area. Or utilize more EO DAA solutions
Determine singular tech solution that has robustness to deliver adequate airspace surveillance.
Increase crew capabilities for mx/contingencies to minimize impacts of inop equipment for sustained operations.
On the communications side of things, possibly a VHF frequency, or similar, which all sites can be tuned into and communicate on.
N/A
Use same preparation methods
Continue pursuing flights addressing medical transportation use cases. Allow more ample time for system integration. Attempt to keep the overall detection system simple, limit to only the requirements of the BVLOS waiver to reduce complexities and eliminate points of failure.
Be sure and have better access to batteries, be sure and have a clear understanding of the need for VOa, have someone in Minot willing to run equipment as we determine needs, figure out ways to have been engagement from Tribal members in the use case.
Better planning communication

## Slide 53: Overall Experience & Recommendations
Have defined roles and how is actually responsible to make certain decisions.
Early and often community communications of all events
Additional time to plan, and competitive radar solutions.
Smaller group (how the future would realistically look, not a 35-member team) to provide operations that are involved with the flight operation from cradle to grave. An aircraft that had more spare parts or a more capable maintenance presence, so the flight operation isn't going into the first flight down to one battery and no back-ups available.
I think we should have a separate meeting to discuss the scope of phase 2.
More airspace surveillance instrumentation
Understand the FAA will not repeatedly approve this type of operation. I highly doubt they would approve it again quite honestly.
Demonstrating a return flight as well

## Slide 54: Overall Experience & Recommendations
In a safety environment there is no room for Chest thumping and discounting of very knowledgable and industry respected persons opinions (not me). i.e. VO necessity, VO communications, VO responsibilities....
No
Great demonstration overall and proof of concept.
N/A
Thanks to ALL involved! But especially ALL UND Experts! and Jared Eagle, Kathy Eagle, and TBC!
N/A

## Slide 55: Other?

## Slide 56: Ideas for Improvement
What could we do better for future complex operations?
What tasks need to be accomplished in order to make the next project/operation more successful?
What resources or training need to be enhanced or conducted prior to the next deployment?