## Dry Run Agenda - Week of Oct 24 (hidden)
Event | Location | Date | Start Time | Duration | 2THEDGE | TTU / SPC | OPO | MissionGO | BNSF | Aerolane | Blood Bank | HEB/Food Bank | ISD | UMC | Media - Dial In | Comments / Questions
Longrange Clinic | Determine launch / landing locations | 2022-10-25 | 17:00 | 2hr | Catherine
Airport Outreach | Post City Garza County: 1381 US380 Post | 2022-10-26 | 8:00 | 1hr | Catherine | [10 empty] | No Office; will call
| Post-Garza County Municipal Airport: 33.20331, -101.33822 33° 12′ 11.9″ N, 101° 20′ 17.6″ W 33° 12.198′ N, 101° 20.293′ W | 2022-10-26 | 9:00 | 1hr | Catherine | [10 empty] | SAA
| ClearTech Aivation @Lubbock Executive Airpark: 12201 County Rd 2500 Lubbock | 2022-10-25 | 8:00 | 2hr | Catherine | [10 empty] | Call a few days prior - let know how close we'll be operating 806-745-4967
| Larry T. Neal Memorial Airport: 12106 FM 400 Slaton | 2022-10-25 | 10:00 | 2hr | Catherine | [10 empty] | Call prior to flights Ruth - 806-3001457
| Biggin Hill Airport-Ta67: 11302 US-84 Shallowater | 2022-10-25 | 13:00 | 2hr | Catherine
| Lubbck Preston Smith It'l: 5401 N Martin L King Blvd Lubbock | 2022-10-26 | 9:00 | 2hr | Ty, Catherine | [10 empty] | Notification will alert LBB
FAA Call | Innovation Hub - 211 | 2022-10-26 | 11:00 | 1hr | Ty, Catherine | Phil | Kevin | [6 empty] | Jeff(?)
Food Bank | South Plains Food Bank - Zoom | 2022-10-26 | 13:00 | 1 hr | Ty, Catherine | Phil, Carleigh, Lena
Food Delivery | HEB Lubbock Store | 2022-10-26 | 14:00 | 1hr | Ty, Catherine | [6 empty] | Alyssa Owens
ISD Coordination | Shallowater, Frenship | TBD | TBD | 1hr | Ty, Catherine | Phil, Carleigh, Lena | Jessica | [5 empty] | Aron, Keith |  |  | Mayor, Police
Train VOs - Responsibilities | Innovation Hub - Multiple Purpose Room | TBD | TBD | 30 mins | Catherine |  |  | Ryan | [7 empty] | Primary, secondary, tertiary
Train Oberservers / Reporters | Innovation Hub - Multiple Purpose Room | TBD | TBD | 30 mins | Ty, Catherine | Phil | [9 empty] | 2 Team Leads assigned to Ty and Catherine; 2 people per POV have a principle ob/re - doc all logistics and how to scale; Emergency mgt procedures - landing procedures; recovery of cargo; Edu how to build drones into STEM edu; Need to develop a template - Phil & team - 17 slots
Familiarize PICs with Reese | Firehouse | 2022-10-26 | 15:00 | 1hr | Ty, Catherine |  |  | Ryan | [7 empty] | Are all of these within walking distance? NO I am going to upload a map. Lacy E. (Reese)
| Wind Turbine | 2022-10-26 |  |  | Ty, Catherine |  |  | Ryan
| Solar Panel | 2022-10-26 |  |  | Ty, Catherine |  |  | Ryan
| Field Area | 2022-10-26 |  |  | Ty, Catherine |  |  | Ryan
| Wind Tunnel | TBD | TBD |  | Ty, Catherine |  |  | Ryan
Conduct Sprectrum Analysis | Ride near tracks | 2022-10-26 | 16:30 | 1hr | Catherine |  |  | Ryan | [7 empty] | Requested telecom surveys from BNSF
Talk Through Events | Innovation Hub - Clinic - STEM Multipurpose Room | 2022-10-27 | 8:00 | 1hr | Ty, Catherine | Phil, Carleigh, Lena, Dr. H G-S, VOs, Oberservers / Reporters | Jessica | Ryan |  |  |  |  | Aron, Keith | Jeff Hill, Marisol, Aaron | Ashley Hamm? Megan Crout, UMC, HSC, Shallowater, Frenship, Reese, TTU, TTUHSC | Need big map
| Innovation Hub - Organ & Blood Multipurpose Room | 2022-10-27 | 9:30 | 1hr | Ty, Catherine | Phil, Carleigh, Lena, Researchers, Observers / Reporters | Jessica |  |  | Jason | ? |  |  |  | OPOs, Blood Bank | Carleigh has scheduled.
| Innovation Hub - Long Range Clinic 211 | 2022-10-27 | 11:00 | 1hr | Ty, Catherine | Phil, Carleigh, Lena |  | Ryan | [5 empty] | Jeff Hill, Marisol, Aaron | UMC | Who from Littlefield?
| Innovation Hub - Infrastructure 211 | 2022-10-27 | 13:00 | 1hr | Ty, Catherine | Phil, Carleigh, Lena |  | Ryan | [6 empty] | MissionGO
| Innovation Hub - Mobile Clinic & Delivery Multipurpose / 211 | 2022-10-27 | 14:30 | 1hr | Ty, Catherine | Phil, Carleigh, Lena |  |  |  | Jason |  | TBD |  | Jeff Hill, Marisol, Aaron, Thomas, + Denver City | UMC, HEB?
| Innovation Hub - Executive Demo Multipurpose | 2022-10-27 | 16:00 | 1hr | Ty, Catherine | Phil, Carleigh, Lena | Jessica sent list | Ryan |  | Jason |  |  |  | Jeff Hill, Marisol, Aaron | All | Ask Jeff for a team that will be responsible for this work within the next week so we can plan this out; need to coordinate with the food banks, etc.
| Innovation Hub - Higher Education Night Multipurpose / 211 | 2022-10-27 | 17:00 | 30 mins | Catherine | Phil, Carleigh, Lena, Venky, Taysha, SPC Lead | Jessica | Ryan |  | Jason |  |  |  |  | TTUHSC | Carleigh will send out
Post Event Deliverable | [15 empty] | Publish deliverables - oberservations, media, recap; ties into the comms plan; vertiport, utm, community impact, stem

## Notification NOTAM List
Name | Company | Location | Phone | Email | When to Contact | Website | Notes
FAA
File NOTAM | FAA |  | 877-487-6867 |  | 48 hrs prior
Sam Colasanti | FAA |  | (405) 706-4493 | samuel.r.colasanti@faa.gov
Gavin Hill | FAA |  |  | gavin.hill@faa.gov
Bruce | FAA |  |  | Bruce.CTR.Kinsler@faa.gov
Paul Hamilton | FAA |  |  | Paul.CTR.Hamilton@faa.gov
Patrick Haas | FAA |  |  | Patrick.CTR.Haas@faa.gov
Rogan Flowers | FAA |  |  | rogan.flowers@faa.gov
Airports
Mylo Wolding (AA/M) Lonn Hagen (AC) | New Town Municipal Airport (05D) CTAF 122.9 | New Town | (701)898-4918 (AA/M) (701)898-1150 (addt'l Contact) |  | Day before we do flight ops | https://www.airnav.com/airport/05D | 8/26: left msg for Wolding; will call back - Mylo called back. Has some contacts with the oil & gas - will let me know. Mylo flies low and sees them so they should have ADS-B Out
Greg Synnes | Dunn County Weydahl Field Airport (9Y1) | Killdeer | (701) 260-1235 |  | Do not need to contact further | https://www.airnav.com/airport/9Y1 | 8/26: guys that fly pipeline - Dakota Pipeline. No problem for the airport
Jason Hutchinson | Pete's Port Airport (55ND) | Killdeer | 701-764-8888 (O/M) |  |  | https://www.airnav.com/airport/55ND | 9/5: called - unable to leave msg - outside of 3 mile radius waiver requires 9/4: called again 8/26: unable to leave msg; will call back
Shawn Morten (AA/M) Kevin Lee (AA) | Beulah Airport (95D) | Beulah | 701-873-4100 (AA/M) 701-873-2259; 701-873-2311 (AA) |  | Do not need to contact further | https://www.airnav.com/airport/95D | 8/26: no concerns
Wayne Entze Airport Manager & Airport Auth | Mercer County Regional Airport (KHZE) | Hazen | 701-880-0042 (O) 701-748-6501 (M) |  |  | https://www.airnav.com/airport/KHZE | 8/26: no concerns - AG 701-321-0767 Rod Matters; called Rob - no concerns
Lyle Lelm | Washburn Municipal Airport (5C8) | Washburn | 701-390-3926 (AA/M) |  | 2 AG sprayers - Airport will alert them - they have ADSB-Out | https://www.airnav.com/airport/5C8 | 8/26: left msg for Lelm; will call back 8/27: called me back - no concerns
Ross Lorentzen (O/M) | Lorentzen Airport (3NA2) | Washburn | 701-462-3678 (O) 701-460-1536 (M) |  | Not in operations | https://www.airnav.com/airport/3NA2 | 8/26: airport not in operation
Jim Wilcox | Garrison Municipal Airport (D05) | Garrison | 701-301-1055 (AA/M) |  | jimwilcox2@outlook.com 8/26: sent email with schedule May need to update if times change | https://www.airnav.com/airport/D05 | 8/26: left msg for Wilcox; will call back; called back - no concerns - will notify the 1 AG sprayer but should not interfere
Richard Bolkan | Parshall-Hankins Airport (Y74) | Parshall | 701-898-3144 (AA/M) |  | Do not need to contact further | https://www.airnav.com/airport/Y74 | 9/4: no concerns 8/26: unable to leave msg will call back
Luke Taylor | Watford City Airport (S25) | Watford | 701-570-2646 (AA/M) | luke@ltenterprisesnd.com | AG season slowing down - let land owners know and have them advise their AG aviators | https://www.airnav.com/airport/S25 | 8/26: unable to leave msg will call back; Luke called back -
Kelly Braun | Dickson/Theodore Roosevelt Regional Airport (KDIK) | Dickinson | 701-483-1062 (AA/M) |  | Only if operating with 10 nm | https://www.airnav.com/airport/KDIK | 8/26: Airport admin - spoke with Kelly - further than what they are concerned with - no future notification required - 10 mi radius is what they're concerned with
Steven Martens | Stanley Municipal Airport (08D) | Stanley | 701-629-0061 (AA/M) |  | Steven may contact me if there appears to be any concern from the airport mtg | https://www.airnav.com/airport/08D | 8/26: spoke with Steven - will bring up in the airport mtg; no spraying going on in the area this year but will keep my number and pass along in case
Anthony Dudas (M) | Williston Basin International Airport (KXWA) | Williston | 701-577-8100 (O) 701-580-5699 (M) |  | 2 days prior to flight operations for logging | https://www.airnav.com/airport/KXWA | 8/26: spoke with Anthony - may not have to do anything
Kenneth Fredrick | Fredricks Rancy (44ND) | Twin Buttes | (701) 460-0058 |  | No concerns |  | 9/11: Kenneth called back and is not planning on flying 9/11: left msg; will call back
AG Contacts | [5 empty] | https://aero.nd.gov/licensing/aerial-applicators/licensed-applicators/
Josh Dipippo | Spotters Aerial AG LLC | Killdeer | 605-630-1044 | rachel@spottersaa.com | No concerns - runs a spray drone and won't be up there |  | 9/5: Called back - no concerns - flight operations in the area or at that time 9/4: left msg; sent email 8/26: unable to leave msg will call back
SHAWN STEINBERGER | MASTER OF NONE LLC | Williston | 701-580-5664 | shawnpsteinberger@gmail.com | Will not cross paths |  | 8/26: no concerns - will be further south than we'll be flying
Rod Matters |  | Hazen | 701-321-0767 |  | Do not need to contact further |  | 8/26: do not know if will be spraying at the time, does have ADSB-out
RICHARD MARBURGER | AERO SPRAYING SERVICE INC | Williston | 701-570-2342 | rckmrbrgr@gmail.com |  |  | 8/26: done spraying for the year
FLETCHER DEKALB | DEKALB AVIATION LLC | Williston | 509-322-6543 | fdekalb@gmail.com |  |  | 8/26: no concerns, done for the year and don't fly that low
DURRELL HAGOOD | WILLIAMS CO VECTOR CONTROL DIST 1 | Williston | 701-770-8645 | durrellh@co.williams.nd.us |  |  | 9/4: left msg; sent email 8/26: unable to leave msg will call back
Oil & Gas Contacts
Shawn Morten | Dakota Helicopters | Killdeer/Beulah | 701-873-4100 | chopr@westriv.com | Do not need to contact further | http://www.dakotaenergytechnologies.com/home.html - 701-764-6753 | 8/26: possible pipeline gets close to that area - ADSB-Out; possible AG sprayers - watford City, Stanley - won't cross paths
| hbk Engineering |  | 312-432-0076 | Corp Headquarters |  | https://www.hbkengineering.com/projects/xto-energy | 8/30: Mark Sheele - have a fixed wing - equipped with ADSB-out 8/26: spoke with Admin - she's finding someone to call me back
| Marathon Oil |  | 713-629-6600 | Corp Headquarters |  | https://www.marathonoil.com/operations/bakken/ | 8/26: advised to email mediarelations@marathonoil.com
| Synergy Oilfield Services | 221 Main St. New Town | 701-621-6545 |  |  | https://www.manta.com/c/mkhb60m/synergy-oil-field-services-llc | 9/10: tried to stop by - no longer there 9/4: left msg 8/26: left msg; will call back
| XTO Energy | 321 22nd Ave E, Williston, ND 58801 Killdeer; Williston | 817-870-2800 817-299-2800 701-774-6700 - Local office | Corp Headquarters |  | https://www.xtoenergy.com/operations/operating-areas/north-dakota | 9/4: tried again 8/26: unable to leave msg will call back
| Dakota Gasification Company | Beulah | 701-873-2100 800-242-2372 (HQ) | Great Plains Synfuels Plant Headquarters |  | https://www.dakotagas.com/ | 9/4: Mr. Anderson - no helicoptors; do have cessna caravan - well south and west of the area - Beuhla to Killdeer and straight north to Tyoga - nothing else scheduled (9/16) 9/4: left msg for Mr. Anderson - asked to call me back 8/26: Called ND # - advised to contact Security for coordination: 701-223-0441 Andy B; will call back
| Petro Hunt | New Town | 701-675-2467 |  |  | https://www.petrohunt.com/ | 8/26: unable to reach someone via phone; completed Contact Us form: https://www.petrohunt.com/contact/
Communitee Resources
Local First Responders
Thomasine | Central POC
Put advisory in Portal

## Contacts
Name | Organization | Title | Phone | Email | Arrival Date | Departure Date | Role | Involved in Ops/need overview | Training Needed
Valkyrie
*Catherine Self | Valkyrie UAS Solutions | Remote Pilot in Command | 907-250-7032 | catherine.self@2thedge.com; cself@valkyrie-uas.co | 2024-02-10 | 2024-02-20 | RPIC | x
*Ty Harmon | Valkyrie UAS Solutions | Hub Operator | 404-435-5900 | tyson.harmon@2thedge.com; tharmon@valkyrie-uas.co | 2024-02-10 | 2024-02-20 | HO/VO | x | VO, HO
Airspace Link
*Kelley Lindish | Airspace Link | Implementation Services DIrector | 207-751-7171 | kelley.lindish@airspacelink.com | 2024-09-15 | 2024-09-20 | ASL Set-up, stream | x
*Alberto Post | Airspace Link | UAS Project Consultant | 703-609-5020 | alberto.post@airspacelink.com | 2024-09-15 | 2024-09-20 | ASL Set-up, stream | x
*Lorenzo Malene | Airspace Link | Project Manager | 248-318-9187 | lorenzo.maleene@airspacelink.com | 2024-09-15 | 2024-09-20 | ASL Set-up, stream | x
Christian Colbert | Airspace Link | BD Director | 307- 256-8035 | christian.colbert@airspacelink.com | 2024-09-15 | 2024-09-17
UND
*David Wilson | University of North Dakota | Associate VP for Research |  | dr.wilson@und.edu
*Thomasine Heitkamp | University of North Dakota | Professor | 218-779-6249 | thomasine.heitkamp@und.edu | 2024-09-16 |  | Floater | x
*Amanda Brandt | University of North Dakota/RIAS | Senior Research Scientist | 520-444-4984 | amanda.brandt@und.edu | 2024-09-12 | 2024-09-20 | HO/VO/Data logger | x | VO, HO
*Natalia Wilson | University of North Dakota/RIAS | Autonomous systems developmer | 602-618-6100 | natalia.wilson@und.edu | 2024-09-16 | 2024-09-19
*Michael Haman | University of North Dakota | Events and Comms Specialists | 218-791-5555 | michael.Haman@und.edu
*Scott Keane | University of North Dakota/RIAS | UAS Chief Pilot | 856-325-9200 | scott.keane@und.edu | 2024-09-14 | TBD | HO/VO/Data logger
*Mark Askelson | University of North Dakota | Director of RIAS | 218-791-9917 | mark.askelson@und.edu
Zachary Reeder | University of North Dakota | Project Manager of RIAS | 920-420-4108 | zachary.reeder@und.edu |  |  | HO/VO/Data logger | x | VO, HO
*Rylee Dahlen | Unveristy of North Dakota | Graduate Assistant for MHA Drones | 701-421-7942 | rylee.dahlen@und.edu |  |  | Helper in TB | x
*Ryan Walsh | DeTect | Senior Project Manager | 701-850-6015 | ryan.walsh@detect-inc.com |  |  |  | x
*Paul Snyder | UND Aerospace | Director of UAS Operations | 218-791-4161 | paul.snyder@und.edu
*James Moe | UND Aerospace | UAS Associate | 218-779-6704 | james.moe@und.edu |  |  | Radar - Mobile Truck | x
Test Site | [6 empty] | Radar - Mobile Truck | x
*Landon Johnson | Northern Plains UAS Test Site | Program Manager | 701-367-1963 | landon.t.johnson@und.edu
Jacob Deforest | Northern Plains UAS Test Site | Director of Operations
Hunter Hegel | Northern Plains UAS Test Site | Operations Specialist
Blake Prozinski | Northern Plains UAS Test Site | Safety Lead
NHS and MHA
*Kerry Hartman | NHS College | Dean | 701-426-8936 | khartm@nhsc.edu
*Prairie Rose Seminole | NHS College | Program Manager | 701-793-6166 | pseminole@nhsc.edu
*Sheila Many Ribs | MHA Nation | Director of Planning and Grants | 701-833-0068 | smanyribs64@gmail.com
*Jared Eagle | Elbowoods | Health Administrator | 701-627-7613 | jared.eagle@ihs.gov
THALES
*Jeff Richards | Thales | ATM Operations Expert | 630-544-1372 | Jeffrey.Richards.e@thalesdigital.io | 2024-09-15 |  | VO 2 | x
*Sean Roy | Thales | UAS Operations Manager | 309-533-9200 | Sean.Roy.e@thalesdigital.io | 9/16/2024 afternoon |  | VO 3 | x
*Ian Joyce | Thales | Field Engineer | 315-263-3425 | Ian.Joyce.e@thalesdigital.io | 2024-09-15 |  | VO 4 | x
*Greta Silewski | Thales | Consultant | 701-739-6841 | greta.silewski.e@thalesdigital.io | 2024-09-16 | 2024-09-18
[5 empty] | 2024-09-15 | 2024-09-19
[5 empty] | 2024-09-15 | 2024-09-19 | VO 5
OTHERS |  |  |  |  | 2024-09-15 | 2024-09-19 | VO 6
Greg Leopold |  |  |  |  | 2024-09-15 | 2024-09-19 | VO 7
Hunter Hegel |  |  |  |  | 2024-09-15 | 2024-09-19
Shawn Roberts |  |  |  |  | 2024-09-15 | 2024-09-19 | VO 8
Steven Englert |  |  |  |  | 2024-09-15 | 2024-09-19
Thomas Gullett
Kyle Schlieman
Quinten Scott

## Needed Assets
Item | Qty | POC | Notes
Cones | 12 | Catherine (4) Landon (8?) | Mark off each launch/landing zone (1 contingency landing)
Ground Radios | ? | NPUASTS | Do we want ground radios?
Aviation Radio | 1 | Catherine
Generator | 1 | NPUASTS
Pod Docks | 2 | Catherine
Batteries | 4 | Catherine
Swoop Aero Aircraft | 2 | Catherine
Safety Vests | 3-4 |  | I think I have enough but need to verify Should others outside of Hub operators/VOs have one?
Mobile radar truck | 1 | UND | UND will bring Mobile Radar truck on 16th. Detect will be brining 2 radars as well - date TBD (PS)
Checklists | 4 | Catherine | Hub Operator - 2 sets (1 set each launch/landing zone) Remote Pilot Operator - 1 set at NT POD Swap Operator - 1 example NT
Waiver/CONOPS | 2 | Catherine | 1 set each launch/landing zone
Goodies |  | Catherine/Ty
Skydio | ? | Catherine
Payload(s) | 2 | Thomasine | Expired Epi-pens? Different sized prescription bottles? Need to finalize Payload
FIrst Aid kit | 4 | NPUASTS
hot spots | 4 | NPUASTS | Plan to have at each alternate LZ
Large TV screens to show Portal image of drone flight live. | 2 | NPUASTS | Needed by ASL/Thales to showcase the drone location on a large screen for all to see. One for take off-location, one for landing location. Power will also be required.
where is a large conference room that we can use to meet as a group? | 1 | Thomasine
Tents | 2 | NPUASTS
Chairs | 10 | NPUASTS
Cradlepoints | 2 | NPUASTS
PA System | 2 | NPUASTS | Have a small speaker/microphone combo
Scales | 2 | Catherine
Tie downs | 4 | Catherine

## 9-15 Sept - Flight Preparation
Date: | Sept 10-12
Operator: | Valkyrie UAS Solutions
Location: | Elbowoods Clinic to Twin Buttes Pavillion
Customer: | MHA Nation
Research Objective: | Check-out flights; Hub Operator training
Primary Media Representative: | N/A
Participants: | Valkyrie, UND, NPUASTS, Hub Operator
Run of Show: | Date | Responsible Party | Notes/Questions | Location
Flight Team Arrives | 2024-09-10 | Valkyrie
Unpack | 2024-09-11 |  | Kerry Hartman, Facilities Deon 701-421-0023 | NHS
Set-up Aircraft | 2024-09-11 |  | Wes has provided the name of Deon number above | NHS
File NOTAM | 2024-09-11 |  |  | NHS
Build Batteries | 2024-09-12 |  |  | NHS
Routine Checks | 2024-09-12 |  |  | NHS
Unexpected Events | 9/13, 9/14 |  |  | NHS
Hub Operator Training | 2024-09-15 |  | Ty, Amanda, NHS Student(s); 8-12 | NHS
Storage location for aircraft and supplies |  |  | NHS - Prairie Rose coordinating
NPUASTS Trailer Mobilization to New Town | 2024-09-12 | NPUASTS | 2-4 hr set up Not needed for 9/16-9/17 | New Town
NPUASTS Trailer Mobilization to Twin Buttes | 2024-09-12 | NPUASTS | 2-4 hr set up Not needed for 9/16-9/17 | Twin Buttes
Detect Radar Trucks in position | 2024-09-16 | Detect | 2 radar trailers est TBD - at clinics 1 mobile truck - | Elbowoods Twin Buttes Madaree

## 13 Sept - Check-out Flight(s) (hidden)
Date: | 2024-09-13 |  |  |  |  | Open Questions:
Operator: | Valkyrie UAS Solutions |  |  |  |  | Amanda is putting together what data is needed to be collected for Grant support
Location: | Elbowoods Clinic to Twin Buttes Pavillion |  |  |  |  | Payloads - schools selecting
Customer: | MHA Nation |  |  |  |  | Does Ty need someone in Twin Buttes with him?
Research Objective: | Check-out flights; Hub Operator training |  |  |  |  | Will the radar truck be available
Primary Media Representative: | N/A
Participants: | Thomasine or Zach or Rylee, Amanda, Landon, Ty, Catherine, perhaps 1 other person |  |  |  |  | Landon - at 1 contingency location
| Central Timezone |  |  |  |  | When set up tables & tents - set up only on day of protocol
Run of Show: | Start | Stop | Dur in min | Responsible Party | Location | Notes
Flight Ops Prep | 7:30 | 9:30 | 120 |  | NHS/Travel | Will update task times once have initial run-through
All participants meet at NHS | 7:30 | 7:45 | 15 | Catherine | NHS
Daily & Safety Briefings | 7:45 | 8:00 | 15 | Catherine | NHA
Bring aircraft to New Town Launch Location & Set Up | 8:00 | 9:00 | 60 | Catherine | Elbowoods Clinic
Perform Daily Checks | 9:00 | 9:30 | 30 | Hub Operator/Amanda
Travel to Twin Buttes | 8:00 | 9:30 | 90 | Ty, Thomasine or Zach or Rylee | Twin Buttes Pavillion | Bring cones, safety vest, cell/laptop
Travel to Contingency Location | 8:30 | 9:30 | 60 | Landon | Test Site | Bring cones, safety vest, cell/laptop
Checkout Flight 1 | 9:30 | 10:36 | 66 |  | Elbowoods to Twin Buttes
Establish Comms Channel | 9:30 | 9:35 | 5 | Catherine | Elbowoods; Twin Buttes | Will send link to participants
Flight Briefing | 9:40 | 9:45 | 5 | Catherine | Elbowoods | Comms
Perform Pre-flight Checks | 9:45 | 9:50 | 5 | Catherine/Hub Operator | Elbowoods
Verbally Confirm Ready for Launch/Launch | 9:50 | 9:51 | 1 | Catherine/Hub Operator | Elbowoods | Comms
Flight to Twin Buttes | 9:51 | 10:30 | 39 | Catherine |  | Will update flight time once load route
Alert Landing 5 mins out | 10:25 |  |  | Catherine
Land | 10:30 |  |  | Catherine
Recover Aircraft | 10:31 | 10:32 | 1 | Ty | Twin Buttes
Swap Payload/Battery | 10:32 | 10:36 | 4 | Ty | Twin Buttes
Checkout Flight 2 | 10:36 | 11:25 | 49 |  | Twin Buttes to Elbowoods
Perform Pre-flight Checks | 10:36 | 10:41 | 5 | Ty/Catherine | Twin Buttes
Announce Ready for Launch | 10:41 |  |  | Ty/Catherine | Twin Buttes
Launch | 10:41 |  |  | Ty | Twin Buttes | Comms
Flight to Twin Buttes | 10:41 | 11:20 | 39 | Catherine |  | Will update flight time once load route
Alert Landing 5 mins out | 11:15 |  |  | Catherine
Land | 11:20 |  |  | Catherine | Elbowoods
Recover Aircraft | 11:20 | 11:21 | 1 | Hub Operator/Amanda/Catherine | Elbowoods
Secure Aircraft | 11:21 | 11:25 | 4 | Catherine | Elbowoods | Catherine to bring lunch - stay with aircraft
Lunch | 11:30 | 12:30 | 60 | All
Checkout Flight 3 | 12:30 | 13:26 | 56 |  | Elbowoods to Twin Buttes
Swap Payload/Battery | 12:30 | 12:35 | 5 | Hub Operator/Amanda | Elbowoods
Establish Comms Channel | 12:30 | 12:35 | 5 | Catherine | Elbowoods; Twin Buttes; Cont Location | Will send link to participants
Perform Pre-flight Checks | 12:35 | 12:40 | 5 | Hub Operator/Amanda | Elbowoods
Verbally Confirm Ready for Launch/Launch | 12:40 | 12:41 | 1 | Hub Operator/Amanda/Catherine | Elbowoods | Comms
Flight to Twin Buttes | 12:41 | 13:20 | 39 | Catherine
Alert Landing 5 mins out | 13:15 |  |  | Catherine
Land | 13:20 |  |  | Catherine | Twin Buttes
Recover Aircraft | 13:21 | 13:22 | 1 | Ty | Twin Buttes
Swap Payload/Battery | 13:22 | 13:26 | 4 | Ty | Twin Buttes
Checkout Flight 4 | 13:26 | 14:11 | 44 |  | Twin Buttes to Elbowoods
Perform Pre-flight Checks | 13:26 | 13:31 | 5 | Ty | Twin Buttes
Verbally Confirm Ready for Launch/Launch | 13:31 |  |  | Ty/Catherine | Twin Buttes
Flight to Twin Buttes | 13:31 | 14:10 | 39 | Catherine |  | Will update flight time once load route
Pack up and Travel back to New Town | 13:31 | 15:31 | 120 | Ty, Thomasine or Zach or Rylee | Twin Buttes
Alert Landing 5 mins out | 14:05 |  |  | Catherine
Land | 14:10 |  |  | Catherine | Elbowoods
Recover Aircraft | 14:10 | 14:11 | 1 | Hub Operator/Amanda | Elbowoods
Pack up and depart for NHA | 14:11 | 15:11 | 60 |  | Elbowoods/NHS
Bingo time Flight 1 | 10:30
Bingo time Flight 2 | 11:30
Bingo time Flight 3 | 17:00
Bingo time Flight 4 | 18:00

## 16 Sept - Check-out Flight(s)
Date: | 2024-09-16 |  |  |  |  | Open Questions:
Operator: | Valkyrie UAS Solutions |  |  |  |  | How much set up time for monitors/streaming, tents, etc.
Location: | Elbowoods Clinic to Twin Buttes Pavillion
Customer: | MHA Nation
Research Objective: | Check-out flights; Hub Operator training
Primary Media Representative: | N/A
Participants: | Valkyrie, NPUASTS, Hub Operator, Amanda, ASL, Data Collector
Central Timezone
Run of Show: | Start | Stop | Dur in min | Responsible Party | Location | Notes
Flight Ops Prep | 7:30 | 9:30 | 120 |  | NHS/Travel | Will update task times once have initial run-through
All participants meet at Earth Lodge Village | 7:30 | 7:45 | 15 | Catherine | Earth Lodge Village
Daily & Safety Briefings | 7:45 | 8:00 | 15 | Catherine | Earth Lodge Village
Perform Daily Checks | 8:00 | 8:30 | 30 | Amanda/Hub Operator | Earth Lodge Village
VLOS Checkout Flights | 8:30 | 10:30 | 120 | Catherine/Ty | Earth Lodge Village
Travel to Twin Buttes | 8:00 | 9:30 | 90 | ASL, NPUASTS, Detect | Twin Buttes Pavillion | Bring cones, safety vest, cell/laptop
Set up Streaming Capability in Twin Buttes | 9:30 | 10:00 | 30 | ASL
Set up Streaming Capability in Elbowoods | 8:00 | 8:30 | 30 | ASL
Travel to Contingency Location | 8:30 | 9:30 | 1h | NPUASTS | Test Site | Bring cones, safety vest, cell/laptop
Travel to Manadree Radar Truck Location | 8:30 | 9:30 | 1h | Detect | TBD
Set up Radar Truck | 9:30 | 10:00 | 30 | Detect | TBD | Confirm ready
Move Drones to Elbowoods | 10:30 | 11:15 | 45 | Catherine
Travel to Twin Buttes | 10:30 | 12:00 | 90 | Ty
Lunch | 11:15 | 12:15 | 60 | All | Elbowoods
Checkout Flight 3 | 12:15 | 13:11 | 54 |  | Elbowoods to Twin Buttes
Establish Comms Channel | 12:15 | 12:20 | 5 | Catherine | Elbowoods; Twin Buttes | Will send link to participants
Perform Pre-flight Checks | 12:20 | 12:25 | 5 | Hub Operator/Amanda | Elbowoods
Verbally Confirm Ready for Launch/Launch | 12:25 | 12:26 | 1 | Hub Operator/Amanda/Catherine | Elbowoods | Comms
Flight to Twin Buttes | 12:26 | 13:05 | 39 | Catherine | In transit
Alert Landing 5 mins out | 13:00 |  |  | Catherine | In transit
Land | 13:05 |  |  | Catherine | Twin Buttes
Recover Aircraft | 13:06 | 13:07 | 1 | Ty | Twin Buttes
Swap Payload/Battery | 13:07 | 13:11 | 4 | Ty | Twin Buttes
Checkout Flight 4 | 13:11 | 13:57 | 45 |  | Twin Buttes to Elbowoods
Perform Pre-flight Checks | 13:11 | 13:16 | 5 | Ty | Twin Buttes
Verbally Confirm Ready for Launch/Launch | 13:16 | 13:17 | 1 | Ty/Catherine | Twin Buttes
Flight to Twin Buttes | 13:17 | 13:56 | 39 | Catherine |  | Will update flight time once load route
Pack up and Travel back to New Town | 13:16 | 15:16 | 120 | Ty, ASL, NPUASTS, Detect | Twin Buttes
Alert Landing 5 mins out | 13:51 |  |  | Catherine
Land | 13:56 |  |  | Catherine | Elbowoods
Recover Aircraft | 13:56 | 13:57 | 1 | Hub Operator/Amanda | Elbowoods
Move Aircraft Back to Earth Lodge for Dinner | 13:57 | 14:42 | 45 | Catherine, Amanda, HO | Earth Lodge Village
Debrief | 15:16 | 15:46 | 30 | All | Earth Lodge Village
Set Up for Dinner Event | 16:00 | 17:00 |  | All | Earth Lodge Village
Dinner Event | 17:00 | 19:00 |  | All | Earth Lodge Village
Bingo time Flight 3 | 13:00
Bingo time Flight 4 | 14:00

## 16 Sept Burger Burn Event
Date: | 2024-09-16 |  | Open Items:
Operator: |  |  | What to cover in the operations awareness event
Location: | NHA or Earth Lodge Villiage |  | Pre-coordination of locations - Prairie Rose
Customer: | Communittee engagement |  | Get list of what we need from Prairie Rose
Participants |  |  | Confirm times with location availability
Thomasine working with event coordinator to plan | Earth Lodge Village is Rented and Better Bs will cater |  | Get picture of drone for the billboard
Run of Show: | Location | Items transported | Start | Stop | Dur in Min | Responsible Party | Notes | Actions | Asignee | Status | Addt'l Notes
Organ Vitality:
Liver: 1-4 hrs…average 2 hrs
Kidney: 1-8 hrs…average 3
Pancreas: 1-6 hrs…average 3

## 17 Sept - Dress Rehersal
Date: | 2024-09-17 |  |  |  |  | Open Questions:
Operator: | Valkyrie UAS Solutions
Location: | Elbowoods Clinic to Twin Buttes Pavillion
Customer: | MHA Nation
Research Objective: | Check-out flights; Hub Operator training
Primary Media Representative: | N/A
Participants: | Valkyrie, NPUASTS, Hub Operator, Amanda, ASL, Data Collector, Dectect
Central Timezone
Run of Show: | Start | Stop | Dur in min | Responsible Party | Location | Notes
Flight Ops Prep | 7:30 | 9:30 | 120 |  | Elbowoods/Travel | Will update task times once have initial run-through
All participants meet at NHS | 7:30 | 7:45 | 15 | Catherine | Elbowoods Clinic
Daily & Safety Briefings | 7:45 | 8:00 | 15 | Catherine | Elbowoods Clinic
Bring aircraft to New Town Launch Location & Set Up | 8:00 | 9:00 | 60 | Catherine | Elbowoods Clinic
Perform Daily Checks | 9:00 | 9:30 | 30 | Hub Operator/Amanda
Travel to Twin Buttes | 8:00 | 9:30 | 90 | Ty, ASL, NPUASTS, Detect | Twin Buttes Pavillion | Bring cones, safety vest, cell/laptop
Travel to Contingency Location | 8:30 | 9:30 | 1h | NPUASTS | Test Site | Bring cones, safety vest, cell/laptop
Travel to Manadree Radar Truck Location | 8:30 |  |  | Detect | TBD
Set up Radar Truck | 0:00 |  |  | Detect | TBD | Confirm ready
Checkout Flight 1 | 9:30 | 10:36 | 66 |  | Elbowoods to Twin Buttes
Establish Comms Channel | 9:30 | 9:35 | 5 | Catherine | Elbowoods; Twin Buttes | Will send link to participants
Flight Briefing | 9:40 | 9:45 | 5 | Catherine | Elbowoods | Comms
Perform Pre-flight Checks | 9:45 | 9:50 | 5 | Catherine/Hub Operator | Elbowoods
Verbally Confirm Ready for Launch/Launch | 9:50 | 9:51 | 1 | Catherine/Hub Operator | Elbowoods | Comms
Flight to Twin Buttes | 9:51 | 10:30 | 39 | Catherine | In transit | Will update flight time once load route
Alert Landing 5 mins out | 10:25 |  |  | Catherine | In transit
Land | 10:30 |  |  | Catherine | Twin Buttes
Recover Aircraft | 10:31 | 10:32 | 1 | Ty | Twin Buttes
Swap Payload/Battery | 10:32 | 10:36 | 4 | Ty | Twin Buttes
Checkout Flight 2 | 10:36 | 11:25 | 49 |  | Twin Buttes to Elbowoods
Perform Pre-flight Checks | 10:36 | 10:41 | 5 | Ty | Twin Buttes
Announce Ready for Launch | 10:41 |  |  | Ty | Twin Buttes
Launch | 10:41 |  |  | Ty | Twin Buttes | Comms
Flight to Twin Buttes | 10:41 | 11:20 | 39 | Catherine | In transit | Will update flight time once load route
Alert Landing 5 mins out | 11:15 |  |  | Catherine | In transit
Land | 11:20 |  |  | Catherine | Elbowoods
Recover Aircraft | 11:20 | 11:21 | 1 | Hub Operator/Amanda | Elbowoods
Secure Aircraft | 11:21 | 11:25 | 4 | Hub Operator/Amanda | Elbowoods | Catherine to bring lunch - stay with aircraft
Lunch | 11:30 | 12:30 | 60 | All | Elbowoods
Checkout Flight 3 | 12:30 | 13:26 | 54 |  | Elbowoods to Twin Buttes
Swap Payload/Battery | 12:30 | 12:35 | 5 | Hub Operator/Amanda | Elbowoods
Establish Comms Channel | 12:30 | 12:35 | 5 | Catherine | Elbowoods; Twin Buttes | Will send link to participants
Perform Pre-flight Checks | 12:35 | 12:40 | 5 | Hub Operator/Amanda | Elbowoods
Verbally Confirm Ready for Launch/Launch | 12:40 |  |  | Hub Operator/Amanda/Catherine | Elbowoods | Comms
Flight to Twin Buttes | 12:41 | 13:20 | 39 | Catherine | In transit
Alert Landing 5 mins out | 13:15 |  |  | Catherine | In transit
Land | 13:20 |  |  | Catherine | Twin Buttes
Recover Aircraft | 13:21 | 13:22 | 1 | Ty | Twin Buttes
Swap Payload/Battery | 13:22 | 13:26 | 4 | Ty | Twin Buttes
Checkout Flight 4 | 13:26 | 14:11 | 45 |  | Twin Buttes to Elbowoods
Perform Pre-flight Checks | 13:26 | 13:31 | 5 | Ty | Twin Buttes
Verbally Confirm Ready for Launch/Launch | 13:31 |  |  | Ty/Catherine | Twin Buttes
Flight to Twin Buttes | 13:31 | 14:10 | 39 | Catherine | In transit | Will update flight time once load route
Pack up and Travel back to New Town | 13:31 | 15:31 | 120 | Ty | Twin Buttes
Alert Landing 5 mins out | 14:05 |  |  | Catherine | In transit
Land | 14:10 |  |  | Catherine | Elbowoods
Recover Aircraft | 14:10 | 14:11 | 1 | Hub Operator/Amanda | Elbowoods
Pack up and depart for NHA | 14:11 | 15:11 | 60 | Ty, ASL, NPUASTS, Detect | Elbowoods/NHS
Bingo time Flight 1 | 10:30
Bingo time Flight 2 | 11:30
Bingo time Flight 3 | 17:00
Bingo time Flight 4 | 18:00

## 18 Sept - Protocol Flight
Date: | 2024-09-18 | Weather day Sept 19 |  |  |  | Open Questions
Operator: | Valkyrie UAS Solutions |  |  |  |  | Can we set up tents, etc. on 9/16 and leave up through 9/18 or do those need to be set up daily?
Location: | Elbowoods Clinic to Twin Buttes Pavillion
Customer: | MHA Nation
Research Objective: | Demonstrate medical transportation use case
Primary Media Representative: | MHA Nation
Participants: | Valkyrie, NPUASTS, Hub Operator, Amanda, ASL, Data Collector, Dectect
Central Timezone
Run of Show: | Start | Stop | Dur in min | Responsible Party | Location | Notes
Flight Ops Prep | 7:30 | 9:30 | 120 |  | Elbowoods/Travel | Will update task times once have initial run-through
All participants meet at NHS | 7:30 | 7:45 | 15 | Catherine | Elbowoods Clinic
Daily & Safety Briefings | 7:45 | 8:00 | 15 | Catherine | Elbowoods Clinic
Bring aircraft to New Town Launch Location & Set Up | 8:00 | 9:00 | 60 | Catherine | Elbowoods Clinic
Perform Daily Checks | 9:00 | 9:30 | 30 | Hub Operator/Amanda
Travel to Twin Buttes | 8:00 | 9:30 | 90 | Ty, ASL, NPUASTS, Detect | Twin Buttes Pavillion | Bring cones, safety vest, cell/laptop
Travel to Contingency Location | 8:30 | 9:30 | 1h | NPUASTS | Test Site | Bring cones, safety vest, cell/laptop
Travel to Manadree Radar Truck Location | 8:30 |  |  | Detect | TBD
Set up Radar Truck | 0:00 |  |  | Detect | TBD | Confirm ready
Checkout Flight 1 | 9:30 | 10:36 | 66 |  | Elbowoods to Twin Buttes
Establish Comms Channel | 9:30 | 9:35 | 5 | Catherine | Elbowoods; Twin Buttes | Will send link to participants
Flight Briefing | 9:40 | 9:45 | 5 | Catherine | Elbowoods | Comms
Perform Pre-flight Checks | 9:45 | 9:50 | 5 | Catherine/Hub Operator | Elbowoods
Verbally Confirm Ready for Launch/Launch | 9:50 | 9:51 | 1 | Catherine/Hub Operator | Elbowoods | Comms
Flight to Twin Buttes | 9:51 | 10:30 | 39 | Catherine | In transit | Will update flight time once load route
Alert Landing 5 mins out | 10:25 |  |  | Catherine | In transit
Land | 10:30 |  |  | Catherine | Twin Buttes
Recover Aircraft | 10:31 | 10:32 | 1 | Ty | Twin Buttes
Swap Payload/Battery | 10:32 | 10:36 | 4 | Ty | Twin Buttes
Public Engagement | 10:36 | 11:06 | 30 |  | Twin Buttes
Checkout Flight 2 | 10:36 | 11:55 | 49 |  | Twin Buttes to Elbowoods
Perform Pre-flight Checks | 11:06 | 11:11 | 5 | Ty | Twin Buttes
Announce Ready for Launch | 11:11 |  |  | Ty | Twin Buttes
Launch | 11:11 |  |  | Ty | Twin Buttes | Comms
Flight to New Town | 11:11 | 11:50 | 39 | Catherine | In transit | Will update flight time once load route
Alert Landing 5 mins out | 11:45 |  |  | Catherine | In transit
Land | 11:50 |  |  | Catherine | Elbowoods
Recover Aircraft | 11:50 | 11:51 | 1 | Hub Operator/Amanda | Elbowoods
Secure Aircraft | 11:51 | 11:55 | 4 | Hub Operator/Amanda | Elbowoods | Catherine to bring lunch - stay with aircraft
Lunch | 11:55 | 12:55 | 60 | All | Elbowoods
Checkout Flight 3 | 12:55 | 13:51 | 54 |  | Elbowoods to Twin Buttes
Swap Payload/Battery | 12:55 | 13:00 | 5 | Hub Operator/Amanda | Elbowoods
Establish Comms Channel | 12:55 | 13:00 | 5 | Catherine | Elbowoods; Twin Buttes | Will send link to participants
Perform Pre-flight Checks | 13:00 | 13:05 | 5 | Hub Operator/Amanda | Elbowoods
Verbally Confirm Ready for Launch/Launch | 13:05 |  |  | Hub Operator/Amanda/Catherine | Elbowoods | Comms
Flight to Twin Buttes | 13:06 | 13:45 | 39 | Catherine | In transit
Alert Landing 5 mins out | 13:40 |  |  | Catherine | In transit
Land | 13:45 |  |  | Catherine | Twin Buttes
Recover Aircraft | 13:46 | 13:47 | 1 | Ty | Twin Buttes
Swap Payload/Battery | 13:47 | 13:51 | 4 | Ty | Twin Buttes
Public Engagement | 13:51 | 14:21 | 30 |  | Twin Buttes
Checkout Flight 4 | 14:21 | 15:06 | 45 |  | Twin Buttes to Elbowoods
Perform Pre-flight Checks | 14:21 | 14:26 | 5 | Ty | Twin Buttes
Verbally Confirm Ready for Launch/Launch | 14:26 |  |  | Ty/Catherine | Twin Buttes
Flight to New Town | 14:26 | 15:05 | 39 | Catherine | In transit | Will update flight time once load route
Pack up and Travel back to New Town | 14:26 | 16:26 | 120 | Twin Buttes Team | Twin Buttes
Alert Landing 5 mins out | 15:00 |  |  | Catherine | In transit
Land | 15:05 |  |  | Catherine | Elbowoods
Recover Aircraft | 15:05 | 15:06 | 1 | Hub Operator/Amanda | Elbowoods
Pack up and depart for NHA | 15:06 | 16:06 | 60 | ASL, NPUASTS, Detect | Elbowoods/NHS
Bingo time Flight 1 | 10:30
Bingo time Flight 2 | 11:30
Bingo time Flight 3 | 17:00
Bingo time Flight 4 | 18:00

## 19 Sept - Debrief
Date: | 2024-09-19
Location: | NHS
Research Objective: | Debrief
Facilitator:
Participants: | ASL, UND, NPUASTS, Valkyrie, NHS, MHA with Roles
Run of Show: | Start | Stop | Dur in min
Arrive | 8:00 | 8:15 | 15
Review Objectives |  |  | 5 | Outline the purpose of the debrief Define what the team hopes to achieve by the end of the meeting
Summary of the Event/Project/Activity |  |  | 10 | Provide a brief overview of what was undertaken Highlight key outcomes and milestones
What Went Well |  |  | 15 | Discuss successes and positive aspects Recognize achievements and contributions
Challenges and Areas for Improvement |  |  | 20 | Identify issues or obstacles encountered Discuss areas where performance could be enhanced
Lessons Learned |  |  | 15 | Share insights gained from the experience Consider how these lessons can be applied in the future
Action Items and Next Steps |  |  | 10 | Assign tasks and responsibilities for follow-up actions Set deadlines and determine who will be accountable
Feedback and Closing Remarks |  |  | 10 | Invite feedback from attendees on the debrief process Summarize key takeaways and final thoughts Confirm date and time for the next meeting if needed
Adjournment
Phase 2 Strategy Discussions?

## Full Schedule and location of e
Twin Buttes | New Town | ELZ #1 | ELZ #2 | ELZ #3

## TBD - Clinic 3 (hidden)
Date:
Operator:
Location:
Customer:
Research Objective:
Primary Media Representative:
Participants:
OIC:
Primary POC:
Secondary POC:
Run of Show: | Start | Stop | Responsible Party | Notes | Actions | Asignee | Status | Addt'l Notes | Addt'l Notes

## Invitees
Notes
VIPs
Tribal Council
Project Team Roles for Protocol Flight
Comm Plans and Invitations