## Slide 1: MHA Nation SMART Grant Execution Timeline

## Slide 2
2023
2025
61 days
62 days
65 days
198 days
Program Mngt
2023
Q4
Q1
Q2
Q3
Nov
Jan
Mar
May
Jul
Sep
Nov
Today
Jan
2024
2025
Q4
Q1
Qtrly Report 1
12/31
Data Managment Plan
3/25
Qtrly Report 2
4/15
Qtrly Report 3
7/15
Qtrly Report 4
10/15
Final SMART Report
2/1
Apr 16 - Jul 10
Draft&Review Qtr3
Jul 16 - Oct 10
Draft&Review Qtr4
Oct 16 - Jan 15
Draft&Review Final Smart Report
Mar 31 - Jan 1
Draft Tier II Funding Request

## Slide 3
2023
2025
0 d
61 days
109 days
33 days
64 days
42 days
33 days
44 days
44 days
44 days
Implementation
2023
Q4
Q1
Q2
Q3
Nov
Jan
Mar
May
Jul
Sep
Nov
Today
3/31
MHA Subs on Contract
Jan
2024
Q4
Dec 31 - Mar 25
Use Case Fully Vetted
Platform Selection
4/15
MHA Route Approved
5/15
MHA Approval of Lauch/Landing Site
6/1
Apr 15 - Sep 15
ID of Vantis Site(s)
MHA Approval of Vantis Site(s)
10/1
Apr 15 - May 30
Safety Case Draft
MHA Approval of CONOPS
6/15
FAA Final Approval of BVLOS
7/30
Protocol Flight Execution
9/15
Jan 1 - Mar 31
Platform Requirements ID'd
Mar 1 - Apr 30
Route ID/GIS obtained
Apr 15 - May 30
CONOPS Draft
Mar 31 - May 30
ID of Launch & Landing Site
Mar 31 - May 30
FAA BVLOS Waiver Draft
FAA BVLOS Submission
6/15
CONOPs Complete
7/1
Safety Case Complete
7/1
2025
Q1
Platform under contract (if able to direct hire)
5/15
MHA Approval of Safety Case
6/15
45 days
Apr 12 - Jun 15
Competative Bid Timeline (If going out for bids)
89 days
Apr 14 - Aug 15
Draft Implementation Plan
Final Implementatin Plan Approval from MHA
7/31
Secondary Use Cases Finalized & Approved by MHA
4/30
Risk Profiles Finalized by Operator & Site Selection Criteria Finalized
4/30
Site Survey of Launch/Landing Site
5/8
Site Survey of Infrastructure Placement Sites
6/8
notional date, dependent on when FAA actually approves
FAA Approval could take up to 90+ days
End of Phase 1 POP
2/14

## Slide 4
2023
2025
55 d
44 days
197 days
Work Force Dvlpmt
Budget Managment
2023
Q4
Q1
Q2
Q3
Nov
Jan
Mar
May
Jul
Sep
Nov
Today
Drone Camp Planning
3/31 - 6/15
Part 107 Curriculum Complete
12/31
Drone Camp Execution
7/17
Apr 15 - Jun 15
Visual Observer Training Plan
Visual Observer Execution
9/15
Mar 31 - Dec 31
Part 107 Curriculum Development
MHA approval of drone camp plan
6/30
MHA approval of VO training plan
6/30
2024
Q4
2025
Q1
Q2
Jan
Mar
Final Budget spend report to DOT
2/15