## README
See CM4QC Document Sec. 7 and Appendix III for detailed descriptions of the SML matrix cells shown on workbook “SML_Assessment_Guide_Rev_0”. The "Documentation Activity Tracker" workbook is intended to be an aid for the team to track numerous ongoing documentation tasks described by the SML Matrix. This document should be customized to the needs of a particular effort, rather than being applied as a prescriptive checklist in the supplied form. As an example, the values and definitions in the "Status" and "Importance" keys should be modified in accordance with a particular project's needs and requirements. Additionally, concurrent activities may span multiple levels from the SML Matrix. The activity tracker is ordered according to SML for convenience, and while there are cases with prerequisite activities, in general the order on the tracker should not be construed as a strict required sequence of activities.

## SML_Assessment_Guide_Rev_0
Maturity Level Assessment Guide for Q&C Simulation Platforms
CM4QC V4.9-12/10/2025
SML | Q&C Simulation Maturity Description | Application & Model Definition | Range of Applicability | Supporting Data | Model Verification | Uncertainty Quantification | Model Validation | Performance Risk Assessment | Documentation
1 | All underlying models are clearly defined, including inputs, outputs, and application intent. Analytical process is exploratory in nature. Fidelity of predictions are largely unproven. Provides some physical insight, but not yet suitable for adoption in Q&C activities. | Application intent defined. Models defined. Model inputs and outputs defined. | Range of applicability of the physics and data-based models are defined to satisfy the intended application. | Supporting data requirements identified and documented in coordination with Verification, Range, UQ, Validation, and Risk tasks. | Code and solution verification plan developed. Preliminary and informal code verification performed. Version control strategy selected. QOIs for solution verification identified. | Parameters of interest and UQ plan defined. | Validation requirements defined for selected application. | Identify risks associated with CM use for application. Complete an initial Risk Assessment. | Outcomes of SML level 1 planning and description activities for other SML criteria documented.
2 | Proven capability for comparative assessment, ranking, or trending. Experimental validation remains incomplete. Can be used to inform other activities relevant to Q&C. | Significant submodels defined. All sub-model inputs and outputs defined. | All input parameter ranges and the effects of their interactions specified to satisfy the intended range of applicability. | Some supporting data available. Data documentation and archival plan developed. Access control and authentication plan in place for cases where broad accessibility is not feasible. FAIR principles considered. | Rigorous code verification completed for individual sub-models by demonstrating theoretical order of accuracy and/or convergence rates, where applicable. Unit testing implemented for sub-models. Version control implemented, documented, and archived. | Deterministic sensitivity study performed on selected input parameters to quantify influence on QOIs. One-at-a-time, DOE, and expert opinion coupled with sensitivity analysis performed for input parameters. Parameters and range of outputs identified. | Validation plan developed for both intended use and all sub-models. | Risk assessment plan should be fully developed taking validation and UQ plans into account. Mitigation plans should also be fully developed. | User guide initiated, SML 1 plans updated, and SML 2 activities documented.
3 | Capability is verified and validated for limited cases. Use is primarily limited to research activities. Impact to industry activities occurs primarily through work where results could be used to inform Q&C activities. | Recommended applications and limitations defined. | Limitations implemented to control use or warn user if inputs & outputs are outside of range. Sub-model outputs generated and assessed over required ranges. | Supporting data adequate to perform SML 3 Validation and UQ tasks over a limited range of application. All supporting data identified, documented, and archived. | Rigorous code verification completed for relevant combinations of sub-models by demonstrating theoretical order of accuracy and/or convergence rates, where applicable. Refinement studies completed for problems of interest, with mesh convergence demonstrated. Regression testing implemented. | Random variables identified and quantified. Probability-based UQ analysis performed for sub-model outputs. Probabilistic sensitivities quantified. | Sub-models validated against established benchmarks or equivalent data. Model output similarly validated for specific cases. | Preliminary risk assessment conducted with input from validation and UQ analysis. Mitigation activities should be reviewed and assessed to reduce likelihood of occurrence and/or consequences to level acceptable for the application. | User guide developed and documented. Licensing and support strategy considered, if applicable. SML 3 activities documented.
4 | Capability is fully verified and validated for industry use cases. Software platform is used by industry, but relevance is primarily to research activities, with occasional direct impact to Q&C activities. Results are used primarily to provide guidance and confidence to design and development activities. | Recommended applications and limitations updated. | Models, sub-models, and their interfaces assessed for all intended input ranges and use cases. | Supporting data adequate to perform SML 4 Validation and UQ tasks for several relevant use cases. All supporting data identified, documented and archived. | Numerical error, including discretization error where applicable, quantified for QOIs in problem of interest and deemed small compared with validation measurement error. Regular regression testing for one or more platforms. | UQ analysis per #3 performed and documented for the quantities of interest (QOIs) from full model for all relevant use cases. Probability results available for validation for all QOIs. | Model and sub-models validated for all relevant use cases using established hierarchical benchmarks or equivalent data. | Risk for CM use assessed for application in component and process development and testing stages. | User guide updated to reference supporting data, UQ analysis, verification and validation cases. Licensing and support implemented, if applicable. SML 4 activities documented.
5 | Software platform is widely adopted by industry. Model predictions are directly applicable to Q&C activities. | Recommended applications and limitations updated. | Full range of applicability updated for all intended use cases. | Supporting data documentation and archive maintenance performed as additional experience from SML 5 Validation or UQ tasks becomes available. | All numerical error sources (including round-off, discretization, and iteration tolerance) are understood and quantified for QOIs. Automated and documented regression testing system implemented for all relevant platforms. | FAIR modeling & measurement data summarized. Results compared against industry-accepted, benchmark or standard cases as available. Results documented and reviewed for validation for all QOIs. | Model fully validated over range of applicability using validation data, operational performance data, and experience. | Risk assessed for application Q&C activities. | User guide updated. SML 5 activities documented.

## Documentation Activity Tracker
Documentation Activity Tracker (Column G) | [8 empty] | Example* Status key |  | Example* Importance Key |  | SML Matrix Column
SML | Item | Status | Date Updated | Importance | SML Column | Notes | Responsible Party (Parties) | Document Reference | Status value | Description | Importance Value | Description | Colum Letter | Full Column Title
1 | Application and model definitions documented | 0-3 |  |  | C |  |  | e.g. file name, commit hash, DOI, link, etc. | N/A | Not applicable | Best Practice |  | C | Application and Model Definition
| Intended range of applicability documented | 0-3 |  |  | D |  |  |  | 0 | Not started | Required |  | D | Range of Applicability
| Supporting data requirements documented | 0-3 |  |  | E |  |  |  | 1 | Draft initiated/outline exists |  |  | E | Supporting Data
| Code verification plan documented | 0-3 |  |  | F |  |  |  | 2 | Mature draft |  |  | F | Model Verification
| Solution verification plan documented | 0-3 |  |  | F |  |  |  | 3 | Item complete |  |  | G | Uncertainty Quantification
| Version control strategy identified and documented | 0-3 |  |  | F |  |  |  | Yes |  |  |  | H | Model Validation
| Verification Quantities of interest defined, documented | 0-3 |  |  | F |  |  |  | No |  |  |  | I | Performance Risk Assessment
| Parameters of interest listed | 0-3 |  |  | G | [7 empty] | J | Documentation
| UQ plan documented | 0-3 |  |  | G
| Validation requirements documented | 0-3 |  |  | H | Application specific
| Initial risk assessment documented | 0-3 |  |  | I |  |  |  | Column Name | Description
1 | This tracker updated |  |  |  | J | Update |  |  | SML | Software Maturitly Level
2 | Submodels defined and documented | 0-3 |  |  | C |  |  |  | Item | Description of the item/activity being considerd
| Submodel inputs/outputs documented | 0-3 |  |  | C |  |  |  | Status | Current status Item as measured on an agreed upon scale
| Input parameter ranges and effects documented | 0-3 |  |  | D | If applicable, also see column G |  |  | SML Column | The column of the SML matrix from which the item is derived
| Any extant supporting data documented | 0-3 |  |  | E | Note sources, etc. |  |  | Notes | Additional comments or considerations
| Supporting data access control plan documented | 0-3 |  |  | E |  |  |  | Responsible Party (Parties) | The individual or entity primarily responsible for completing actions related to Item.
| FAIR principles considered | Yes/No |  |  | E | Note whether FAIR will be utilized |  |  | Document Reference | A link or reference to relevant, substantiating documents (e.g., DOI, URL, file path)
| Code verification cases documented | 0-3 |  |  | F
| Submodel unit tests documented | 0-3 |  |  | F | Note % passing
| Any changes to version control strategy documented | 0-3 |  |  | F | If applicable
| Sensitivity analysis results documented, including range of outputs | 0-3 |  |  | G
| Validation plan documented | 0-3 |  |  | H | For main and submodels
| Risk Assessment and Mitigation plans documented | 0-3 |  |  | I | With consideration for columns G and H.
| Draft user guide written | 0-3 |  |  | J
2 | This tracker updated |  |  |  | J
3 | Applications and limitations documentation updated | 0-3 |  |  | C | If applicable
| Range limitations documented | 0-3 |  |  | D
| Sub-model output assessment documented | 0-3 |  |  | D
| Supporting data description and archive manifest updated | 0-3 |  |  | E | Update, if applicable. Note requirements from SML 3 activities in columns G and H.
| Code verification case documentation updated | 0-3 |  |  | F | As applicable
| Regression testing cases documented | 0-3 |  |  | F
| Random variables documented | 0-3 |  |  | G
| Probability based UQ analysis outcomes documented for sub-models | 0-3 |  |  | G
| Sub-model validation performance documented | 0-3 |  |  | H
| Model validation performance documented for specific cases | 0-3 |  |  | H | For specific/subset of use cases
| Preliminary risk assessment documented | 0-3 |  |  | I | Describes input from columns G and H.
| Updates to mitigation activities documented | 0-3 |  |  | I | Describes input from columns G and H.
| User guide updated | 0-3 |  |  | J
| Licensing strategy documented | 0-3 |  |  | J | If applicable
| Support strategy documented | 0-3 |  |  | J | If applicable
3 | This tracker updated |  |  |  | J
4 | Applications and limitations documentation updated | 0-3 |  |  | C | If applicable
| Model and submodel range limitations documents updated | 0-3 |  |  | D
| Adequacy of supporting data for Validation, UQ documented | 0-3 |  |  | E
| Supporting data archive manifest updated | 0-3 |  |  | E
| Discretization errors documented | 0-3 |  |  | F | If applicable
| Regression testing cases documented, updated | 0-3 |  |  | F
| Probability based UQ analysis outcomes documented for full model, all test cases | 0-3 |  |  | G
| UQ probability validation documented | 0-3 |  |  | G
| Model and submodel validation performance documented across relevant cases | 0-3 |  |  | H | For all use-cases considered
| Risk assessment documented for development and testing stage | 0-3 |  |  | I
| User guide updated | 0-3 |  |  | J
| Licensing, support documents available | Yes/no |  |  | J | If applicable
4 | This tracker updated |  |  |  | J
5 | Applications and limitations documentation updated | 0-3 |  |  | C | If applicable
| Range of applicability updated across relevant use cases | 0-3 |  |  | D
| Supporting data documentation updated/maintained | 0-3 |  |  | E | If applicable. Ongoing as additional validation cases added
| All numerical error sources documented | 0-3 |  |  | F
| Regression testing documentation updated | 0-3 |  |  | F | Ongoing
| UQ applied benchmark cases documented | 0-3 |  |  | G
| Model performance compared to requirements for intended use | 0-3 |  |  | G (possibly H)
| Benchmark validation case outcomes documented | 0-3 |  |  | H
| Risk quantification documentation updated to include application Q & C activities | 0-3 |  |  | I
| User guide updated | 0-3 |  |  | J | If applicable
| Verification and Validation cases fully documented | 0-3 |  |  | J | Note tasks for columns F and H.
5 | This tracker updated |  |  |  | J

## Risk Matrix
Figure 1: Consequences vs Likelihood 5X5 Risk Matrix*
Adapted for ICME / Simulation Maturity Level Applications
| Likelihood of Occurrence | 5 (>70%)
4 (>50%)
3 (>30%)
2 (>5%)
1 (<5%)
|  |  | 1 Minor | 2 Low | 3 Moderate | 4 Significant | 5 Severe
Consequences (Increasing Severity >>)
Low risk: Monitor to ensure risk remains low.
Medium Risk: Aggressively manage. Consider alternatives or risk mitigation actions.
High Risk: Develop and implement alternative or concurrent approaches.
*Adapted from: NASA, “Guidelines for Preparing Project Risk Management Plans”, New Millennium Program, NMP-GL-07, 6/7/2005.
Figure 2: Example of Risk Identification, Impact, and Mitigation Actions
ICME for Qualification of AM Metallic Parts
[8 empty] | Item |  | Risk | Likelihood | Consequence | Rating
[8 empty] | 1 | Risk: | Thermal process model does not predict temperature transients accurately. | 3 (> 30%, Moderate) | 3 (Moderate) | Y
[9 empty] | Impact: | Residual stress (RS), distortion, microstructure, and property predictions will not be accurate
[9 empty] | Mitigation: | Add thermo-physical measurements; improve thermal melt profile measurement | 2 | 3 | G
[8 empty] | 2 | Risk: | Fatigue predictions not accurate enough for life predictions | 4 (>50%, More likely than not) | 3 (Moderate) | R
[9 empty] | Impact: | Cannot use fatigue predictions in life prediction
[9 empty] | Mitigation: | Use alternate modeling options like AI/ML or add missing physics | 3 (>30%, Moderate) | 3 (Moderate) | Y
[8 empty] | 3 | Risk: | Uncertainty quantification indicates RS values having insufficent fidelity for life prediction | 4 (>50%, More likely than not) | 4 (Significant impact) | R
[9 empty] | Impact: | Cannot include residual stress predictions directly in life predictions.
[9 empty] | Mitigation: | Use multiple RS measurement methods to quantify and bound UQ; use Bayseian updating of models to improve accuracy | 3 (>30%, Moderate) | 3 (Moderate) | Y
Figure 3: Example Illustration of Risk Matrix and Mitigation Actions
| Likelihood of Occurrence | 5 (>70%)
4 (>50%)
3 (>30%)
2 (>5%)
1 (<5%)
|  |  | 1 Minor | 2 Low | 3 Moderate | 4 Significant | 5 Severe
Consequences (Increasing Severity >>)
Low risk: Monitor to ensure risk remains low.
Medium Risk: Aggressively manage. Consider alternatives or risk mitigation actions.
High Risk: Develop and implement alternative or concurrent approaches.
| Risk Item: from table |  |  | Effect of risk mitigation action.
1
1
2
3
3
x
Notes:
1. Risk identification may come from project team using various techniques, including PIRT or other expert elicitation process.
2. Risk and Consequences should be assessed for specific application.
3. Risk-Consequences assessment should be included in V&V planning and any gate review for the project. See step 7 in the Recommended Best Practice Flow Chart.
2
Note on C7: Brad: Very likely to occur.
Note on C8: Brad: More likely than not to occur.
Note on C9: Brad: Moderate likelihood of occurrence.
Note on C10: Brad: Low likelihood of occurrence.
Note on C11: Brad: Very low likelihood of occurrence.
Note on D12: Brad: Minimal impact to cost, schedule, or technical result.
Note on E12: Brad: Some impact to cost, schedule, or technical result. Recoverable within program or project scope.
Note on F12: Brad: Moderate impact to cost, schedule, or technical result. Requires significant program or project resources to recover.
Note on G12: Brad: Significant impact to cost, schedule, or technical results of program or project. Goals or objectives not fully achievable.
Note on H12: Brad: Extreme impact to cost, schedule, or technical results of project or program. Not recoverable with program or project resources. Jeopardizes or fails to meet project or program objectives.
Note on C44: Brad: Very likely to occur.
Note on C45: Brad: More likely than not to occur.
Note on C46: Brad: Moderate likelihood of occurrence.
Note on C47: Brad: Low likelihood of occurrence.
Note on C48: Brad: Very low likelihood of occurrence.
Note on D49: Brad: Minimal impact to cost, schedule, or technical result.
Note on E49: Brad: Some impact to cost, schedule, or technical result. Recoverable within program or project scope.
Note on F49: Brad: Moderate impact to cost, schedule, or technical result. Requires significant program or project resources to recover.
Note on G49: Brad: Significant impact to cost, schedule, or technical results of program or project. Goals or objectives not fully achievable.
Note on H49: Brad: Extreme impact to cost, schedule, or technical results of project or program. Not recoverable with program or project resources. Jeopardizes or fails to meet project or program objectives.